## User Stories Import
Story ID | Work Type * | Epic | Summary * | Description * | Acceptance Criteria * | Priority * | Story Points * | Assignee Name * | Sprint | Status * | Labels
US-101 | Story | Platform Access | Student registration and login | As a student, I want to register and sign in with my own credentials so that I can reach my workspace securely. | 1. Valid credentials sign the student in. 2. Invalid credentials show a clear error. 3. A session is created and expires after inactivity. 4. Passwords are stored only as salted hashes. | High | 5 | A. DHANUSH | Sprint 1 | To Do | rag,auth,frontend
US-102 | Story | Platform Access | Password reset | As a student, I want to reset a forgotten password so that I can regain access without an administrator. | 1. A reset link or OTP is sent to the registered contact. 2. The link expires after a set time. 3. A new password can be saved and used to sign in. 4. Reset attempts are recorded in the audit log. | Medium | 3 | ALE VIJAYALAXMI | Sprint 1 | To Do | auth,security
US-103 | Story | Platform Access | Role-based access for faculty coordinator | As a faculty coordinator, I want a separate privileged view so that I can manage records without using a student account. | 1. Student and faculty coordinator roles see different menus. 2. Privileged actions are refused for a normal student. 3. Every privileged action is written to an audit trail. | High | 5 | BURRI MALLIKARJUN | Sprint 1 | To Do | auth,rbac
US-104 | Story | Documents Intake | Submit academic documents | As a student, I want to submit academic documents to the system so that they can be processed. | 1. Supported formats are accepted and stored. 2. Unsupported or oversized input is refused with a reason. 3. Each submission is timestamped and linked to its owner. 4. A confirmation is shown once the upload completes. | Highest | 5 | ATRAGADA NAGATRIMURTHULU | Sprint 1 | To Do | rag,ingestion
US-105 | Story | Documents Intake | Validate and clean academic documents | As a system, I want to validate and clean incoming academic documents so that poor quality input does not corrupt later stages. | 1. Missing and malformed fields are detected. 2. Duplicates are removed before processing. 3. A validation summary is available for each batch. 4. Rejected records are retained for review. | High | 5 | A. DHANUSH | Sprint 1 | To Do | validation,data
US-106 | Task | Documents Intake | Project repository and environment setup | As a developer, I want a version-controlled repository with a reproducible environment so that the whole team builds on the same base. | 1. Repository created and branch rules agreed. 2. Dependencies pinned in a requirements file. 3. The project runs from a clean checkout by following the README. | Medium | 3 | ALE VIJAYALAXMI | Sprint 1 | To Do | setup,devops
US-107 | Spike | Document Ingestion | Evaluate approaches for document ingestion | Research candidate approaches for document ingestion and record which one this project adopts. Existing work applies RAG to general question answering and context compression. None of the surveyed systems combines document ingestion, syllabus-grounded tutoring and progress. | 1. At least three approaches are compared. 2. Strengths and limits of each are written up. 3. A recommendation with reasons is recorded. | Low | 3 | BURRI MALLIKARJUN | Sprint 2 | To Do | research,spike
US-108 | Story | Document Ingestion | Build a document ingestion module | As a developer, I want to build a document ingestion module that parses syllabi, lecture notes and question banks and extracts subjects, units and topics so that the rest of the document ingestion pipeline can depend on it. | 1. The delivered system provides a document ingestion module that parses syllabi, lecture notes and question banks and extracts subjects, units and topics. 2. Invalid or missing academic documents are rejected with a clear message. 3. Behaviour is verified on a representative sample of academic documents. 4. Errors are logged with enough context to debug them. | Highest | 8 | ATRAGADA NAGATRIMURTHULU | Sprint 2 | To Do | rag,learning,nlp
US-109 | Story | Document Ingestion | Store the extracted content as vector embeddings | As a system, I want to store the extracted content as vector embeddings so that material can be searched semantically rather than by keyword. | 1. The system stores the extracted content as vector embeddings. 2. The step runs end to end on the full project dataset. 3. Results are persisted and can be retrieved later. 4. The run is reproducible from a fixed configuration. | High | 8 | A. DHANUSH | Sprint 2 | To Do | rag,learning,nlp
US-110 | Story | Document Ingestion | Implement a RAG question-answering engine | As a developer, I want to implement a RAG question-answering engine that answers strictly from the uploaded material and cites the source so that academic documents are processed consistently. | 1. The delivered system provides a RAG question-answering engine that answers strictly from the uploaded material and cites the source. 2. Configuration values are read from settings rather than hard-coded. 3. Edge cases found during testing are handled. 4. The faculty coordinator can inspect the outcome. | High | 8 | ALE VIJAYALAXMI | Sprint 2 | To Do | rag,learning,nlp
US-111 | Story | Document Ingestion | Apply semantic context compression | As a system, I want to apply semantic context compression so that retrieval stays accurate without exceeding the model context window. | 1. The system applies semantic context compression. 2. Processing completes within the agreed time budget. 3. The module has unit tests covering its main paths. 4. The step is documented in the project README. | High | 8 | BURRI MALLIKARJUN | Sprint 3 | To Do | rag,learning,nlp
US-112 | Story | Document Ingestion | Generate personalised study roadmaps | As a system, I want to generate personalised study roadmaps and revision schedules from topic coverage and performance so that later features can build on a dependable output. | 1. The system generates personalised study roadmaps and revision schedules from topic coverage and performance. 2. Invalid or missing academic documents are rejected with a clear message. 3. Behaviour is verified on a representative sample of academic documents. 4. Errors are logged with enough context to debug them. | High | 8 | ATRAGADA NAGATRIMURTHULU | Sprint 3 | To Do | rag,learning,nlp
US-113 | Story | Document Ingestion | Present curriculum coverage | As a system, I want to present curriculum coverage, study velocity and engagement metrics on an interactive dashboard so that the requirement can be demonstrated at review. | 1. The system presents curriculum coverage, study velocity and engagement metrics on an interactive dashboard. 2. The step runs end to end on the full project dataset. 3. Results are persisted and can be retrieved later. 4. The run is reproducible from a fixed configuration. | High | 8 | A. DHANUSH | Sprint 3 | To Do | rag,learning,nlp
US-114 | Story | Document Ingestion | Review document ingestion output | As a student, I want to review the document ingestion output in the interface so that I can confirm it before acting on it. | 1. The most recent output is shown together with its inputs. 2. The student can flag an incorrect result. 3. Flagged items are queued for the faculty coordinator to check. | Medium | 5 | ALE VIJAYALAXMI | Sprint 2 | To Do | rag,backend
US-115 | Task | Document Ingestion | Retry and logging for document ingestion | As a system, I want to retry and log failures in document ingestion so that a transient error does not lose data. | 1. Failed operations retry with backoff. 2. Repeated failures raise an alert. 3. Every failure is logged with its input reference. | Medium | 5 | BURRI MALLIKARJUN | Sprint 3 | To Do | rag,backend
US-116 | Story | Document Ingestion | Tune document ingestion | As a developer, I want to tune document ingestion on validation data so that accuracy improves before release. | 1. A parameter search is run and recorded. 2. Before and after metrics are compared. 3. The chosen settings are committed to the repository. | Medium | 5 | ATRAGADA NAGATRIMURTHULU | Sprint 3 | To Do | rag,backend
US-117 | Task | Document Ingestion | Expose document ingestion through an API | As a developer, I want to expose document ingestion through an internal API so that the interface and other modules can consume it. | 1. Endpoint documented with request and response examples. 2. Errors return meaningful status codes. 3. The endpoint is covered by an integration test. | Medium | 5 | A. DHANUSH | Sprint 3 | To Do | rag,backend
US-118 | Story | Results and Reporting | Results dashboard | As a student, I want a dashboard summarising the latest results so that I can understand the outcome at a glance. | 1. Key figures are shown with the date of the run. 2. Charts render correctly for an empty and a full dataset. 3. The dashboard loads within an acceptable time. | High | 5 | ALE VIJAYALAXMI | Sprint 4 | To Do | dashboard,frontend
US-119 | Story | Results and Reporting | Export report | As a faculty coordinator, I want to export the results as PDF or CSV so that I can share them outside the system. | 1. The export includes the figures shown on screen. 2. The file name carries the project and the date. 3. Large exports complete without timing out. | Medium | 3 | BURRI MALLIKARJUN | Sprint 4 | To Do | export,reporting
US-120 | Story | Results and Reporting | History and search | As a student, I want to search past records so that I can compare an earlier result with the current one. | 1. Records can be filtered by date and by status. 2. Search returns promptly on the full dataset. 3. An empty result set is shown clearly. | Medium | 3 | ATRAGADA NAGATRIMURTHULU | Sprint 4 | To Do | search,frontend
US-121 | Story | Notifications | Notify student of an important outcome | As a student, I want to be notified when the system produces an outcome needing my attention so that I can respond promptly. | 1. A notification is raised when the configured condition is met. 2. The student can see the notification history. 3. Repeated notifications for the same event are suppressed. | Medium | 3 | A. DHANUSH | Sprint 4 | To Do | notification,alerts
US-122 | Spike | Evaluation | Define and measure evaluation metrics | Decide which metrics judge this project and measure the current build against them. | 1. Metrics chosen and justified for this problem. 2. Current scores recorded as a baseline. 3. A target for the final review is agreed. | Low | 3 | ALE VIJAYALAXMI | Sprint 5 | To Do | evaluation,research
US-123 | Task | Release | Deployment and user documentation | As a developer, I want the system deployed with setup and usage documentation so that the evaluators can run and demonstrate it. | 1. The application runs on the target environment. 2. Setup steps are documented and verified from scratch. 3. A short user guide covers the main workflow. | Low | 2 | BURRI MALLIKARJUN | Sprint 5 | To Do | deployment,docs

## Field Guide
BharatBuild — User Stories Excel Import Guide
Fields marked with * are mandatory. Assignee Roll No and Assignee Name must match a registered student in the selected batch.
Field | Mandatory | Example | Validation / Usage
Story ID | No | US-101 | Optional unique reference. BharatBuild may generate one if blank.
Work Type | Yes | Story | Allowed: Story, Task, Spike.
Epic | No | Authentication | Existing or importable epic/feature grouping.
Summary | Yes | Student Login and Authentication | Short title of the user story.
Description | Yes | As a student, I want to... | Detailed functional/user-story description.
Acceptance Criteria | Yes | 1. Valid login... | Use numbered lines in one cell.
Priority | Yes | High | Highest, High, Medium, Low, Lowest.
Story Points | Yes | 5 | Numeric estimate; recommended Fibonacci values such as 1,2,3,5,8,13.
Assignee Roll No | Yes | 23K91A05L5 | Must belong to the currently selected project batch.
Assignee Name | Yes | Royyala Sindhuja | Must match the student identified by Assignee Roll No.
Sprint | No | Sprint 1 | If blank, story remains unscheduled/backlog.
Status | Yes | To Do | Allowed: To Do, In Progress, In Review, Done.
Labels | No | authentication,frontend | Comma-separated tags.

## Import Process
Trainer Import Workflow
Step | Action | Expected Result
1 | Select Department → Section → Batch → Project | BharatBuild establishes project context.
2 | Open User Stories → Import Stories | Import wizard opens.
3 | Upload this Excel file | Columns are detected automatically.
4 | Map Excel columns | Excel fields are mapped to BharatBuild story fields.
5 | Validate | Missing mandatory data, duplicate IDs and invalid assignees are flagged.
6 | Preview | Trainer reviews stories and student assignments.
7 | Confirm Import | Valid stories are created under the selected project.