## User Stories Import
Story ID | Work Type * | Epic | Summary * | Description * | Acceptance Criteria * | Priority * | Story Points * | Assignee Name * | Sprint | Status * | Labels
US-101 | Story | Platform Access | Commuter registration and login | As a commuter, I want to register and sign in with my own credentials so that I can reach my workspace securely. | 1. Valid credentials sign the commuter in. 2. Invalid credentials show a clear error. 3. A session is created and expires after inactivity. 4. Passwords are stored only as salted hashes. | High | 5 | Buneti Harshitha | Sprint 1 | To Do | traffic,auth,frontend
US-102 | Story | Platform Access | Password reset | As a commuter, I want to reset a forgotten password so that I can regain access without an administrator. | 1. A reset link or OTP is sent to the registered contact. 2. The link expires after a set time. 3. A new password can be saved and used to sign in. 4. Reset attempts are recorded in the audit log. | Medium | 3 | Bhuvaneshwari Kadike | Sprint 1 | To Do | auth,security
US-103 | Story | Platform Access | Role-based access for traffic operator | As a traffic operator, I want a separate privileged view so that I can manage records without using a commuter account. | 1. Commuter and traffic operator roles see different menus. 2. Privileged actions are refused for a normal commuter. 3. Every privileged action is written to an audit trail. | High | 5 | Ambati Sai Nikhil | Sprint 1 | To Do | auth,rbac
US-104 | Story | Feeds Intake | Submit junction video feeds | As a commuter, I want to submit junction video feeds to the system so that they can be processed. | 1. Supported formats are accepted and stored. 2. Unsupported or oversized input is refused with a reason. 3. Each submission is timestamped and linked to its owner. 4. A confirmation is shown once the upload completes. | Highest | 5 | Chapala Rohith Reddy | Sprint 1 | To Do | traffic,ingestion
US-105 | Story | Feeds Intake | Validate and clean junction video feeds | As a system, I want to validate and clean incoming junction video feeds so that poor quality input does not corrupt later stages. | 1. Missing and malformed fields are detected. 2. Duplicates are removed before processing. 3. A validation summary is available for each batch. 4. Rejected records are retained for review. | High | 5 | Buneti Harshitha | Sprint 1 | To Do | validation,data
US-106 | Task | Feeds Intake | Project repository and environment setup | As a developer, I want a version-controlled repository with a reproducible environment so that the whole team builds on the same base. | 1. Repository created and branch rules agreed. 2. Dependencies pinned in a requirements file. 3. The project runs from a clean checkout by following the README. | Medium | 3 | Bhuvaneshwari Kadike | Sprint 1 | To Do | setup,devops
US-107 | Spike | Signal Control | Evaluate approaches for signal control | Research candidate approaches for signal control and record which one this project adopts. The surveyed systems perform adaptive signal control or vehicle detection separately. The gap is one pipeline that detects, adapts timing, prioritises emergency vehicles and. | 1. At least three approaches are compared. 2. Strengths and limits of each are written up. 3. A recommendation with reasons is recorded. | Low | 3 | Ambati Sai Nikhil | Sprint 2 | To Do | research,spike
US-108 | Story | Signal Control | Ingest live video from junction cameras and detect | As a system, I want to ingest live video from junction cameras and detect and count vehicles using a YOLO-based model so that the rest of the signal control pipeline can depend on it. | 1. The system ingests live video from junction cameras and detect and count vehicles using a YOLO-based model. 2. Invalid or missing junction video feeds are rejected with a clear message. 3. Behaviour is verified on a representative sample of junction video feeds. 4. Errors are logged with enough context to debug them. | Highest | 8 | Chapala Rohith Reddy | Sprint 2 | To Do | traffic,cv,iot
US-109 | Story | Signal Control | Estimate traffic density per approach lane | As a system, I want to estimate traffic density per approach lane from the detection output so that the capability is available to the modules that follow. | 1. The system estimates traffic density per approach lane from the detection output. 2. The step runs end to end on the full project dataset. 3. Results are persisted and can be retrieved later. 4. The run is reproducible from a fixed configuration. | High | 8 | Buneti Harshitha | Sprint 2 | To Do | traffic,cv,iot
US-110 | Story | Signal Control | Compute adaptive signal timings | As a system, I want to compute adaptive signal timings that allocate green time in proportion to measured density so that junction video feeds are processed consistently. | 1. The system computes adaptive signal timings that allocate green time in proportion to measured density. 2. Configuration values are read from settings rather than hard-coded. 3. Edge cases found during testing are handled. 4. The traffic operator can inspect the outcome. | High | 8 | Bhuvaneshwari Kadike | Sprint 2 | To Do | traffic,cv,iot
US-111 | Story | Signal Control | Detect emergency vehicles | As a system, I want to detect emergency vehicles and grant priority passage through the junction so that the behaviour is correct for both typical and edge inputs. | 1. The system detects emergency vehicles and grant priority passage through the junction. 2. Processing completes within the agreed time budget. 3. The module has unit tests covering its main paths. 4. The step is documented in the project README. | High | 8 | Ambati Sai Nikhil | Sprint 3 | To Do | traffic,cv,iot
US-112 | Story | Signal Control | Enable coordination between adjacent junctions | As a system, I want to enable coordination between adjacent junctions to smooth traffic along a corridor so that later features can build on a dependable output. | 1. The system enables coordination between adjacent junctions to smooth traffic along a corridor. 2. Invalid or missing junction video feeds are rejected with a clear message. 3. Behaviour is verified on a representative sample of junction video feeds. 4. Errors are logged with enough context to debug them. | High | 8 | Chapala Rohith Reddy | Sprint 3 | To Do | traffic,cv,iot
US-113 | Story | Signal Control | Evaluate detection accuracy | As a developer, I want to evaluate detection accuracy, average waiting time and emergency vehicle clearance time so that the requirement can be demonstrated at review. | 1. The team has evaluated detection accuracy, average waiting time and emergency vehicle clearance time. 2. The step runs end to end on the full project dataset. 3. Results are persisted and can be retrieved later. 4. The run is reproducible from a fixed configuration. | High | 8 | Buneti Harshitha | Sprint 3 | To Do | traffic,cv,iot
US-114 | Story | Signal Control | Review signal control output | As a commuter, I want to review the signal control output in the interface so that I can confirm it before acting on it. | 1. The most recent output is shown together with its inputs. 2. The commuter can flag an incorrect result. 3. Flagged items are queued for the traffic operator to check. | Medium | 5 | Bhuvaneshwari Kadike | Sprint 2 | To Do | traffic,backend
US-115 | Task | Signal Control | Retry and logging for signal control | As a system, I want to retry and log failures in signal control so that a transient error does not lose data. | 1. Failed operations retry with backoff. 2. Repeated failures raise an alert. 3. Every failure is logged with its input reference. | Medium | 5 | Ambati Sai Nikhil | Sprint 3 | To Do | traffic,backend
US-116 | Story | Signal Control | Tune signal control | As a developer, I want to tune signal control on validation data so that accuracy improves before release. | 1. A parameter search is run and recorded. 2. Before and after metrics are compared. 3. The chosen settings are committed to the repository. | Medium | 5 | Chapala Rohith Reddy | Sprint 3 | To Do | traffic,backend
US-117 | Task | Signal Control | Expose signal control through an API | As a developer, I want to expose signal control through an internal API so that the interface and other modules can consume it. | 1. Endpoint documented with request and response examples. 2. Errors return meaningful status codes. 3. The endpoint is covered by an integration test. | Medium | 5 | Buneti Harshitha | Sprint 3 | To Do | traffic,backend
US-118 | Story | Results and Reporting | Results dashboard | As a commuter, I want a dashboard summarising the latest results so that I can understand the outcome at a glance. | 1. Key figures are shown with the date of the run. 2. Charts render correctly for an empty and a full dataset. 3. The dashboard loads within an acceptable time. | High | 5 | Bhuvaneshwari Kadike | Sprint 4 | To Do | dashboard,frontend
US-119 | Story | Results and Reporting | Export report | As a traffic operator, I want to export the results as PDF or CSV so that I can share them outside the system. | 1. The export includes the figures shown on screen. 2. The file name carries the project and the date. 3. Large exports complete without timing out. | Medium | 3 | Ambati Sai Nikhil | Sprint 4 | To Do | export,reporting
US-120 | Story | Results and Reporting | History and search | As a commuter, I want to search past records so that I can compare an earlier result with the current one. | 1. Records can be filtered by date and by status. 2. Search returns promptly on the full dataset. 3. An empty result set is shown clearly. | Medium | 3 | Chapala Rohith Reddy | Sprint 4 | To Do | search,frontend
US-121 | Story | Notifications | Notify commuter of an important outcome | As a commuter, I want to be notified when the system produces an outcome needing my attention so that I can respond promptly. | 1. A notification is raised when the configured condition is met. 2. The commuter can see the notification history. 3. Repeated notifications for the same event are suppressed. | Medium | 3 | Buneti Harshitha | Sprint 4 | To Do | notification,alerts
US-122 | Spike | Evaluation | Define and measure evaluation metrics | Decide which metrics judge this project and measure the current build against them. | 1. Metrics chosen and justified for this problem. 2. Current scores recorded as a baseline. 3. A target for the final review is agreed. | Low | 3 | Bhuvaneshwari Kadike | Sprint 5 | To Do | evaluation,research
US-123 | Task | Release | Deployment and user documentation | As a developer, I want the system deployed with setup and usage documentation so that the evaluators can run and demonstrate it. | 1. The application runs on the target environment. 2. Setup steps are documented and verified from scratch. 3. A short user guide covers the main workflow. | Low | 2 | Ambati Sai Nikhil | Sprint 5 | To Do | deployment,docs

## Field Guide
BharatBuild — User Stories Excel Import Guide
Fields marked with * are mandatory. Assignee Roll No and Assignee Name must match a registered student in the selected batch.
Field | Mandatory | Example | Validation / Usage
Story ID | No | US-101 | Optional unique reference. BharatBuild may generate one if blank.
Work Type | Yes | Story | Allowed: Story, Task, Spike.
Epic | No | Authentication | Existing or importable epic/feature grouping.
Summary | Yes | Student Login and Authentication | Short title of the user story.
Description | Yes | As a student, I want to... | Detailed functional/user-story description.
Acceptance Criteria | Yes | 1. Valid login... | Use numbered lines in one cell.
Priority | Yes | High | Highest, High, Medium, Low, Lowest.
Story Points | Yes | 5 | Numeric estimate; recommended Fibonacci values such as 1,2,3,5,8,13.
Assignee Roll No | Yes | 23K91A05L5 | Must belong to the currently selected project batch.
Assignee Name | Yes | Royyala Sindhuja | Must match the student identified by Assignee Roll No.
Sprint | No | Sprint 1 | If blank, story remains unscheduled/backlog.
Status | Yes | To Do | Allowed: To Do, In Progress, In Review, Done.
Labels | No | authentication,frontend | Comma-separated tags.

## Import Process
Trainer Import Workflow
Step | Action | Expected Result
1 | Select Department → Section → Batch → Project | BharatBuild establishes project context.
2 | Open User Stories → Import Stories | Import wizard opens.
3 | Upload this Excel file | Columns are detected automatically.
4 | Map Excel columns | Excel fields are mapped to BharatBuild story fields.
5 | Validate | Missing mandatory data, duplicate IDs and invalid assignees are flagged.
6 | Preview | Trainer reviews stories and student assignments.
7 | Confirm Import | Valid stories are created under the selected project.