## User Stories Import
Story ID | Work Type * | Epic | Summary * | Description * | Acceptance Criteria * | Priority * | Story Points * | Assignee Name * | Sprint | Status * | Labels
US-101 | Story | Platform Access | Developer registration and login | As a developer, I want to register and sign in with my own credentials so that I can reach my workspace securely. | 1. Valid credentials sign the developer in. 2. Invalid credentials show a clear error. 3. A session is created and expires after inactivity. 4. Passwords are stored only as salted hashes. | High | 5 | BODA SANDEEP | Sprint 1 | To Do | llm,auth,frontend
US-102 | Story | Platform Access | Password reset | As a developer, I want to reset a forgotten password so that I can regain access without an administrator. | 1. A reset link or OTP is sent to the registered contact. 2. The link expires after a set time. 3. A new password can be saved and used to sign in. 4. Reset attempts are recorded in the audit log. | Medium | 3 | NARISIMHA REDDY | Sprint 1 | To Do | auth,security
US-103 | Story | Platform Access | Role-based access for security reviewer | As a security reviewer, I want a separate privileged view so that I can manage records without using a developer account. | 1. Developer and security reviewer roles see different menus. 2. Privileged actions are refused for a normal developer. 3. Every privileged action is written to an audit trail. | High | 5 | CHEPURI RISHIVARDHAN | Sprint 1 | To Do | auth,rbac
US-104 | Story | Diffs Intake | Submit pull request diffs | As a developer, I want to submit pull request diffs to the system so that they can be processed. | 1. Supported formats are accepted and stored. 2. Unsupported or oversized input is refused with a reason. 3. Each submission is timestamped and linked to its owner. 4. A confirmation is shown once the upload completes. | Highest | 5 | DHARAVATH SEETHARAM | Sprint 1 | To Do | llm,ingestion
US-105 | Story | Diffs Intake | Validate and clean pull request diffs | As a system, I want to validate and clean incoming pull request diffs so that poor quality input does not corrupt later stages. | 1. Missing and malformed fields are detected. 2. Duplicates are removed before processing. 3. A validation summary is available for each batch. 4. Rejected records are retained for review. | High | 5 | BODA SANDEEP | Sprint 1 | To Do | validation,data
US-106 | Task | Diffs Intake | Project repository and environment setup | As a developer, I want a version-controlled repository with a reproducible environment so that the whole team builds on the same base. | 1. Repository created and branch rules agreed. 2. Dependencies pinned in a requirements file. 3. The project runs from a clean checkout by following the README. | Medium | 3 | NARISIMHA REDDY | Sprint 1 | To Do | setup,devops
US-107 | Spike | Code Analysis | Evaluate approaches for code analysis | Research candidate approaches for code analysis and record which one this project adopts. The surveyed work predicts vulnerabilities from code metrics offline. The gap is applying that signal inside the live pull request workflow, combined with agentic review that explains. | 1. At least three approaches are compared. 2. Strengths and limits of each are written up. 3. A recommendation with reasons is recorded. | Low | 3 | CHEPURI RISHIVARDHAN | Sprint 2 | To Do | research,spike
US-108 | Story | Code Analysis | Extract changed files and diff context automatically | As a system, I want to extract changed files and diff context automatically when a pull request is opened so that the rest of the code analysis pipeline can depend on it. | 1. The system extracts changed files and diff context automatically when a pull request is opened. 2. Invalid or missing pull request diffs are rejected with a clear message. 3. Behaviour is verified on a representative sample of pull request diffs. 4. Errors are logged with enough context to debug them. | Highest | 8 | DHARAVATH SEETHARAM | Sprint 2 | To Do | llm,security,devops
US-109 | Story | Code Analysis | Compute source-code metrics for changed files | As a system, I want to compute source-code metrics for changed files and use them to rank vulnerability likelihood so that the capability is available to the modules that follow. | 1. The system computes source-code metrics for changed files and use them to rank vulnerability likelihood. 2. The step runs end to end on the full project dataset. 3. Results are persisted and can be retrieved later. 4. The run is reproducible from a fixed configuration. | High | 8 | BODA SANDEEP | Sprint 2 | To Do | llm,security,devops
US-110 | Story | Code Analysis | Perform AST-based static analysis to detect injection | As a system, I want to perform AST-based static analysis to detect injection, access-control and validation flaws so that pull request diffs are processed consistently. | 1. The system performs AST-based static analysis to detect injection, access-control and validation flaws. 2. Configuration values are read from settings rather than hard-coded. 3. Edge cases found during testing are handled. 4. The security reviewer can inspect the outcome. | High | 8 | NARISIMHA REDDY | Sprint 2 | To Do | llm,security,devops
US-111 | Story | Code Analysis | Deploy multiple LLM agents covering security | As a developer, I want to deploy multiple LLM agents covering security, code quality and maintainability concerns so that the behaviour is correct for both typical and edge inputs. | 1. The delivered system provides multiple LLM agents covering security, code quality and maintainability concerns. 2. Processing completes within the agreed time budget. 3. The module has unit tests covering its main paths. 4. The step is documented in the project README. | High | 8 | CHEPURI RISHIVARDHAN | Sprint 3 | To Do | llm,security,devops
US-112 | Story | Code Analysis | Retrieve related code from the repository | As a system, I want to retrieve related code from the repository so that review comments reflect the wider codebase. | 1. The system retrieves related code from the repository. 2. Invalid or missing pull request diffs are rejected with a clear message. 3. Behaviour is verified on a representative sample of pull request diffs. 4. Errors are logged with enough context to debug them. | High | 8 | DHARAVATH SEETHARAM | Sprint 3 | To Do | llm,security,devops
US-113 | Story | Code Analysis | Post consolidated review comments | As a system, I want to post consolidated review comments and evaluate precision against manually reviewed pull requests so that the requirement can be demonstrated at review. | 1. The system posts consolidated review comments and evaluate precision against manually reviewed pull requests. 2. The step runs end to end on the full project dataset. 3. Results are persisted and can be retrieved later. 4. The run is reproducible from a fixed configuration. | High | 8 | BODA SANDEEP | Sprint 3 | To Do | llm,security,devops
US-114 | Story | Code Analysis | Review code analysis output | As a developer, I want to review the code analysis output in the interface so that I can confirm it before acting on it. | 1. The most recent output is shown together with its inputs. 2. The developer can flag an incorrect result. 3. Flagged items are queued for the security reviewer to check. | Medium | 5 | NARISIMHA REDDY | Sprint 2 | To Do | llm,backend
US-115 | Task | Code Analysis | Retry and logging for code analysis | As a system, I want to retry and log failures in code analysis so that a transient error does not lose data. | 1. Failed operations retry with backoff. 2. Repeated failures raise an alert. 3. Every failure is logged with its input reference. | Medium | 5 | CHEPURI RISHIVARDHAN | Sprint 3 | To Do | llm,backend
US-116 | Story | Code Analysis | Tune code analysis | As a developer, I want to tune code analysis on validation data so that accuracy improves before release. | 1. A parameter search is run and recorded. 2. Before and after metrics are compared. 3. The chosen settings are committed to the repository. | Medium | 5 | DHARAVATH SEETHARAM | Sprint 3 | To Do | llm,backend
US-117 | Task | Code Analysis | Expose code analysis through an API | As a developer, I want to expose code analysis through an internal API so that the interface and other modules can consume it. | 1. Endpoint documented with request and response examples. 2. Errors return meaningful status codes. 3. The endpoint is covered by an integration test. | Medium | 5 | BODA SANDEEP | Sprint 3 | To Do | llm,backend
US-118 | Story | Results and Reporting | Results dashboard | As a developer, I want a dashboard summarising the latest results so that I can understand the outcome at a glance. | 1. Key figures are shown with the date of the run. 2. Charts render correctly for an empty and a full dataset. 3. The dashboard loads within an acceptable time. | High | 5 | NARISIMHA REDDY | Sprint 4 | To Do | dashboard,frontend
US-119 | Story | Results and Reporting | Export report | As a security reviewer, I want to export the results as PDF or CSV so that I can share them outside the system. | 1. The export includes the figures shown on screen. 2. The file name carries the project and the date. 3. Large exports complete without timing out. | Medium | 3 | CHEPURI RISHIVARDHAN | Sprint 4 | To Do | export,reporting
US-120 | Story | Results and Reporting | History and search | As a developer, I want to search past records so that I can compare an earlier result with the current one. | 1. Records can be filtered by date and by status. 2. Search returns promptly on the full dataset. 3. An empty result set is shown clearly. | Medium | 3 | DHARAVATH SEETHARAM | Sprint 4 | To Do | search,frontend
US-121 | Story | Notifications | Notify developer of an important outcome | As a developer, I want to be notified when the system produces an outcome needing my attention so that I can respond promptly. | 1. A notification is raised when the configured condition is met. 2. The developer can see the notification history. 3. Repeated notifications for the same event are suppressed. | Medium | 3 | BODA SANDEEP | Sprint 4 | To Do | notification,alerts
US-122 | Spike | Evaluation | Define and measure evaluation metrics | Decide which metrics judge this project and measure the current build against them. | 1. Metrics chosen and justified for this problem. 2. Current scores recorded as a baseline. 3. A target for the final review is agreed. | Low | 3 | NARISIMHA REDDY | Sprint 5 | To Do | evaluation,research
US-123 | Task | Release | Deployment and user documentation | As a developer, I want the system deployed with setup and usage documentation so that the evaluators can run and demonstrate it. | 1. The application runs on the target environment. 2. Setup steps are documented and verified from scratch. 3. A short user guide covers the main workflow. | Low | 2 | CHEPURI RISHIVARDHAN | Sprint 5 | To Do | deployment,docs

## Field Guide
BharatBuild — User Stories Excel Import Guide
Fields marked with * are mandatory. Assignee Roll No and Assignee Name must match a registered student in the selected batch.
Field | Mandatory | Example | Validation / Usage
Story ID | No | US-101 | Optional unique reference. BharatBuild may generate one if blank.
Work Type | Yes | Story | Allowed: Story, Task, Spike.
Epic | No | Authentication | Existing or importable epic/feature grouping.
Summary | Yes | Student Login and Authentication | Short title of the user story.
Description | Yes | As a student, I want to... | Detailed functional/user-story description.
Acceptance Criteria | Yes | 1. Valid login... | Use numbered lines in one cell.
Priority | Yes | High | Highest, High, Medium, Low, Lowest.
Story Points | Yes | 5 | Numeric estimate; recommended Fibonacci values such as 1,2,3,5,8,13.
Assignee Roll No | Yes | 23K91A05L5 | Must belong to the currently selected project batch.
Assignee Name | Yes | Royyala Sindhuja | Must match the student identified by Assignee Roll No.
Sprint | No | Sprint 1 | If blank, story remains unscheduled/backlog.
Status | Yes | To Do | Allowed: To Do, In Progress, In Review, Done.
Labels | No | authentication,frontend | Comma-separated tags.

## Import Process
Trainer Import Workflow
Step | Action | Expected Result
1 | Select Department → Section → Batch → Project | BharatBuild establishes project context.
2 | Open User Stories → Import Stories | Import wizard opens.
3 | Upload this Excel file | Columns are detected automatically.
4 | Map Excel columns | Excel fields are mapped to BharatBuild story fields.
5 | Validate | Missing mandatory data, duplicate IDs and invalid assignees are flagged.
6 | Preview | Trainer reviews stories and student assignments.
7 | Confirm Import | Valid stories are created under the selected project.