## User Stories Import
Story ID | Work Type * | Epic | Summary * | Description * | Acceptance Criteria * | Priority * | Story Points * | Assignee Name * | Sprint | Status * | Labels
US-101 | Story | Platform Access | Radiologist registration and login | As a radiologist, I want to register and sign in with my own credentials so that I can reach my workspace securely. | 1. Valid credentials sign the radiologist in. 2. Invalid credentials show a clear error. 3. A session is created and expires after inactivity. 4. Passwords are stored only as salted hashes. | High | 5 | CH. Akshitha | Sprint 1 | To Do | cnn,auth,frontend
US-102 | Story | Platform Access | Password reset | As a radiologist, I want to reset a forgotten password so that I can regain access without an administrator. | 1. A reset link or OTP is sent to the registered contact. 2. The link expires after a set time. 3. A new password can be saved and used to sign in. 4. Reset attempts are recorded in the audit log. | Medium | 3 | B. SATVIK KUMAR | Sprint 1 | To Do | auth,security
US-103 | Story | Platform Access | Role-based access for hospital administrator | As a hospital administrator, I want a separate privileged view so that I can manage records without using a radiologist account. | 1. Radiologist and hospital administrator roles see different menus. 2. Privileged actions are refused for a normal radiologist. 3. Every privileged action is written to an audit trail. | High | 5 | A. ABHITHEJ REDDY | Sprint 1 | To Do | auth,rbac
US-104 | Story | Images Intake | Submit chest X-ray images | As a radiologist, I want to submit chest X-ray images to the system so that they can be processed. | 1. Supported formats are accepted and stored. 2. Unsupported or oversized input is refused with a reason. 3. Each submission is timestamped and linked to its owner. 4. A confirmation is shown once the upload completes. | Highest | 5 | D. LIKHITHA | Sprint 1 | To Do | cnn,ingestion
US-105 | Story | Images Intake | Validate and clean chest X-ray images | As a system, I want to validate and clean incoming chest X-ray images so that poor quality input does not corrupt later stages. | 1. Missing and malformed fields are detected. 2. Duplicates are removed before processing. 3. A validation summary is available for each batch. 4. Rejected records are retained for review. | High | 5 | CH. Akshitha | Sprint 1 | To Do | validation,data
US-106 | Task | Images Intake | Project repository and environment setup | As a developer, I want a version-controlled repository with a reproducible environment so that the whole team builds on the same base. | 1. Repository created and branch rules agreed. 2. Dependencies pinned in a requirements file. 3. The project runs from a clean checkout by following the README. | Medium | 3 | B. SATVIK KUMAR | Sprint 1 | To Do | setup,devops
US-107 | Spike | Image Classification | Evaluate approaches for image classification | Research candidate approaches for image classification and record which one this project adopts. The surveyed work reports classification accuracy on public datasets. The gap is combining segmentation, calibrated uncertainty and visual explanation into a single deployable. | 1. At least three approaches are compared. 2. Strengths and limits of each are written up. 3. A recommendation with reasons is recorded. | Low | 3 | A. ABHITHEJ REDDY | Sprint 2 | To Do | research,spike
US-108 | Story | Image Classification | Acquire and preprocess a chest X-ray dataset | As a system, I want to acquire and preprocess a chest X-ray dataset with consistent resizing, normalisation and augmentation so that the rest of the image classification pipeline can depend on it. | 1. The team has acquired and preprocessed a chest X-ray dataset with consistent resizing, normalisation and augmentation. 2. Invalid or missing chest X-ray images are rejected with a clear message. 3. Behaviour is verified on a representative sample of chest X-ray images. 4. Errors are logged with enough context to debug them. | Highest | 8 | D. LIKHITHA | Sprint 2 | To Do | cnn,healthcare,imaging
US-109 | Story | Image Classification | Apply U-Net based lung segmentation | As a system, I want to apply U-Net based lung segmentation to isolate the region of interest before classification so that the capability is available to the modules that follow. | 1. The system applies U-Net based lung segmentation to isolate the region of interest before classification. 2. The step runs end to end on the full project dataset. 3. Results are persisted and can be retrieved later. 4. The run is reproducible from a fixed configuration. | High | 8 | CH. Akshitha | Sprint 2 | To Do | cnn,healthcare,imaging
US-110 | Story | Image Classification | Train a CNN classifier to distinguish pneumonia-positive | As a developer, I want to train a CNN classifier to distinguish pneumonia-positive from normal chest X-rays so that chest X-ray images are processed consistently. | 1. The team has trained a CNN classifier to distinguish pneumonia-positive from normal chest X-rays. 2. Configuration values are read from settings rather than hard-coded. 3. Edge cases found during testing are handled. 4. The hospital administrator can inspect the outcome. | High | 8 | B. SATVIK KUMAR | Sprint 2 | To Do | cnn,healthcare,imaging
US-111 | Story | Image Classification | Evaluate using accuracy, sensitivity, specificity | As a developer, I want to evaluate using accuracy, sensitivity, specificity, F1-score and a confusion matrix so that the behaviour is correct for both typical and edge inputs. | 1. The team has evaluated using accuracy, sensitivity, specificity, F1-score and a confusion matrix. 2. Processing completes within the agreed time budget. 3. The module has unit tests covering its main paths. 4. The step is documented in the project README. | High | 8 | A. ABHITHEJ REDDY | Sprint 3 | To Do | cnn,healthcare,imaging
US-112 | Story | Image Classification | Generate heatmap visualisations | As a system, I want to generate heatmap visualisations so that each prediction can be verified against the image. | 1. The system generates heatmap visualisations. 2. Invalid or missing chest X-ray images are rejected with a clear message. 3. Behaviour is verified on a representative sample of chest X-ray images. 4. Errors are logged with enough context to debug them. | High | 8 | D. LIKHITHA | Sprint 3 | To Do | cnn,healthcare,imaging
US-113 | Story | Image Classification | Deploy the model behind an interface | As a developer, I want to deploy the model behind an interface that returns the prediction with its confidence and heatmap so that the requirement can be demonstrated at review. | 1. The delivered system provides the model behind an interface that returns the prediction with its confidence and heatmap. 2. The step runs end to end on the full project dataset. 3. Results are persisted and can be retrieved later. 4. The run is reproducible from a fixed configuration. | High | 8 | CH. Akshitha | Sprint 3 | To Do | cnn,healthcare,imaging
US-114 | Story | Image Classification | Review image classification output | As a radiologist, I want to review the image classification output in the interface so that I can confirm it before acting on it. | 1. The most recent output is shown together with its inputs. 2. The radiologist can flag an incorrect result. 3. Flagged items are queued for the hospital administrator to check. | Medium | 5 | B. SATVIK KUMAR | Sprint 2 | To Do | cnn,backend
US-115 | Task | Image Classification | Retry and logging for image classification | As a system, I want to retry and log failures in image classification so that a transient error does not lose data. | 1. Failed operations retry with backoff. 2. Repeated failures raise an alert. 3. Every failure is logged with its input reference. | Medium | 5 | A. ABHITHEJ REDDY | Sprint 3 | To Do | cnn,backend
US-116 | Story | Image Classification | Tune image classification | As a developer, I want to tune image classification on validation data so that accuracy improves before release. | 1. A parameter search is run and recorded. 2. Before and after metrics are compared. 3. The chosen settings are committed to the repository. | Medium | 5 | D. LIKHITHA | Sprint 3 | To Do | cnn,backend
US-117 | Task | Image Classification | Expose image classification through an API | As a developer, I want to expose image classification through an internal API so that the interface and other modules can consume it. | 1. Endpoint documented with request and response examples. 2. Errors return meaningful status codes. 3. The endpoint is covered by an integration test. | Medium | 5 | CH. Akshitha | Sprint 3 | To Do | cnn,backend
US-118 | Story | Results and Reporting | Results dashboard | As a radiologist, I want a dashboard summarising the latest results so that I can understand the outcome at a glance. | 1. Key figures are shown with the date of the run. 2. Charts render correctly for an empty and a full dataset. 3. The dashboard loads within an acceptable time. | High | 5 | B. SATVIK KUMAR | Sprint 4 | To Do | dashboard,frontend
US-119 | Story | Results and Reporting | Export report | As a hospital administrator, I want to export the results as PDF or CSV so that I can share them outside the system. | 1. The export includes the figures shown on screen. 2. The file name carries the project and the date. 3. Large exports complete without timing out. | Medium | 3 | A. ABHITHEJ REDDY | Sprint 4 | To Do | export,reporting
US-120 | Story | Results and Reporting | History and search | As a radiologist, I want to search past records so that I can compare an earlier result with the current one. | 1. Records can be filtered by date and by status. 2. Search returns promptly on the full dataset. 3. An empty result set is shown clearly. | Medium | 3 | D. LIKHITHA | Sprint 4 | To Do | search,frontend
US-121 | Story | Notifications | Notify radiologist of an important outcome | As a radiologist, I want to be notified when the system produces an outcome needing my attention so that I can respond promptly. | 1. A notification is raised when the configured condition is met. 2. The radiologist can see the notification history. 3. Repeated notifications for the same event are suppressed. | Medium | 3 | CH. Akshitha | Sprint 4 | To Do | notification,alerts
US-122 | Spike | Evaluation | Define and measure evaluation metrics | Decide which metrics judge this project and measure the current build against them. | 1. Metrics chosen and justified for this problem. 2. Current scores recorded as a baseline. 3. A target for the final review is agreed. | Low | 3 | B. SATVIK KUMAR | Sprint 5 | To Do | evaluation,research
US-123 | Task | Release | Deployment and user documentation | As a developer, I want the system deployed with setup and usage documentation so that the evaluators can run and demonstrate it. | 1. The application runs on the target environment. 2. Setup steps are documented and verified from scratch. 3. A short user guide covers the main workflow. | Low | 2 | A. ABHITHEJ REDDY | Sprint 5 | To Do | deployment,docs

## Field Guide
BharatBuild — User Stories Excel Import Guide
Fields marked with * are mandatory. Assignee Roll No and Assignee Name must match a registered student in the selected batch.
Field | Mandatory | Example | Validation / Usage
Story ID | No | US-101 | Optional unique reference. BharatBuild may generate one if blank.
Work Type | Yes | Story | Allowed: Story, Task, Spike.
Epic | No | Authentication | Existing or importable epic/feature grouping.
Summary | Yes | Student Login and Authentication | Short title of the user story.
Description | Yes | As a student, I want to... | Detailed functional/user-story description.
Acceptance Criteria | Yes | 1. Valid login... | Use numbered lines in one cell.
Priority | Yes | High | Highest, High, Medium, Low, Lowest.
Story Points | Yes | 5 | Numeric estimate; recommended Fibonacci values such as 1,2,3,5,8,13.
Assignee Roll No | Yes | 23K91A05L5 | Must belong to the currently selected project batch.
Assignee Name | Yes | Royyala Sindhuja | Must match the student identified by Assignee Roll No.
Sprint | No | Sprint 1 | If blank, story remains unscheduled/backlog.
Status | Yes | To Do | Allowed: To Do, In Progress, In Review, Done.
Labels | No | authentication,frontend | Comma-separated tags.

## Import Process
Trainer Import Workflow
Step | Action | Expected Result
1 | Select Department → Section → Batch → Project | BharatBuild establishes project context.
2 | Open User Stories → Import Stories | Import wizard opens.
3 | Upload this Excel file | Columns are detected automatically.
4 | Map Excel columns | Excel fields are mapped to BharatBuild story fields.
5 | Validate | Missing mandatory data, duplicate IDs and invalid assignees are flagged.
6 | Preview | Trainer reviews stories and student assignments.
7 | Confirm Import | Valid stories are created under the selected project.