## User Stories Import
Story ID | Work Type * | Epic | Summary * | Description * | Acceptance Criteria * | Priority * | Story Points * | Assignee Name * | Sprint | Status * | Labels
US-101 | Story | Platform Access | Grid operator registration and login | As a grid operator, I want to register and sign in with my own credentials so that I can reach my workspace securely. | 1. Valid credentials sign the grid operator in. 2. Invalid credentials show a clear error. 3. A session is created and expires after inactivity. 4. Passwords are stored only as salted hashes. | High | 5 | Disha Kaushal | Sprint 1 | To Do | agents,auth,frontend
US-102 | Story | Platform Access | Password reset | As a grid operator, I want to reset a forgotten password so that I can regain access without an administrator. | 1. A reset link or OTP is sent to the registered contact. 2. The link expires after a set time. 3. A new password can be saved and used to sign in. 4. Reset attempts are recorded in the audit log. | Medium | 3 | Bollam Rakesh | Sprint 1 | To Do | auth,security
US-103 | Story | Platform Access | Role-based access for system administrator | As a system administrator, I want a separate privileged view so that I can manage records without using a grid operator account. | 1. Grid operator and system administrator roles see different menus. 2. Privileged actions are refused for a normal grid operator. 3. Every privileged action is written to an audit trail. | High | 5 | Chinnolla Ravindhar | Sprint 1 | To Do | auth,rbac
US-104 | Story | Telemetry Intake | Submit grid telemetry | As a grid operator, I want to submit grid telemetry to the system so that they can be processed. | 1. Supported formats are accepted and stored. 2. Unsupported or oversized input is refused with a reason. 3. Each submission is timestamped and linked to its owner. 4. A confirmation is shown once the upload completes. | Highest | 5 | Affan Mohammed Ramy | Sprint 1 | To Do | agents,ingestion
US-105 | Story | Telemetry Intake | Validate and clean grid telemetry | As a system, I want to validate and clean incoming grid telemetry so that poor quality input does not corrupt later stages. | 1. Missing and malformed fields are detected. 2. Duplicates are removed before processing. 3. A validation summary is available for each batch. 4. Rejected records are retained for review. | High | 5 | Disha Kaushal | Sprint 1 | To Do | validation,data
US-106 | Task | Telemetry Intake | Project repository and environment setup | As a developer, I want a version-controlled repository with a reproducible environment so that the whole team builds on the same base. | 1. Repository created and branch rules agreed. 2. Dependencies pinned in a requirements file. 3. The project runs from a clean checkout by following the README. | Medium | 3 | Bollam Rakesh | Sprint 1 | To Do | setup,devops
US-107 | Spike | Agent Routing | Evaluate approaches for agent routing | Research candidate approaches for agent routing and record which one this project adopts. The surveyed work builds multi-agent energy management for microgrids without a language-model planning layer. The gap is combining agentic planning with formal safety shielding and. | 1. At least three approaches are compared. 2. Strengths and limits of each are written up. 3. A recommendation with reasons is recorded. | Low | 3 | Chinnolla Ravindhar | Sprint 2 | To Do | research,spike
US-108 | Story | Agent Routing | Model the grid as a multi-agent system | As a system, I want to model the grid as a multi-agent system with agents responsible for generation, storage and load so that the rest of the agent routing pipeline can depend on it. | 1. The system models the grid as a multi-agent system with agents responsible for generation, storage and load. 2. Invalid or missing grid telemetry are rejected with a clear message. 3. Behaviour is verified on a representative sample of grid telemetry. 4. Errors are logged with enough context to debug them. | Highest | 8 | Affan Mohammed Ramy | Sprint 2 | To Do | agents,grid,xai
US-109 | Story | Agent Routing | Implement an LLM-driven planning agent | As a developer, I want to implement an LLM-driven planning agent that proposes routing actions from observed grid state so that the capability is available to the modules that follow. | 1. The delivered system provides an LLM-driven planning agent that proposes routing actions from observed grid state. 2. The step runs end to end on the full project dataset. 3. Results are persisted and can be retrieved later. 4. The run is reproducible from a fixed configuration. | High | 8 | Disha Kaushal | Sprint 2 | To Do | agents,grid,xai
US-110 | Story | Agent Routing | Add a safety shielding layer | As a developer, I want to add a safety shielding layer that validates each action against physical and operational constraints so that grid telemetry are processed consistently. | 1. The delivered system provides a safety shielding layer that validates each action against physical and operational constraints. 2. Configuration values are read from settings rather than hard-coded. 3. Edge cases found during testing are handled. 4. The system administrator can inspect the outcome. | High | 8 | Bollam Rakesh | Sprint 2 | To Do | agents,grid,xai
US-111 | Story | Agent Routing | Provide explanations for every routing decision | As a system, I want to provide explanations for every routing decision so that operators can audit the reasoning. | 1. The system provides explanations for every routing decision. 2. Processing completes within the agreed time budget. 3. The module has unit tests covering its main paths. 4. The step is documented in the project README. | High | 8 | Chinnolla Ravindhar | Sprint 3 | To Do | agents,grid,xai
US-112 | Story | Agent Routing | Simulate fault and overload scenarios | As a system, I want to simulate fault and overload scenarios to test dynamic rerouting behaviour so that later features can build on a dependable output. | 1. The system simulates fault and overload scenarios to test dynamic rerouting behaviour. 2. Invalid or missing grid telemetry are rejected with a clear message. 3. Behaviour is verified on a representative sample of grid telemetry. 4. Errors are logged with enough context to debug them. | High | 8 | Affan Mohammed Ramy | Sprint 3 | To Do | agents,grid,xai
US-113 | Story | Agent Routing | Evaluate violation resolution rate | As a developer, I want to evaluate violation resolution rate, decision latency and the number of unsafe actions blocked so that the requirement can be demonstrated at review. | 1. The team has evaluated violation resolution rate, decision latency and the number of unsafe actions blocked. 2. The step runs end to end on the full project dataset. 3. Results are persisted and can be retrieved later. 4. The run is reproducible from a fixed configuration. | High | 8 | Disha Kaushal | Sprint 3 | To Do | agents,grid,xai
US-114 | Story | Agent Routing | Review agent routing output | As a grid operator, I want to review the agent routing output in the interface so that I can confirm it before acting on it. | 1. The most recent output is shown together with its inputs. 2. The grid operator can flag an incorrect result. 3. Flagged items are queued for the system administrator to check. | Medium | 5 | Bollam Rakesh | Sprint 2 | To Do | agents,backend
US-115 | Task | Agent Routing | Retry and logging for agent routing | As a system, I want to retry and log failures in agent routing so that a transient error does not lose data. | 1. Failed operations retry with backoff. 2. Repeated failures raise an alert. 3. Every failure is logged with its input reference. | Medium | 5 | Chinnolla Ravindhar | Sprint 3 | To Do | agents,backend
US-116 | Story | Agent Routing | Tune agent routing | As a developer, I want to tune agent routing on validation data so that accuracy improves before release. | 1. A parameter search is run and recorded. 2. Before and after metrics are compared. 3. The chosen settings are committed to the repository. | Medium | 5 | Affan Mohammed Ramy | Sprint 3 | To Do | agents,backend
US-117 | Task | Agent Routing | Expose agent routing through an API | As a developer, I want to expose agent routing through an internal API so that the interface and other modules can consume it. | 1. Endpoint documented with request and response examples. 2. Errors return meaningful status codes. 3. The endpoint is covered by an integration test. | Medium | 5 | Disha Kaushal | Sprint 3 | To Do | agents,backend
US-118 | Story | Results and Reporting | Results dashboard | As a grid operator, I want a dashboard summarising the latest results so that I can understand the outcome at a glance. | 1. Key figures are shown with the date of the run. 2. Charts render correctly for an empty and a full dataset. 3. The dashboard loads within an acceptable time. | High | 5 | Bollam Rakesh | Sprint 4 | To Do | dashboard,frontend
US-119 | Story | Results and Reporting | Export report | As a system administrator, I want to export the results as PDF or CSV so that I can share them outside the system. | 1. The export includes the figures shown on screen. 2. The file name carries the project and the date. 3. Large exports complete without timing out. | Medium | 3 | Chinnolla Ravindhar | Sprint 4 | To Do | export,reporting
US-120 | Story | Results and Reporting | History and search | As a grid operator, I want to search past records so that I can compare an earlier result with the current one. | 1. Records can be filtered by date and by status. 2. Search returns promptly on the full dataset. 3. An empty result set is shown clearly. | Medium | 3 | Affan Mohammed Ramy | Sprint 4 | To Do | search,frontend
US-121 | Story | Notifications | Notify grid operator of an important outcome | As a grid operator, I want to be notified when the system produces an outcome needing my attention so that I can respond promptly. | 1. A notification is raised when the configured condition is met. 2. The grid operator can see the notification history. 3. Repeated notifications for the same event are suppressed. | Medium | 3 | Disha Kaushal | Sprint 4 | To Do | notification,alerts
US-122 | Spike | Evaluation | Define and measure evaluation metrics | Decide which metrics judge this project and measure the current build against them. | 1. Metrics chosen and justified for this problem. 2. Current scores recorded as a baseline. 3. A target for the final review is agreed. | Low | 3 | Bollam Rakesh | Sprint 5 | To Do | evaluation,research
US-123 | Task | Release | Deployment and user documentation | As a developer, I want the system deployed with setup and usage documentation so that the evaluators can run and demonstrate it. | 1. The application runs on the target environment. 2. Setup steps are documented and verified from scratch. 3. A short user guide covers the main workflow. | Low | 2 | Chinnolla Ravindhar | Sprint 5 | To Do | deployment,docs

## Field Guide
BharatBuild — User Stories Excel Import Guide
Fields marked with * are mandatory. Assignee Roll No and Assignee Name must match a registered student in the selected batch.
Field | Mandatory | Example | Validation / Usage
Story ID | No | US-101 | Optional unique reference. BharatBuild may generate one if blank.
Work Type | Yes | Story | Allowed: Story, Task, Spike.
Epic | No | Authentication | Existing or importable epic/feature grouping.
Summary | Yes | Student Login and Authentication | Short title of the user story.
Description | Yes | As a student, I want to... | Detailed functional/user-story description.
Acceptance Criteria | Yes | 1. Valid login... | Use numbered lines in one cell.
Priority | Yes | High | Highest, High, Medium, Low, Lowest.
Story Points | Yes | 5 | Numeric estimate; recommended Fibonacci values such as 1,2,3,5,8,13.
Assignee Roll No | Yes | 23K91A05L5 | Must belong to the currently selected project batch.
Assignee Name | Yes | Royyala Sindhuja | Must match the student identified by Assignee Roll No.
Sprint | No | Sprint 1 | If blank, story remains unscheduled/backlog.
Status | Yes | To Do | Allowed: To Do, In Progress, In Review, Done.
Labels | No | authentication,frontend | Comma-separated tags.

## Import Process
Trainer Import Workflow
Step | Action | Expected Result
1 | Select Department → Section → Batch → Project | BharatBuild establishes project context.
2 | Open User Stories → Import Stories | Import wizard opens.
3 | Upload this Excel file | Columns are detected automatically.
4 | Map Excel columns | Excel fields are mapped to BharatBuild story fields.
5 | Validate | Missing mandatory data, duplicate IDs and invalid assignees are flagged.
6 | Preview | Trainer reviews stories and student assignments.
7 | Confirm Import | Valid stories are created under the selected project.