## User Stories Import
Story ID | Work Type * | Epic | Summary * | Description * | Acceptance Criteria * | Priority * | Story Points * | Assignee Name * | Sprint | Status * | Labels
US-101 | Story | Platform Access | Retention manager registration and login | As a retention manager, I want to register and sign in with my own credentials so that I can reach my workspace securely. | 1. Valid credentials sign the retention manager in. 2. Invalid credentials show a clear error. 3. A session is created and expires after inactivity. 4. Passwords are stored only as salted hashes. | High | 5 | Anantula Sai Nikhila Sravani | Sprint 1 | To Do | churn,auth,frontend
US-102 | Story | Platform Access | Password reset | As a retention manager, I want to reset a forgotten password so that I can regain access without an administrator. | 1. A reset link or OTP is sent to the registered contact. 2. The link expires after a set time. 3. A new password can be saved and used to sign in. 4. Reset attempts are recorded in the audit log. | Medium | 3 | Avula Anudeep | Sprint 1 | To Do | auth,security
US-103 | Story | Platform Access | Role-based access for business analyst | As a business analyst, I want a separate privileged view so that I can manage records without using a retention manager account. | 1. Retention manager and business analyst roles see different menus. 2. Privileged actions are refused for a normal retention manager. 3. Every privileged action is written to an audit trail. | High | 5 | Boda Sandeep | Sprint 1 | To Do | auth,rbac
US-104 | Story | Records Intake | Submit customer usage records | As a retention manager, I want to submit customer usage records to the system so that they can be processed. | 1. Supported formats are accepted and stored. 2. Unsupported or oversized input is refused with a reason. 3. Each submission is timestamped and linked to its owner. 4. A confirmation is shown once the upload completes. | Highest | 5 | Daragani Vinod Kumar | Sprint 1 | To Do | churn,ingestion
US-105 | Story | Records Intake | Validate and clean customer usage records | As a system, I want to validate and clean incoming customer usage records so that poor quality input does not corrupt later stages. | 1. Missing and malformed fields are detected. 2. Duplicates are removed before processing. 3. A validation summary is available for each batch. 4. Rejected records are retained for review. | High | 5 | Anantula Sai Nikhila Sravani | Sprint 1 | To Do | validation,data
US-106 | Task | Records Intake | Project repository and environment setup | As a developer, I want a version-controlled repository with a reproducible environment so that the whole team builds on the same base. | 1. Repository created and branch rules agreed. 2. Dependencies pinned in a requirements file. 3. The project runs from a clean checkout by following the README. | Medium | 3 | Avula Anudeep | Sprint 1 | To Do | setup,devops
US-107 | Spike | Churn Modelling | Evaluate approaches for churn modelling | Research candidate approaches for churn modelling and record which one this project adopts. The surveyed work compares classifiers on churn datasets. The gap is pairing accurate prediction with per-customer explanation so that retention action can be targeted rather than. | 1. At least three approaches are compared. 2. Strengths and limits of each are written up. 3. A recommendation with reasons is recorded. | Low | 3 | Boda Sandeep | Sprint 2 | To Do | research,spike
US-108 | Story | Churn Modelling | Acquire a telecom customer dataset | As a system, I want to acquire a telecom customer dataset and perform exploratory analysis of churn behaviour so that the rest of the churn modelling pipeline can depend on it. | 1. The team has acquired a telecom customer dataset and perform exploratory analysis of churn behaviour. 2. Invalid or missing customer usage records are rejected with a clear message. 3. Behaviour is verified on a representative sample of customer usage records. 4. Errors are logged with enough context to debug them. | Highest | 8 | Daragani Vinod Kumar | Sprint 2 | To Do | churn,analytics,ml
US-109 | Story | Churn Modelling | Clean the data, encode categorical fields | As a system, I want to clean the data, encode categorical fields and address class imbalance between churned and retained customers so that the capability is available to the modules that follow. | 1. The system cleans the data, encode categorical fields and address class imbalance between churned and retained customers. 2. The step runs end to end on the full project dataset. 3. Results are persisted and can be retrieved later. 4. The run is reproducible from a fixed configuration. | High | 8 | Anantula Sai Nikhila Sravani | Sprint 2 | To Do | churn,analytics,ml
US-110 | Story | Churn Modelling | Train and compare Logistic Regression | As a developer, I want to train and compare Logistic Regression, Decision Tree and Random Forest classifiers so that customer usage records are processed consistently. | 1. The team has trained and compared Logistic Regression, Decision Tree and Random Forest classifiers. 2. Configuration values are read from settings rather than hard-coded. 3. Edge cases found during testing are handled. 4. The business analyst can inspect the outcome. | High | 8 | Avula Anudeep | Sprint 2 | To Do | churn,analytics,ml
US-111 | Story | Churn Modelling | Evaluate using accuracy, precision, recall | As a developer, I want to evaluate using accuracy, precision, recall, F1-score and ROC-AUC so that the behaviour is correct for both typical and edge inputs. | 1. The team has evaluated using accuracy, precision, recall, F1-score and ROC-AUC. 2. Processing completes within the agreed time budget. 3. The module has unit tests covering its main paths. 4. The step is documented in the project README. | High | 8 | Boda Sandeep | Sprint 3 | To Do | churn,analytics,ml
US-112 | Story | Churn Modelling | Identify the features | As a system, I want to identify the features that contribute most strongly to churn risk so that later features can build on a dependable output. | 1. The system identifies the features that contribute most strongly to churn risk. 2. Invalid or missing customer usage records are rejected with a clear message. 3. Behaviour is verified on a representative sample of customer usage records. 4. Errors are logged with enough context to debug them. | High | 8 | Daragani Vinod Kumar | Sprint 3 | To Do | churn,analytics,ml
US-113 | Story | Churn Modelling | Present at-risk customers and their risk drivers | As a system, I want to present at-risk customers and their risk drivers through a retention dashboard so that the requirement can be demonstrated at review. | 1. The system presents at-risk customers and their risk drivers through a retention dashboard. 2. The step runs end to end on the full project dataset. 3. Results are persisted and can be retrieved later. 4. The run is reproducible from a fixed configuration. | High | 8 | Anantula Sai Nikhila Sravani | Sprint 3 | To Do | churn,analytics,ml
US-114 | Story | Churn Modelling | Review churn modelling output | As a retention manager, I want to review the churn modelling output in the interface so that I can confirm it before acting on it. | 1. The most recent output is shown together with its inputs. 2. The retention manager can flag an incorrect result. 3. Flagged items are queued for the business analyst to check. | Medium | 5 | Avula Anudeep | Sprint 2 | To Do | churn,backend
US-115 | Task | Churn Modelling | Retry and logging for churn modelling | As a system, I want to retry and log failures in churn modelling so that a transient error does not lose data. | 1. Failed operations retry with backoff. 2. Repeated failures raise an alert. 3. Every failure is logged with its input reference. | Medium | 5 | Boda Sandeep | Sprint 3 | To Do | churn,backend
US-116 | Story | Churn Modelling | Tune churn modelling | As a developer, I want to tune churn modelling on validation data so that accuracy improves before release. | 1. A parameter search is run and recorded. 2. Before and after metrics are compared. 3. The chosen settings are committed to the repository. | Medium | 5 | Daragani Vinod Kumar | Sprint 3 | To Do | churn,backend
US-117 | Task | Churn Modelling | Expose churn modelling through an API | As a developer, I want to expose churn modelling through an internal API so that the interface and other modules can consume it. | 1. Endpoint documented with request and response examples. 2. Errors return meaningful status codes. 3. The endpoint is covered by an integration test. | Medium | 5 | Anantula Sai Nikhila Sravani | Sprint 3 | To Do | churn,backend
US-118 | Story | Results and Reporting | Results dashboard | As a retention manager, I want a dashboard summarising the latest results so that I can understand the outcome at a glance. | 1. Key figures are shown with the date of the run. 2. Charts render correctly for an empty and a full dataset. 3. The dashboard loads within an acceptable time. | High | 5 | Avula Anudeep | Sprint 4 | To Do | dashboard,frontend
US-119 | Story | Results and Reporting | Export report | As a business analyst, I want to export the results as PDF or CSV so that I can share them outside the system. | 1. The export includes the figures shown on screen. 2. The file name carries the project and the date. 3. Large exports complete without timing out. | Medium | 3 | Boda Sandeep | Sprint 4 | To Do | export,reporting
US-120 | Story | Results and Reporting | History and search | As a retention manager, I want to search past records so that I can compare an earlier result with the current one. | 1. Records can be filtered by date and by status. 2. Search returns promptly on the full dataset. 3. An empty result set is shown clearly. | Medium | 3 | Daragani Vinod Kumar | Sprint 4 | To Do | search,frontend
US-121 | Story | Notifications | Notify retention manager of an important outcome | As a retention manager, I want to be notified when the system produces an outcome needing my attention so that I can respond promptly. | 1. A notification is raised when the configured condition is met. 2. The retention manager can see the notification history. 3. Repeated notifications for the same event are suppressed. | Medium | 3 | Anantula Sai Nikhila Sravani | Sprint 4 | To Do | notification,alerts
US-122 | Spike | Evaluation | Define and measure evaluation metrics | Decide which metrics judge this project and measure the current build against them. | 1. Metrics chosen and justified for this problem. 2. Current scores recorded as a baseline. 3. A target for the final review is agreed. | Low | 3 | Avula Anudeep | Sprint 5 | To Do | evaluation,research
US-123 | Task | Release | Deployment and user documentation | As a developer, I want the system deployed with setup and usage documentation so that the evaluators can run and demonstrate it. | 1. The application runs on the target environment. 2. Setup steps are documented and verified from scratch. 3. A short user guide covers the main workflow. | Low | 2 | Boda Sandeep | Sprint 5 | To Do | deployment,docs

## Field Guide
BharatBuild — User Stories Excel Import Guide
Fields marked with * are mandatory. Assignee Roll No and Assignee Name must match a registered student in the selected batch.
Field | Mandatory | Example | Validation / Usage
Story ID | No | US-101 | Optional unique reference. BharatBuild may generate one if blank.
Work Type | Yes | Story | Allowed: Story, Task, Spike.
Epic | No | Authentication | Existing or importable epic/feature grouping.
Summary | Yes | Student Login and Authentication | Short title of the user story.
Description | Yes | As a student, I want to... | Detailed functional/user-story description.
Acceptance Criteria | Yes | 1. Valid login... | Use numbered lines in one cell.
Priority | Yes | High | Highest, High, Medium, Low, Lowest.
Story Points | Yes | 5 | Numeric estimate; recommended Fibonacci values such as 1,2,3,5,8,13.
Assignee Roll No | Yes | 23K91A05L5 | Must belong to the currently selected project batch.
Assignee Name | Yes | Royyala Sindhuja | Must match the student identified by Assignee Roll No.
Sprint | No | Sprint 1 | If blank, story remains unscheduled/backlog.
Status | Yes | To Do | Allowed: To Do, In Progress, In Review, Done.
Labels | No | authentication,frontend | Comma-separated tags.

## Import Process
Trainer Import Workflow
Step | Action | Expected Result
1 | Select Department → Section → Batch → Project | BharatBuild establishes project context.
2 | Open User Stories → Import Stories | Import wizard opens.
3 | Upload this Excel file | Columns are detected automatically.
4 | Map Excel columns | Excel fields are mapped to BharatBuild story fields.
5 | Validate | Missing mandatory data, duplicate IDs and invalid assignees are flagged.
6 | Preview | Trainer reviews stories and student assignments.
7 | Confirm Import | Valid stories are created under the selected project.