## User Stories Import
Story ID | Work Type * | Epic | Summary * | Description * | Acceptance Criteria * | Priority * | Story Points * | Assignee Name * | Sprint | Status * | Labels
US-101 | Story | Platform Access | Data owner registration and login | As a data owner, I want to register and sign in with my own credentials so that I can reach my workspace securely. | 1. Valid credentials sign the data owner in. 2. Invalid credentials show a clear error. 3. A session is created and expires after inactivity. 4. Passwords are stored only as salted hashes. | High | 5 | Allam Rakesh | Sprint 1 | To Do | crypto,auth,frontend
US-102 | Story | Platform Access | Password reset | As a data owner, I want to reset a forgotten password so that I can regain access without an administrator. | 1. A reset link or OTP is sent to the registered contact. 2. The link expires after a set time. 3. A new password can be saved and used to sign in. 4. Reset attempts are recorded in the audit log. | Medium | 3 | Bolleddu Shanker | Sprint 1 | To Do | auth,security
US-103 | Story | Platform Access | Role-based access for security administrator | As a security administrator, I want a separate privileged view so that I can manage records without using a data owner account. | 1. Data owner and security administrator roles see different menus. 2. Privileged actions are refused for a normal data owner. 3. Every privileged action is written to an audit trail. | High | 5 | Agram Sri Sarvagna | Sprint 1 | To Do | auth,rbac
US-104 | Story | Files Intake | Submit confidential files | As a data owner, I want to submit confidential files to the system so that they can be processed. | 1. Supported formats are accepted and stored. 2. Unsupported or oversized input is refused with a reason. 3. Each submission is timestamped and linked to its owner. 4. A confirmation is shown once the upload completes. | Highest | 5 | B. Akshay | Sprint 1 | To Do | crypto,ingestion
US-105 | Story | Files Intake | Validate and clean confidential files | As a system, I want to validate and clean incoming confidential files so that poor quality input does not corrupt later stages. | 1. Missing and malformed fields are detected. 2. Duplicates are removed before processing. 3. A validation summary is available for each batch. 4. Rejected records are retained for review. | High | 5 | Allam Rakesh | Sprint 1 | To Do | validation,data
US-106 | Task | Files Intake | Project repository and environment setup | As a developer, I want a version-controlled repository with a reproducible environment so that the whole team builds on the same base. | 1. Repository created and branch rules agreed. 2. Dependencies pinned in a requirements file. 3. The project runs from a clean checkout by following the README. | Medium | 3 | Bolleddu Shanker | Sprint 1 | To Do | setup,devops
US-107 | Spike | Encryption and Embedding | Evaluate approaches for encryption and embedding | Research candidate approaches for encryption and embedding and record which one this project adopts. The surveyed work advances steganography and encryption independently, including provably secure constructions. The gap is a practical hybrid AES-RSA plus LSB pipeline evaluated end to. | 1. At least three approaches are compared. 2. Strengths and limits of each are written up. 3. A recommendation with reasons is recorded. | Low | 3 | Agram Sri Sarvagna | Sprint 2 | To Do | research,spike
US-108 | Story | Encryption and Embedding | Implement AES encryption for the secret payload | As a developer, I want to implement AES encryption for the secret payload and RSA encryption for the AES key so that the rest of the encryption and embedding pipeline can depend on it. | 1. The delivered system provides AES encryption for the secret payload and RSA encryption for the AES key. 2. Invalid or missing confidential files are rejected with a clear message. 3. Behaviour is verified on a representative sample of confidential files. 4. Errors are logged with enough context to debug them. | Highest | 8 | B. Akshay | Sprint 2 | To Do | crypto,steganography,security
US-109 | Story | Encryption and Embedding | Build a secure key generation | As a developer, I want to build a secure key generation and exchange mechanism between sender and receiver so that the capability is available to the modules that follow. | 1. The delivered system provides a secure key generation and exchange mechanism between sender and receiver. 2. The step runs end to end on the full project dataset. 3. Results are persisted and can be retrieved later. 4. The run is reproducible from a fixed configuration. | High | 8 | Allam Rakesh | Sprint 2 | To Do | crypto,steganography,security
US-110 | Story | Encryption and Embedding | Embed the encrypted payload into a cover image | As a system, I want to embed the encrypted payload into a cover image using LSB steganography so that confidential files are processed consistently. | 1. The system embeds the encrypted payload into a cover image using LSB steganography. 2. Configuration values are read from settings rather than hard-coded. 3. Edge cases found during testing are handled. 4. The security administrator can inspect the outcome. | High | 8 | Bolleddu Shanker | Sprint 2 | To Do | crypto,steganography,security
US-111 | Story | Encryption and Embedding | Implement the extraction and decryption path | As a developer, I want to implement the extraction and decryption path to recover the original data so that the behaviour is correct for both typical and edge inputs. | 1. The delivered system provides the extraction and decryption path to recover the original data. 2. Processing completes within the agreed time budget. 3. The module has unit tests covering its main paths. 4. The step is documented in the project README. | High | 8 | Agram Sri Sarvagna | Sprint 3 | To Do | crypto,steganography,security
US-112 | Story | Encryption and Embedding | Measure imperceptibility | As a system, I want to measure imperceptibility using PSNR and SSIM against the original cover image so that later features can build on a dependable output. | 1. The system measures imperceptibility using PSNR and SSIM against the original cover image. 2. Invalid or missing confidential files are rejected with a clear message. 3. Behaviour is verified on a representative sample of confidential files. 4. Errors are logged with enough context to debug them. | High | 8 | B. Akshay | Sprint 3 | To Do | crypto,steganography,security
US-113 | Story | Encryption and Embedding | Evaluate embedding capacity | As a developer, I want to evaluate embedding capacity, processing time and robustness of the combined scheme so that the requirement can be demonstrated at review. | 1. The team has evaluated embedding capacity, processing time and robustness of the combined scheme. 2. The step runs end to end on the full project dataset. 3. Results are persisted and can be retrieved later. 4. The run is reproducible from a fixed configuration. | High | 8 | Allam Rakesh | Sprint 3 | To Do | crypto,steganography,security
US-114 | Story | Encryption and Embedding | Review encryption and embedding output | As a data owner, I want to review the encryption and embedding output in the interface so that I can confirm it before acting on it. | 1. The most recent output is shown together with its inputs. 2. The data owner can flag an incorrect result. 3. Flagged items are queued for the security administrator to check. | Medium | 5 | Bolleddu Shanker | Sprint 2 | To Do | crypto,backend
US-115 | Task | Encryption and Embedding | Retry and logging for encryption and embedding | As a system, I want to retry and log failures in encryption and embedding so that a transient error does not lose data. | 1. Failed operations retry with backoff. 2. Repeated failures raise an alert. 3. Every failure is logged with its input reference. | Medium | 5 | Agram Sri Sarvagna | Sprint 3 | To Do | crypto,backend
US-116 | Story | Encryption and Embedding | Tune encryption and embedding | As a developer, I want to tune encryption and embedding on validation data so that accuracy improves before release. | 1. A parameter search is run and recorded. 2. Before and after metrics are compared. 3. The chosen settings are committed to the repository. | Medium | 5 | B. Akshay | Sprint 3 | To Do | crypto,backend
US-117 | Task | Encryption and Embedding | Expose encryption and embedding through an API | As a developer, I want to expose encryption and embedding through an internal API so that the interface and other modules can consume it. | 1. Endpoint documented with request and response examples. 2. Errors return meaningful status codes. 3. The endpoint is covered by an integration test. | Medium | 5 | Allam Rakesh | Sprint 3 | To Do | crypto,backend
US-118 | Story | Results and Reporting | Results dashboard | As a data owner, I want a dashboard summarising the latest results so that I can understand the outcome at a glance. | 1. Key figures are shown with the date of the run. 2. Charts render correctly for an empty and a full dataset. 3. The dashboard loads within an acceptable time. | High | 5 | Bolleddu Shanker | Sprint 4 | To Do | dashboard,frontend
US-119 | Story | Results and Reporting | Export report | As a security administrator, I want to export the results as PDF or CSV so that I can share them outside the system. | 1. The export includes the figures shown on screen. 2. The file name carries the project and the date. 3. Large exports complete without timing out. | Medium | 3 | Agram Sri Sarvagna | Sprint 4 | To Do | export,reporting
US-120 | Story | Results and Reporting | History and search | As a data owner, I want to search past records so that I can compare an earlier result with the current one. | 1. Records can be filtered by date and by status. 2. Search returns promptly on the full dataset. 3. An empty result set is shown clearly. | Medium | 3 | B. Akshay | Sprint 4 | To Do | search,frontend
US-121 | Story | Notifications | Notify data owner of an important outcome | As a data owner, I want to be notified when the system produces an outcome needing my attention so that I can respond promptly. | 1. A notification is raised when the configured condition is met. 2. The data owner can see the notification history. 3. Repeated notifications for the same event are suppressed. | Medium | 3 | Allam Rakesh | Sprint 4 | To Do | notification,alerts
US-122 | Spike | Evaluation | Define and measure evaluation metrics | Decide which metrics judge this project and measure the current build against them. | 1. Metrics chosen and justified for this problem. 2. Current scores recorded as a baseline. 3. A target for the final review is agreed. | Low | 3 | Bolleddu Shanker | Sprint 5 | To Do | evaluation,research
US-123 | Task | Release | Deployment and user documentation | As a developer, I want the system deployed with setup and usage documentation so that the evaluators can run and demonstrate it. | 1. The application runs on the target environment. 2. Setup steps are documented and verified from scratch. 3. A short user guide covers the main workflow. | Low | 2 | Agram Sri Sarvagna | Sprint 5 | To Do | deployment,docs

## Field Guide
BharatBuild — User Stories Excel Import Guide
Fields marked with * are mandatory. Assignee Roll No and Assignee Name must match a registered student in the selected batch.
Field | Mandatory | Example | Validation / Usage
Story ID | No | US-101 | Optional unique reference. BharatBuild may generate one if blank.
Work Type | Yes | Story | Allowed: Story, Task, Spike.
Epic | No | Authentication | Existing or importable epic/feature grouping.
Summary | Yes | Student Login and Authentication | Short title of the user story.
Description | Yes | As a student, I want to... | Detailed functional/user-story description.
Acceptance Criteria | Yes | 1. Valid login... | Use numbered lines in one cell.
Priority | Yes | High | Highest, High, Medium, Low, Lowest.
Story Points | Yes | 5 | Numeric estimate; recommended Fibonacci values such as 1,2,3,5,8,13.
Assignee Roll No | Yes | 23K91A05L5 | Must belong to the currently selected project batch.
Assignee Name | Yes | Royyala Sindhuja | Must match the student identified by Assignee Roll No.
Sprint | No | Sprint 1 | If blank, story remains unscheduled/backlog.
Status | Yes | To Do | Allowed: To Do, In Progress, In Review, Done.
Labels | No | authentication,frontend | Comma-separated tags.

## Import Process
Trainer Import Workflow
Step | Action | Expected Result
1 | Select Department → Section → Batch → Project | BharatBuild establishes project context.
2 | Open User Stories → Import Stories | Import wizard opens.
3 | Upload this Excel file | Columns are detected automatically.
4 | Map Excel columns | Excel fields are mapped to BharatBuild story fields.
5 | Validate | Missing mandatory data, duplicate IDs and invalid assignees are flagged.
6 | Preview | Trainer reviews stories and student assignments.
7 | Confirm Import | Valid stories are created under the selected project.