## User Stories Import
Story ID | Work Type * | Epic | Summary * | Description * | Acceptance Criteria * | Priority * | Story Points * | Assignee Name * | Sprint | Status * | Labels
US-101 | Story | Platform Access | Deaf or hard-of-hearing user registration and login | As a deaf or hard-of-hearing user, I want to register and sign in with my own credentials so that I can reach my workspace securely. | 1. Valid credentials sign the deaf or hard-of-hearing user in. 2. Invalid credentials show a clear error. 3. A session is created and expires after inactivity. 4. Passwords are stored only as salted hashes. | High | 5 | Ajay | Sprint 1 | To Do | cnn,auth,frontend
US-102 | Story | Platform Access | Password reset | As a deaf or hard-of-hearing user, I want to reset a forgotten password so that I can regain access without an administrator. | 1. A reset link or OTP is sent to the registered contact. 2. The link expires after a set time. 3. A new password can be saved and used to sign in. 4. Reset attempts are recorded in the audit log. | Medium | 3 | Navadeep | Sprint 1 | To Do | auth,security
US-103 | Story | Platform Access | Role-based access for accessibility coordinator | As a accessibility coordinator, I want a separate privileged view so that I can manage records without using a deaf or hard-of-hearing user account. | 1. Deaf or hard-of-hearing user and accessibility coordinator roles see different menus. 2. Privileged actions are refused for a normal deaf or hard-of-hearing user. 3. Every privileged action is written to an audit trail. | High | 5 | Manideep | Sprint 1 | To Do | auth,rbac
US-104 | Story | Video Intake | Submit sign gesture video | As a deaf or hard-of-hearing user, I want to submit sign gesture video to the system so that they can be processed. | 1. Supported formats are accepted and stored. 2. Unsupported or oversized input is refused with a reason. 3. Each submission is timestamped and linked to its owner. 4. A confirmation is shown once the upload completes. | Highest | 5 | Maheshwari | Sprint 1 | To Do | cnn,ingestion
US-105 | Story | Video Intake | Validate and clean sign gesture video | As a system, I want to validate and clean incoming sign gesture video so that poor quality input does not corrupt later stages. | 1. Missing and malformed fields are detected. 2. Duplicates are removed before processing. 3. A validation summary is available for each batch. 4. Rejected records are retained for review. | High | 5 | Ajay | Sprint 1 | To Do | validation,data
US-106 | Task | Video Intake | Project repository and environment setup | As a developer, I want a version-controlled repository with a reproducible environment so that the whole team builds on the same base. | 1. Repository created and branch rules agreed. 2. Dependencies pinned in a requirements file. 3. The project runs from a clean checkout by following the README. | Medium | 3 | Navadeep | Sprint 1 | To Do | setup,devops
US-107 | Spike | Gesture Recognition | Evaluate approaches for gesture recognition | Research candidate approaches for gesture recognition and record which one this project adopts. The surveyed work advances skeleton-based recognition and knowledge distillation for accuracy and efficiency. The gap is an accessible end-to-end system that recognises signs live and. | 1. At least three approaches are compared. 2. Strengths and limits of each are written up. 3. A recommendation with reasons is recorded. | Low | 3 | Manideep | Sprint 2 | To Do | research,spike
US-108 | Story | Gesture Recognition | Build a dataset of hand gesture images covering the target | As a developer, I want to build a dataset of hand gesture images covering the target sign alphabet and common words so that the rest of the gesture recognition pipeline can depend on it. | 1. The delivered system provides a dataset of hand gesture images covering the target sign alphabet and common words. 2. Invalid or missing sign gesture video are rejected with a clear message. 3. Behaviour is verified on a representative sample of sign gesture video. 4. Errors are logged with enough context to debug them. | Highest | 8 | Maheshwari | Sprint 2 | To Do | cnn,accessibility,cv
US-109 | Story | Gesture Recognition | Preprocess images with segmentation | As a developer, I want to preprocess images with segmentation, resizing and augmentation to improve generalisation so that the capability is available to the modules that follow. | 1. The team has preprocessed images with segmentation, resizing and augmentation to improve generalisation. 2. The step runs end to end on the full project dataset. 3. Results are persisted and can be retrieved later. 4. The run is reproducible from a fixed configuration. | High | 8 | Ajay | Sprint 2 | To Do | cnn,accessibility,cv
US-110 | Story | Gesture Recognition | Design and train a CNN architecture for gesture classification | As a developer, I want to design and train a CNN architecture for gesture classification so that sign gesture video are processed consistently. | 1. The team has designed and trained a CNN architecture for gesture classification. 2. Configuration values are read from settings rather than hard-coded. 3. Edge cases found during testing are handled. 4. The accessibility coordinator can inspect the outcome. | High | 8 | Navadeep | Sprint 2 | To Do | cnn,accessibility,cv
US-111 | Story | Gesture Recognition | Optimise the model for real-time inference | As a developer, I want to optimise the model for real-time inference from a live camera feed so that the behaviour is correct for both typical and edge inputs. | 1. The team has optimised the model for real-time inference from a live camera feed. 2. Processing completes within the agreed time budget. 3. The module has unit tests covering its main paths. 4. The step is documented in the project README. | High | 8 | Manideep | Sprint 3 | To Do | cnn,accessibility,cv
US-112 | Story | Gesture Recognition | Convert recognised signs into on-screen text | As a system, I want to convert recognised signs into on-screen text and synthesised speech output so that later features can build on a dependable output. | 1. The system converts recognised signs into on-screen text and synthesised speech output. 2. Invalid or missing sign gesture video are rejected with a clear message. 3. Behaviour is verified on a representative sample of sign gesture video. 4. Errors are logged with enough context to debug them. | High | 8 | Maheshwari | Sprint 3 | To Do | cnn,accessibility,cv
US-113 | Story | Gesture Recognition | Evaluate accuracy, per-class performance | As a developer, I want to evaluate accuracy, per-class performance and inference latency on unseen signers so that the requirement can be demonstrated at review. | 1. The team has evaluated accuracy, per-class performance and inference latency on unseen signers. 2. The step runs end to end on the full project dataset. 3. Results are persisted and can be retrieved later. 4. The run is reproducible from a fixed configuration. | High | 8 | Ajay | Sprint 3 | To Do | cnn,accessibility,cv
US-114 | Story | Gesture Recognition | Review gesture recognition output | As a deaf or hard-of-hearing user, I want to review the gesture recognition output in the interface so that I can confirm it before acting on it. | 1. The most recent output is shown together with its inputs. 2. The deaf or hard-of-hearing user can flag an incorrect result. 3. Flagged items are queued for the accessibility coordinator to check. | Medium | 5 | Navadeep | Sprint 2 | To Do | cnn,backend
US-115 | Task | Gesture Recognition | Retry and logging for gesture recognition | As a system, I want to retry and log failures in gesture recognition so that a transient error does not lose data. | 1. Failed operations retry with backoff. 2. Repeated failures raise an alert. 3. Every failure is logged with its input reference. | Medium | 5 | Manideep | Sprint 3 | To Do | cnn,backend
US-116 | Story | Gesture Recognition | Tune gesture recognition | As a developer, I want to tune gesture recognition on validation data so that accuracy improves before release. | 1. A parameter search is run and recorded. 2. Before and after metrics are compared. 3. The chosen settings are committed to the repository. | Medium | 5 | Maheshwari | Sprint 3 | To Do | cnn,backend
US-117 | Task | Gesture Recognition | Expose gesture recognition through an API | As a developer, I want to expose gesture recognition through an internal API so that the interface and other modules can consume it. | 1. Endpoint documented with request and response examples. 2. Errors return meaningful status codes. 3. The endpoint is covered by an integration test. | Medium | 5 | Ajay | Sprint 3 | To Do | cnn,backend
US-118 | Story | Results and Reporting | Results dashboard | As a deaf or hard-of-hearing user, I want a dashboard summarising the latest results so that I can understand the outcome at a glance. | 1. Key figures are shown with the date of the run. 2. Charts render correctly for an empty and a full dataset. 3. The dashboard loads within an acceptable time. | High | 5 | Navadeep | Sprint 4 | To Do | dashboard,frontend
US-119 | Story | Results and Reporting | Export report | As a accessibility coordinator, I want to export the results as PDF or CSV so that I can share them outside the system. | 1. The export includes the figures shown on screen. 2. The file name carries the project and the date. 3. Large exports complete without timing out. | Medium | 3 | Manideep | Sprint 4 | To Do | export,reporting
US-120 | Story | Results and Reporting | History and search | As a deaf or hard-of-hearing user, I want to search past records so that I can compare an earlier result with the current one. | 1. Records can be filtered by date and by status. 2. Search returns promptly on the full dataset. 3. An empty result set is shown clearly. | Medium | 3 | Maheshwari | Sprint 4 | To Do | search,frontend
US-121 | Story | Notifications | Notify deaf or hard-of-hearing user of an important outcome | As a deaf or hard-of-hearing user, I want to be notified when the system produces an outcome needing my attention so that I can respond promptly. | 1. A notification is raised when the configured condition is met. 2. The deaf or hard-of-hearing user can see the notification history. 3. Repeated notifications for the same event are suppressed. | Medium | 3 | Ajay | Sprint 4 | To Do | notification,alerts
US-122 | Spike | Evaluation | Define and measure evaluation metrics | Decide which metrics judge this project and measure the current build against them. | 1. Metrics chosen and justified for this problem. 2. Current scores recorded as a baseline. 3. A target for the final review is agreed. | Low | 3 | Navadeep | Sprint 5 | To Do | evaluation,research
US-123 | Task | Release | Deployment and user documentation | As a developer, I want the system deployed with setup and usage documentation so that the evaluators can run and demonstrate it. | 1. The application runs on the target environment. 2. Setup steps are documented and verified from scratch. 3. A short user guide covers the main workflow. | Low | 2 | Manideep | Sprint 5 | To Do | deployment,docs

## Field Guide
BharatBuild — User Stories Excel Import Guide
Fields marked with * are mandatory. Assignee Roll No and Assignee Name must match a registered student in the selected batch.
Field | Mandatory | Example | Validation / Usage
Story ID | No | US-101 | Optional unique reference. BharatBuild may generate one if blank.
Work Type | Yes | Story | Allowed: Story, Task, Spike.
Epic | No | Authentication | Existing or importable epic/feature grouping.
Summary | Yes | Student Login and Authentication | Short title of the user story.
Description | Yes | As a student, I want to... | Detailed functional/user-story description.
Acceptance Criteria | Yes | 1. Valid login... | Use numbered lines in one cell.
Priority | Yes | High | Highest, High, Medium, Low, Lowest.
Story Points | Yes | 5 | Numeric estimate; recommended Fibonacci values such as 1,2,3,5,8,13.
Assignee Roll No | Yes | 23K91A05L5 | Must belong to the currently selected project batch.
Assignee Name | Yes | Royyala Sindhuja | Must match the student identified by Assignee Roll No.
Sprint | No | Sprint 1 | If blank, story remains unscheduled/backlog.
Status | Yes | To Do | Allowed: To Do, In Progress, In Review, Done.
Labels | No | authentication,frontend | Comma-separated tags.

## Import Process
Trainer Import Workflow
Step | Action | Expected Result
1 | Select Department → Section → Batch → Project | BharatBuild establishes project context.
2 | Open User Stories → Import Stories | Import wizard opens.
3 | Upload this Excel file | Columns are detected automatically.
4 | Map Excel columns | Excel fields are mapped to BharatBuild story fields.
5 | Validate | Missing mandatory data, duplicate IDs and invalid assignees are flagged.
6 | Preview | Trainer reviews stories and student assignments.
7 | Confirm Import | Valid stories are created under the selected project.