## User Stories Import
Story ID | Work Type * | Epic | Summary * | Description * | Acceptance Criteria * | Priority * | Story Points * | Assignee Name * | Sprint | Status * | Labels
US-101 | Story | Platform Access | Merchandising planner registration and login | As a merchandising planner, I want to register and sign in with my own credentials so that I can reach my workspace securely. | 1. Valid credentials sign the merchandising planner in. 2. Invalid credentials show a clear error. 3. A session is created and expires after inactivity. 4. Passwords are stored only as salted hashes. | High | 5 | B. Shilpa | Sprint 1 | To Do | forecasting,auth,frontend
US-102 | Story | Platform Access | Password reset | As a merchandising planner, I want to reset a forgotten password so that I can regain access without an administrator. | 1. A reset link or OTP is sent to the registered contact. 2. The link expires after a set time. 3. A new password can be saved and used to sign in. 4. Reset attempts are recorded in the audit log. | Medium | 3 | B. Hari Narayana | Sprint 1 | To Do | auth,security
US-103 | Story | Platform Access | Role-based access for supply chain manager | As a supply chain manager, I want a separate privileged view so that I can manage records without using a merchandising planner account. | 1. Merchandising planner and supply chain manager roles see different menus. 2. Privileged actions are refused for a normal merchandising planner. 3. Every privileged action is written to an audit trail. | High | 5 | A. Rani Tejaswini | Sprint 1 | To Do | auth,rbac
US-104 | Story | Data Intake | Submit historical sales data | As a merchandising planner, I want to submit historical sales data to the system so that they can be processed. | 1. Supported formats are accepted and stored. 2. Unsupported or oversized input is refused with a reason. 3. Each submission is timestamped and linked to its owner. 4. A confirmation is shown once the upload completes. | Highest | 5 | A. Sanjana | Sprint 1 | To Do | forecasting,ingestion
US-105 | Story | Data Intake | Validate and clean historical sales data | As a system, I want to validate and clean incoming historical sales data so that poor quality input does not corrupt later stages. | 1. Missing and malformed fields are detected. 2. Duplicates are removed before processing. 3. A validation summary is available for each batch. 4. Rejected records are retained for review. | High | 5 | B. Shilpa | Sprint 1 | To Do | validation,data
US-106 | Task | Data Intake | Project repository and environment setup | As a developer, I want a version-controlled repository with a reproducible environment so that the whole team builds on the same base. | 1. Repository created and branch rules agreed. 2. Dependencies pinned in a requirements file. 3. The project runs from a clean checkout by following the README. | Medium | 3 | B. Hari Narayana | Sprint 1 | To Do | setup,devops
US-107 | Spike | Demand Forecasting | Evaluate approaches for demand forecasting | Research candidate approaches for demand forecasting and record which one this project adopts. The surveyed work applies gradient boosting with explainability to retail demand. The gap is adding domain adaptation so a model trained in one retail context transfers to a new market. | 1. At least three approaches are compared. 2. Strengths and limits of each are written up. 3. A recommendation with reasons is recorded. | Low | 3 | A. Rani Tejaswini | Sprint 2 | To Do | research,spike
US-108 | Story | Demand Forecasting | Collect historical fashion retail sales data | As a system, I want to collect historical fashion retail sales data and engineer seasonal, pricing and category features so that the rest of the demand forecasting pipeline can depend on it. | 1. The system collects historical fashion retail sales data and engineer seasonal, pricing and category features. 2. Invalid or missing historical sales data are rejected with a clear message. 3. Behaviour is verified on a representative sample of historical sales data. 4. Errors are logged with enough context to debug them. | Highest | 8 | A. Sanjana | Sprint 2 | To Do | forecasting,retail,ml
US-109 | Story | Demand Forecasting | Train gradient-boosting models such as XGBoost | As a developer, I want to train gradient-boosting models such as XGBoost to forecast demand at product and category level so that the capability is available to the modules that follow. | 1. The team has trained gradient-boosting models such as XGBoost to forecast demand at product and category level. 2. The step runs end to end on the full project dataset. 3. Results are persisted and can be retrieved later. 4. The run is reproducible from a fixed configuration. | High | 8 | B. Shilpa | Sprint 2 | To Do | forecasting,retail,ml
US-110 | Story | Demand Forecasting | Apply domain adaptation | As a system, I want to apply domain adaptation to transfer the model across markets and product categories so that historical sales data are processed consistently. | 1. The system applies domain adaptation to transfer the model across markets and product categories. 2. Configuration values are read from settings rather than hard-coded. 3. Edge cases found during testing are handled. 4. The supply chain manager can inspect the outcome. | High | 8 | B. Hari Narayana | Sprint 2 | To Do | forecasting,retail,ml
US-111 | Story | Demand Forecasting | Compare adapted and non-adapted models | As a developer, I want to compare adapted and non-adapted models on a target market with a different data distribution so that the behaviour is correct for both typical and edge inputs. | 1. The team has compared adapted and non-adapted models on a target market with a different data distribution. 2. Processing completes within the agreed time budget. 3. The module has unit tests covering its main paths. 4. The step is documented in the project README. | High | 8 | A. Rani Tejaswini | Sprint 3 | To Do | forecasting,retail,ml
US-112 | Story | Demand Forecasting | Explain forecast drivers | As a system, I want to explain forecast drivers so planners understand why demand is predicted to move so that later features can build on a dependable output. | 1. The system explains forecast drivers so planners understand why demand is predicted to move. 2. Invalid or missing historical sales data are rejected with a clear message. 3. Behaviour is verified on a representative sample of historical sales data. 4. Errors are logged with enough context to debug them. | High | 8 | A. Sanjana | Sprint 3 | To Do | forecasting,retail,ml
US-113 | Story | Demand Forecasting | Evaluate using MAE, RMSE and MAPE | As a developer, I want to evaluate using MAE, RMSE and MAPE, and translate error into inventory impact so that the requirement can be demonstrated at review. | 1. The team has evaluated using MAE, RMSE and MAPE, and translate error into inventory impact. 2. The step runs end to end on the full project dataset. 3. Results are persisted and can be retrieved later. 4. The run is reproducible from a fixed configuration. | High | 8 | B. Shilpa | Sprint 3 | To Do | forecasting,retail,ml
US-114 | Story | Demand Forecasting | Review demand forecasting output | As a merchandising planner, I want to review the demand forecasting output in the interface so that I can confirm it before acting on it. | 1. The most recent output is shown together with its inputs. 2. The merchandising planner can flag an incorrect result. 3. Flagged items are queued for the supply chain manager to check. | Medium | 5 | B. Hari Narayana | Sprint 2 | To Do | forecasting,backend
US-115 | Task | Demand Forecasting | Retry and logging for demand forecasting | As a system, I want to retry and log failures in demand forecasting so that a transient error does not lose data. | 1. Failed operations retry with backoff. 2. Repeated failures raise an alert. 3. Every failure is logged with its input reference. | Medium | 5 | A. Rani Tejaswini | Sprint 3 | To Do | forecasting,backend
US-116 | Story | Demand Forecasting | Tune demand forecasting | As a developer, I want to tune demand forecasting on validation data so that accuracy improves before release. | 1. A parameter search is run and recorded. 2. Before and after metrics are compared. 3. The chosen settings are committed to the repository. | Medium | 5 | A. Sanjana | Sprint 3 | To Do | forecasting,backend
US-117 | Task | Demand Forecasting | Expose demand forecasting through an API | As a developer, I want to expose demand forecasting through an internal API so that the interface and other modules can consume it. | 1. Endpoint documented with request and response examples. 2. Errors return meaningful status codes. 3. The endpoint is covered by an integration test. | Medium | 5 | B. Shilpa | Sprint 3 | To Do | forecasting,backend
US-118 | Story | Results and Reporting | Results dashboard | As a merchandising planner, I want a dashboard summarising the latest results so that I can understand the outcome at a glance. | 1. Key figures are shown with the date of the run. 2. Charts render correctly for an empty and a full dataset. 3. The dashboard loads within an acceptable time. | High | 5 | B. Hari Narayana | Sprint 4 | To Do | dashboard,frontend
US-119 | Story | Results and Reporting | Export report | As a supply chain manager, I want to export the results as PDF or CSV so that I can share them outside the system. | 1. The export includes the figures shown on screen. 2. The file name carries the project and the date. 3. Large exports complete without timing out. | Medium | 3 | A. Rani Tejaswini | Sprint 4 | To Do | export,reporting
US-120 | Story | Results and Reporting | History and search | As a merchandising planner, I want to search past records so that I can compare an earlier result with the current one. | 1. Records can be filtered by date and by status. 2. Search returns promptly on the full dataset. 3. An empty result set is shown clearly. | Medium | 3 | A. Sanjana | Sprint 4 | To Do | search,frontend
US-121 | Story | Notifications | Notify merchandising planner of an important outcome | As a merchandising planner, I want to be notified when the system produces an outcome needing my attention so that I can respond promptly. | 1. A notification is raised when the configured condition is met. 2. The merchandising planner can see the notification history. 3. Repeated notifications for the same event are suppressed. | Medium | 3 | B. Shilpa | Sprint 4 | To Do | notification,alerts
US-122 | Spike | Evaluation | Define and measure evaluation metrics | Decide which metrics judge this project and measure the current build against them. | 1. Metrics chosen and justified for this problem. 2. Current scores recorded as a baseline. 3. A target for the final review is agreed. | Low | 3 | B. Hari Narayana | Sprint 5 | To Do | evaluation,research
US-123 | Task | Release | Deployment and user documentation | As a developer, I want the system deployed with setup and usage documentation so that the evaluators can run and demonstrate it. | 1. The application runs on the target environment. 2. Setup steps are documented and verified from scratch. 3. A short user guide covers the main workflow. | Low | 2 | A. Rani Tejaswini | Sprint 5 | To Do | deployment,docs

## Field Guide
BharatBuild — User Stories Excel Import Guide
Fields marked with * are mandatory. Assignee Roll No and Assignee Name must match a registered student in the selected batch.
Field | Mandatory | Example | Validation / Usage
Story ID | No | US-101 | Optional unique reference. BharatBuild may generate one if blank.
Work Type | Yes | Story | Allowed: Story, Task, Spike.
Epic | No | Authentication | Existing or importable epic/feature grouping.
Summary | Yes | Student Login and Authentication | Short title of the user story.
Description | Yes | As a student, I want to... | Detailed functional/user-story description.
Acceptance Criteria | Yes | 1. Valid login... | Use numbered lines in one cell.
Priority | Yes | High | Highest, High, Medium, Low, Lowest.
Story Points | Yes | 5 | Numeric estimate; recommended Fibonacci values such as 1,2,3,5,8,13.
Assignee Roll No | Yes | 23K91A05L5 | Must belong to the currently selected project batch.
Assignee Name | Yes | Royyala Sindhuja | Must match the student identified by Assignee Roll No.
Sprint | No | Sprint 1 | If blank, story remains unscheduled/backlog.
Status | Yes | To Do | Allowed: To Do, In Progress, In Review, Done.
Labels | No | authentication,frontend | Comma-separated tags.

## Import Process
Trainer Import Workflow
Step | Action | Expected Result
1 | Select Department → Section → Batch → Project | BharatBuild establishes project context.
2 | Open User Stories → Import Stories | Import wizard opens.
3 | Upload this Excel file | Columns are detected automatically.
4 | Map Excel columns | Excel fields are mapped to BharatBuild story fields.
5 | Validate | Missing mandatory data, duplicate IDs and invalid assignees are flagged.
6 | Preview | Trainer reviews stories and student assignments.
7 | Confirm Import | Valid stories are created under the selected project.