## User Stories Import
Story ID | Work Type * | Epic | Summary * | Description * | Acceptance Criteria * | Priority * | Story Points * | Assignee Name * | Sprint | Status * | Labels
US-101 | Story | Platform Access | Emergency responder registration and login | As a emergency responder, I want to register and sign in with my own credentials so that I can reach my workspace securely. | 1. Valid credentials sign the emergency responder in. 2. Invalid credentials show a clear error. 3. A session is created and expires after inactivity. 4. Passwords are stored only as salted hashes. | High | 5 | Adepu Meenakshi | Sprint 1 | To Do | accident,auth,frontend
US-102 | Story | Platform Access | Password reset | As a emergency responder, I want to reset a forgotten password so that I can regain access without an administrator. | 1. A reset link or OTP is sent to the registered contact. 2. The link expires after a set time. 3. A new password can be saved and used to sign in. 4. Reset attempts are recorded in the audit log. | Medium | 3 | Ayila Shanmukha Sai | Sprint 1 | To Do | auth,security
US-103 | Story | Platform Access | Role-based access for control room operator | As a control room operator, I want a separate privileged view so that I can manage records without using a emergency responder account. | 1. Emergency responder and control room operator roles see different menus. 2. Privileged actions are refused for a normal emergency responder. 3. Every privileged action is written to an audit trail. | High | 5 | Chekka Chandrashekhar | Sprint 1 | To Do | auth,rbac
US-104 | Story | Data Intake | Submit crash sensor and camera data | As a emergency responder, I want to submit crash sensor and camera data to the system so that they can be processed. | 1. Supported formats are accepted and stored. 2. Unsupported or oversized input is refused with a reason. 3. Each submission is timestamped and linked to its owner. 4. A confirmation is shown once the upload completes. | Highest | 5 | Avula Sreeya | Sprint 1 | To Do | accident,ingestion
US-105 | Story | Data Intake | Validate and clean crash sensor and camera data | As a system, I want to validate and clean incoming crash sensor and camera data so that poor quality input does not corrupt later stages. | 1. Missing and malformed fields are detected. 2. Duplicates are removed before processing. 3. A validation summary is available for each batch. 4. Rejected records are retained for review. | High | 5 | Adepu Meenakshi | Sprint 1 | To Do | validation,data
US-106 | Task | Data Intake | Project repository and environment setup | As a developer, I want a version-controlled repository with a reproducible environment so that the whole team builds on the same base. | 1. Repository created and branch rules agreed. 2. Dependencies pinned in a requirements file. 3. The project runs from a clean checkout by following the README. | Medium | 3 | Ayila Shanmukha Sai | Sprint 1 | To Do | setup,devops
US-107 | Spike | Accident Detection | Evaluate approaches for accident detection | Research candidate approaches for accident detection and record which one this project adopts. The surveyed work predicts accident severity from recorded datasets after the event. None of it closes the loop from live sensing through severity grading to automated hospital dispatch. | 1. At least three approaches are compared. 2. Strengths and limits of each are written up. 3. A recommendation with reasons is recorded. | Low | 3 | Chekka Chandrashekhar | Sprint 2 | To Do | research,spike
US-108 | Story | Accident Detection | Collect and preprocess smartphone accelerometer, gyroscope | As a system, I want to collect and preprocess smartphone accelerometer, gyroscope, speed and GPS data for normal driving and collision events so that the rest of the accident detection pipeline can depend on it. | 1. The system collects and preprocesses smartphone accelerometer, gyroscope, speed and GPS data for normal driving and collision events. 2. Invalid or missing crash sensor and camera data are rejected with a clear message. 3. Behaviour is verified on a representative sample of crash sensor and camera data. 4. Errors are logged with enough context to debug them. | Highest | 8 | Avula Sreeya | Sprint 2 | To Do | accident,detection,emergency
US-109 | Story | Accident Detection | Train a classifier that distinguishes genuine accidents | As a developer, I want to train a classifier that distinguishes genuine accidents from potholes, speed breakers and hard braking so that the capability is available to the modules that follow. | 1. The team has trained a classifier that distinguishes genuine accidents from potholes, speed breakers and hard braking. 2. The step runs end to end on the full project dataset. 3. Results are persisted and can be retrieved later. 4. The run is reproducible from a fixed configuration. | High | 8 | Adepu Meenakshi | Sprint 2 | To Do | accident,detection,emergency
US-110 | Story | Accident Detection | Build a severity model | As a developer, I want to build a severity model that grades an impact as minor, moderate or severe so that crash sensor and camera data are processed consistently. | 1. The delivered system provides a severity model that grades an impact as minor, moderate or severe. 2. Configuration values are read from settings rather than hard-coded. 3. Edge cases found during testing are handled. 4. The control room operator can inspect the outcome. | High | 8 | Ayila Shanmukha Sai | Sprint 2 | To Do | accident,detection,emergency
US-111 | Story | Accident Detection | Use GPS to locate the crash | As a system, I want to use GPS to locate the crash and identify a suitable nearby hospital so that the behaviour is correct for both typical and edge inputs. | 1. The system uses GPS to locate the crash and identify a suitable nearby hospital. 2. Processing completes within the agreed time budget. 3. The module has unit tests covering its main paths. 4. The step is documented in the project README. | High | 8 | Chekka Chandrashekhar | Sprint 3 | To Do | accident,detection,emergency
US-112 | Story | Accident Detection | Dispatch an automated alert carrying location | As a system, I want to dispatch an automated alert carrying location and severity to emergency contacts and medical services so that later features can build on a dependable output. | 1. The system dispatches an automated alert carrying location and severity to emergency contacts and medical services. 2. Invalid or missing crash sensor and camera data are rejected with a clear message. 3. Behaviour is verified on a representative sample of crash sensor and camera data. 4. Errors are logged with enough context to debug them. | High | 8 | Avula Sreeya | Sprint 3 | To Do | accident,detection,emergency
US-113 | Story | Accident Detection | Evaluate detection accuracy | As a developer, I want to evaluate detection accuracy, false alarm rate and end-to-end alert latency so that the requirement can be demonstrated at review. | 1. The team has evaluated detection accuracy, false alarm rate and end-to-end alert latency. 2. The step runs end to end on the full project dataset. 3. Results are persisted and can be retrieved later. 4. The run is reproducible from a fixed configuration. | High | 8 | Adepu Meenakshi | Sprint 3 | To Do | accident,detection,emergency
US-114 | Story | Accident Detection | Review accident detection output | As a emergency responder, I want to review the accident detection output in the interface so that I can confirm it before acting on it. | 1. The most recent output is shown together with its inputs. 2. The emergency responder can flag an incorrect result. 3. Flagged items are queued for the control room operator to check. | Medium | 5 | Ayila Shanmukha Sai | Sprint 2 | To Do | accident,backend
US-115 | Task | Accident Detection | Retry and logging for accident detection | As a system, I want to retry and log failures in accident detection so that a transient error does not lose data. | 1. Failed operations retry with backoff. 2. Repeated failures raise an alert. 3. Every failure is logged with its input reference. | Medium | 5 | Chekka Chandrashekhar | Sprint 3 | To Do | accident,backend
US-116 | Story | Accident Detection | Tune accident detection | As a developer, I want to tune accident detection on validation data so that accuracy improves before release. | 1. A parameter search is run and recorded. 2. Before and after metrics are compared. 3. The chosen settings are committed to the repository. | Medium | 5 | Avula Sreeya | Sprint 3 | To Do | accident,backend
US-117 | Task | Accident Detection | Expose accident detection through an API | As a developer, I want to expose accident detection through an internal API so that the interface and other modules can consume it. | 1. Endpoint documented with request and response examples. 2. Errors return meaningful status codes. 3. The endpoint is covered by an integration test. | Medium | 5 | Adepu Meenakshi | Sprint 3 | To Do | accident,backend
US-118 | Story | Results and Reporting | Results dashboard | As a emergency responder, I want a dashboard summarising the latest results so that I can understand the outcome at a glance. | 1. Key figures are shown with the date of the run. 2. Charts render correctly for an empty and a full dataset. 3. The dashboard loads within an acceptable time. | High | 5 | Ayila Shanmukha Sai | Sprint 4 | To Do | dashboard,frontend
US-119 | Story | Results and Reporting | Export report | As a control room operator, I want to export the results as PDF or CSV so that I can share them outside the system. | 1. The export includes the figures shown on screen. 2. The file name carries the project and the date. 3. Large exports complete without timing out. | Medium | 3 | Chekka Chandrashekhar | Sprint 4 | To Do | export,reporting
US-120 | Story | Results and Reporting | History and search | As a emergency responder, I want to search past records so that I can compare an earlier result with the current one. | 1. Records can be filtered by date and by status. 2. Search returns promptly on the full dataset. 3. An empty result set is shown clearly. | Medium | 3 | Avula Sreeya | Sprint 4 | To Do | search,frontend
US-121 | Story | Notifications | Notify emergency responder of an important outcome | As a emergency responder, I want to be notified when the system produces an outcome needing my attention so that I can respond promptly. | 1. A notification is raised when the configured condition is met. 2. The emergency responder can see the notification history. 3. Repeated notifications for the same event are suppressed. | Medium | 3 | Adepu Meenakshi | Sprint 4 | To Do | notification,alerts
US-122 | Spike | Evaluation | Define and measure evaluation metrics | Decide which metrics judge this project and measure the current build against them. | 1. Metrics chosen and justified for this problem. 2. Current scores recorded as a baseline. 3. A target for the final review is agreed. | Low | 3 | Ayila Shanmukha Sai | Sprint 5 | To Do | evaluation,research
US-123 | Task | Release | Deployment and user documentation | As a developer, I want the system deployed with setup and usage documentation so that the evaluators can run and demonstrate it. | 1. The application runs on the target environment. 2. Setup steps are documented and verified from scratch. 3. A short user guide covers the main workflow. | Low | 2 | Chekka Chandrashekhar | Sprint 5 | To Do | deployment,docs

## Field Guide
BharatBuild — User Stories Excel Import Guide
Fields marked with * are mandatory. Assignee Roll No and Assignee Name must match a registered student in the selected batch.
Field | Mandatory | Example | Validation / Usage
Story ID | No | US-101 | Optional unique reference. BharatBuild may generate one if blank.
Work Type | Yes | Story | Allowed: Story, Task, Spike.
Epic | No | Authentication | Existing or importable epic/feature grouping.
Summary | Yes | Student Login and Authentication | Short title of the user story.
Description | Yes | As a student, I want to... | Detailed functional/user-story description.
Acceptance Criteria | Yes | 1. Valid login... | Use numbered lines in one cell.
Priority | Yes | High | Highest, High, Medium, Low, Lowest.
Story Points | Yes | 5 | Numeric estimate; recommended Fibonacci values such as 1,2,3,5,8,13.
Assignee Roll No | Yes | 23K91A05L5 | Must belong to the currently selected project batch.
Assignee Name | Yes | Royyala Sindhuja | Must match the student identified by Assignee Roll No.
Sprint | No | Sprint 1 | If blank, story remains unscheduled/backlog.
Status | Yes | To Do | Allowed: To Do, In Progress, In Review, Done.
Labels | No | authentication,frontend | Comma-separated tags.

## Import Process
Trainer Import Workflow
Step | Action | Expected Result
1 | Select Department → Section → Batch → Project | BharatBuild establishes project context.
2 | Open User Stories → Import Stories | Import wizard opens.
3 | Upload this Excel file | Columns are detected automatically.
4 | Map Excel columns | Excel fields are mapped to BharatBuild story fields.
5 | Validate | Missing mandatory data, duplicate IDs and invalid assignees are flagged.
6 | Preview | Trainer reviews stories and student assignments.
7 | Confirm Import | Valid stories are created under the selected project.