## User Stories Import
Story ID | Work Type * | Epic | Summary * | Description * | Acceptance Criteria * | Priority * | Story Points * | Assignee Name * | Sprint | Status * | Labels
US-101 | Story | Platform Access | Patient registration and login | As a patient, I want to register and sign in with my own credentials so that I can reach my workspace securely. | 1. Valid credentials sign the patient in. 2. Invalid credentials show a clear error. 3. A session is created and expires after inactivity. 4. Passwords are stored only as salted hashes. | High | 5 | Ajmeera Harini | Sprint 1 | To Do | ml,auth,frontend
US-102 | Story | Platform Access | Password reset | As a patient, I want to reset a forgotten password so that I can regain access without an administrator. | 1. A reset link or OTP is sent to the registered contact. 2. The link expires after a set time. 3. A new password can be saved and used to sign in. 4. Reset attempts are recorded in the audit log. | Medium | 3 | Bandi Likitha | Sprint 1 | To Do | auth,security
US-103 | Story | Platform Access | Role-based access for clinician | As a clinician, I want a separate privileged view so that I can manage records without using a patient account. | 1. Patient and clinician roles see different menus. 2. Privileged actions are refused for a normal patient. 3. Every privileged action is written to an audit trail. | High | 5 | Chintakindi Swathi | Sprint 1 | To Do | auth,rbac
US-104 | Story | Records Intake | Submit patient health records | As a patient, I want to submit patient health records to the system so that they can be processed. | 1. Supported formats are accepted and stored. 2. Unsupported or oversized input is refused with a reason. 3. Each submission is timestamped and linked to its owner. 4. A confirmation is shown once the upload completes. | Highest | 5 | Badroju Sri Hansika | Sprint 1 | To Do | ml,ingestion
US-105 | Story | Records Intake | Validate and clean patient health records | As a system, I want to validate and clean incoming patient health records so that poor quality input does not corrupt later stages. | 1. Missing and malformed fields are detected. 2. Duplicates are removed before processing. 3. A validation summary is available for each batch. 4. Rejected records are retained for review. | High | 5 | Ajmeera Harini | Sprint 1 | To Do | validation,data
US-106 | Task | Records Intake | Project repository and environment setup | As a developer, I want a version-controlled repository with a reproducible environment so that the whole team builds on the same base. | 1. Repository created and branch rules agreed. 2. Dependencies pinned in a requirements file. 3. The project runs from a clean checkout by following the README. | Medium | 3 | Bandi Likitha | Sprint 1 | To Do | setup,devops
US-107 | Spike | Disease Prediction | Evaluate approaches for disease prediction | Research candidate approaches for disease prediction and record which one this project adopts. The surveyed papers each target one disease in isolation. The gap is a single pipeline that screens several conditions from one patient record and explains which parameters drove each. | 1. At least three approaches are compared. 2. Strengths and limits of each are written up. 3. A recommendation with reasons is recorded. | Low | 3 | Chintakindi Swathi | Sprint 2 | To Do | research,spike
US-108 | Story | Disease Prediction | Collect and clean benchmark datasets covering diabetes | As a system, I want to collect and clean benchmark datasets covering diabetes, heart disease, liver and kidney disorders so that the rest of the disease prediction pipeline can depend on it. | 1. The system collects and cleans benchmark datasets covering diabetes, heart disease, liver and kidney disorders. 2. Invalid or missing patient health records are rejected with a clear message. 3. Behaviour is verified on a representative sample of patient health records. 4. Errors are logged with enough context to debug them. | Highest | 8 | Badroju Sri Hansika | Sprint 2 | To Do | ml,healthcare,prediction
US-109 | Story | Disease Prediction | Handle missing values, outliers and feature scaling | As a system, I want to handle missing values, outliers and feature scaling through a common preprocessing pipeline so that the capability is available to the modules that follow. | 1. The system handles missing values, outliers and feature scaling through a common preprocessing pipeline. 2. The step runs end to end on the full project dataset. 3. Results are persisted and can be retrieved later. 4. The run is reproducible from a fixed configuration. | High | 8 | Ajmeera Harini | Sprint 2 | To Do | ml,healthcare,prediction
US-110 | Story | Disease Prediction | Train and compare Logistic Regression, Decision Tree | As a developer, I want to train and compare Logistic Regression, Decision Tree, Random Forest and Support Vector Machine for each disease so that patient health records are processed consistently. | 1. The team has trained and compared Logistic Regression, Decision Tree, Random Forest and Support Vector Machine for each disease. 2. Configuration values are read from settings rather than hard-coded. 3. Edge cases found during testing are handled. 4. The clinician can inspect the outcome. | High | 8 | Bandi Likitha | Sprint 2 | To Do | ml,healthcare,prediction
US-111 | Story | Disease Prediction | Select the best model per disease | As a developer, I want to select the best model per disease using accuracy, precision, recall and ROC-AUC so that the behaviour is correct for both typical and edge inputs. | 1. The team has selected the best model per disease using accuracy, precision, recall and ROC-AUC. 2. Processing completes within the agreed time budget. 3. The module has unit tests covering its main paths. 4. The step is documented in the project README. | High | 8 | Chintakindi Swathi | Sprint 3 | To Do | ml,healthcare,prediction
US-112 | Story | Disease Prediction | Serve the selected models behind a single interface | As a system, I want to serve the selected models behind a single interface that accepts one patient record so that later features can build on a dependable output. | 1. The system serves the selected models behind a single interface that accepts one patient record. 2. Invalid or missing patient health records are rejected with a clear message. 3. Behaviour is verified on a representative sample of patient health records. 4. Errors are logged with enough context to debug them. | High | 8 | Badroju Sri Hansika | Sprint 3 | To Do | ml,healthcare,prediction
US-113 | Story | Disease Prediction | Present a per-disease risk indication together | As a system, I want to present a per-disease risk indication together with the parameters that drove it so that the requirement can be demonstrated at review. | 1. The system presents a per-disease risk indication together with the parameters that drove it. 2. The step runs end to end on the full project dataset. 3. Results are persisted and can be retrieved later. 4. The run is reproducible from a fixed configuration. | High | 8 | Ajmeera Harini | Sprint 3 | To Do | ml,healthcare,prediction
US-114 | Story | Disease Prediction | Review disease prediction output | As a patient, I want to review the disease prediction output in the interface so that I can confirm it before acting on it. | 1. The most recent output is shown together with its inputs. 2. The patient can flag an incorrect result. 3. Flagged items are queued for the clinician to check. | Medium | 5 | Bandi Likitha | Sprint 2 | To Do | ml,backend
US-115 | Task | Disease Prediction | Retry and logging for disease prediction | As a system, I want to retry and log failures in disease prediction so that a transient error does not lose data. | 1. Failed operations retry with backoff. 2. Repeated failures raise an alert. 3. Every failure is logged with its input reference. | Medium | 5 | Chintakindi Swathi | Sprint 3 | To Do | ml,backend
US-116 | Story | Disease Prediction | Tune disease prediction | As a developer, I want to tune disease prediction on validation data so that accuracy improves before release. | 1. A parameter search is run and recorded. 2. Before and after metrics are compared. 3. The chosen settings are committed to the repository. | Medium | 5 | Badroju Sri Hansika | Sprint 3 | To Do | ml,backend
US-117 | Task | Disease Prediction | Expose disease prediction through an API | As a developer, I want to expose disease prediction through an internal API so that the interface and other modules can consume it. | 1. Endpoint documented with request and response examples. 2. Errors return meaningful status codes. 3. The endpoint is covered by an integration test. | Medium | 5 | Ajmeera Harini | Sprint 3 | To Do | ml,backend
US-118 | Story | Results and Reporting | Results dashboard | As a patient, I want a dashboard summarising the latest results so that I can understand the outcome at a glance. | 1. Key figures are shown with the date of the run. 2. Charts render correctly for an empty and a full dataset. 3. The dashboard loads within an acceptable time. | High | 5 | Bandi Likitha | Sprint 4 | To Do | dashboard,frontend
US-119 | Story | Results and Reporting | Export report | As a clinician, I want to export the results as PDF or CSV so that I can share them outside the system. | 1. The export includes the figures shown on screen. 2. The file name carries the project and the date. 3. Large exports complete without timing out. | Medium | 3 | Chintakindi Swathi | Sprint 4 | To Do | export,reporting
US-120 | Story | Results and Reporting | History and search | As a patient, I want to search past records so that I can compare an earlier result with the current one. | 1. Records can be filtered by date and by status. 2. Search returns promptly on the full dataset. 3. An empty result set is shown clearly. | Medium | 3 | Badroju Sri Hansika | Sprint 4 | To Do | search,frontend
US-121 | Story | Notifications | Notify patient of an important outcome | As a patient, I want to be notified when the system produces an outcome needing my attention so that I can respond promptly. | 1. A notification is raised when the configured condition is met. 2. The patient can see the notification history. 3. Repeated notifications for the same event are suppressed. | Medium | 3 | Ajmeera Harini | Sprint 4 | To Do | notification,alerts
US-122 | Spike | Evaluation | Define and measure evaluation metrics | Decide which metrics judge this project and measure the current build against them. | 1. Metrics chosen and justified for this problem. 2. Current scores recorded as a baseline. 3. A target for the final review is agreed. | Low | 3 | Bandi Likitha | Sprint 5 | To Do | evaluation,research
US-123 | Task | Release | Deployment and user documentation | As a developer, I want the system deployed with setup and usage documentation so that the evaluators can run and demonstrate it. | 1. The application runs on the target environment. 2. Setup steps are documented and verified from scratch. 3. A short user guide covers the main workflow. | Low | 2 | Chintakindi Swathi | Sprint 5 | To Do | deployment,docs

## Field Guide
BharatBuild — User Stories Excel Import Guide
Fields marked with * are mandatory. Assignee Roll No and Assignee Name must match a registered student in the selected batch.
Field | Mandatory | Example | Validation / Usage
Story ID | No | US-101 | Optional unique reference. BharatBuild may generate one if blank.
Work Type | Yes | Story | Allowed: Story, Task, Spike.
Epic | No | Authentication | Existing or importable epic/feature grouping.
Summary | Yes | Student Login and Authentication | Short title of the user story.
Description | Yes | As a student, I want to... | Detailed functional/user-story description.
Acceptance Criteria | Yes | 1. Valid login... | Use numbered lines in one cell.
Priority | Yes | High | Highest, High, Medium, Low, Lowest.
Story Points | Yes | 5 | Numeric estimate; recommended Fibonacci values such as 1,2,3,5,8,13.
Assignee Roll No | Yes | 23K91A05L5 | Must belong to the currently selected project batch.
Assignee Name | Yes | Royyala Sindhuja | Must match the student identified by Assignee Roll No.
Sprint | No | Sprint 1 | If blank, story remains unscheduled/backlog.
Status | Yes | To Do | Allowed: To Do, In Progress, In Review, Done.
Labels | No | authentication,frontend | Comma-separated tags.

## Import Process
Trainer Import Workflow
Step | Action | Expected Result
1 | Select Department → Section → Batch → Project | BharatBuild establishes project context.
2 | Open User Stories → Import Stories | Import wizard opens.
3 | Upload this Excel file | Columns are detected automatically.
4 | Map Excel columns | Excel fields are mapped to BharatBuild story fields.
5 | Validate | Missing mandatory data, duplicate IDs and invalid assignees are flagged.
6 | Preview | Trainer reviews stories and student assignments.
7 | Confirm Import | Valid stories are created under the selected project.