## User Stories Import
Story ID | Work Type * | Epic | Summary * | Description * | Acceptance Criteria * | Priority * | Story Points * | Assignee Name * | Sprint | Status * | Labels
US-101 | Story | Platform Access | Cardholder registration and login | As a cardholder, I want to register and sign in with my own credentials so that I can reach my workspace securely. | 1. Valid credentials sign the cardholder in. 2. Invalid credentials show a clear error. 3. A session is created and expires after inactivity. 4. Passwords are stored only as salted hashes. | High | 5 | A. PRAVEEN KUMAR | Sprint 1 | To Do | fraud,auth,frontend
US-102 | Story | Platform Access | Password reset | As a cardholder, I want to reset a forgotten password so that I can regain access without an administrator. | 1. A reset link or OTP is sent to the registered contact. 2. The link expires after a set time. 3. A new password can be saved and used to sign in. 4. Reset attempts are recorded in the audit log. | Medium | 3 | B. AJAY KUMAR | Sprint 1 | To Do | auth,security
US-103 | Story | Platform Access | Role-based access for fraud analyst | As a fraud analyst, I want a separate privileged view so that I can manage records without using a cardholder account. | 1. Cardholder and fraud analyst roles see different menus. 2. Privileged actions are refused for a normal cardholder. 3. Every privileged action is written to an audit trail. | High | 5 | D. CHANDRIKA | Sprint 1 | To Do | auth,rbac
US-104 | Story | Records Intake | Submit card transaction records | As a cardholder, I want to submit card transaction records to the system so that they can be processed. | 1. Supported formats are accepted and stored. 2. Unsupported or oversized input is refused with a reason. 3. Each submission is timestamped and linked to its owner. 4. A confirmation is shown once the upload completes. | Highest | 5 | B. VIJAY | Sprint 1 | To Do | fraud,ingestion
US-105 | Story | Records Intake | Validate and clean card transaction records | As a system, I want to validate and clean incoming card transaction records so that poor quality input does not corrupt later stages. | 1. Missing and malformed fields are detected. 2. Duplicates are removed before processing. 3. A validation summary is available for each batch. 4. Rejected records are retained for review. | High | 5 | A. PRAVEEN KUMAR | Sprint 1 | To Do | validation,data
US-106 | Task | Records Intake | Project repository and environment setup | As a developer, I want a version-controlled repository with a reproducible environment so that the whole team builds on the same base. | 1. Repository created and branch rules agreed. 2. Dependencies pinned in a requirements file. 3. The project runs from a clean checkout by following the README. | Medium | 3 | B. AJAY KUMAR | Sprint 1 | To Do | setup,devops
US-107 | Spike | Fraud Detection | Evaluate approaches for fraud detection | Research candidate approaches for fraud detection and record which one this project adopts. The surveyed work explores individual classifiers and sampling methods separately. The gap is a compared, tuned pipeline that is evaluated on recall rather than accuracy and is. | 1. At least three approaches are compared. 2. Strengths and limits of each are written up. 3. A recommendation with reasons is recorded. | Low | 3 | D. CHANDRIKA | Sprint 2 | To Do | research,spike
US-108 | Story | Fraud Detection | Acquire a benchmark credit card transaction dataset | As a system, I want to acquire a benchmark credit card transaction dataset and quantify the degree of class imbalance so that the rest of the fraud detection pipeline can depend on it. | 1. The team has acquired a benchmark credit card transaction dataset and quantify the degree of class imbalance. 2. Invalid or missing card transaction records are rejected with a clear message. 3. Behaviour is verified on a representative sample of card transaction records. 4. Errors are logged with enough context to debug them. | Highest | 8 | B. VIJAY | Sprint 2 | To Do | fraud,transactions,ml
US-109 | Story | Fraud Detection | Apply preprocessing including scaling | As a system, I want to apply preprocessing including scaling, feature selection and stratified train-test splitting so that the capability is available to the modules that follow. | 1. The system applies preprocessing including scaling, feature selection and stratified train-test splitting. 2. The step runs end to end on the full project dataset. 3. Results are persisted and can be retrieved later. 4. The run is reproducible from a fixed configuration. | High | 8 | A. PRAVEEN KUMAR | Sprint 2 | To Do | fraud,transactions,ml
US-110 | Story | Fraud Detection | Balance the training data | As a system, I want to balance the training data using SMOTE and compare it against random undersampling so that card transaction records are processed consistently. | 1. The system balances the training data using SMOTE and compare it against random undersampling. 2. Configuration values are read from settings rather than hard-coded. 3. Edge cases found during testing are handled. 4. The fraud analyst can inspect the outcome. | High | 8 | B. AJAY KUMAR | Sprint 2 | To Do | fraud,transactions,ml
US-111 | Story | Fraud Detection | Train Logistic Regression, Random Forest | As a developer, I want to train Logistic Regression, Random Forest and XGBoost classifiers on the balanced data so that the behaviour is correct for both typical and edge inputs. | 1. The team has trained Logistic Regression, Random Forest and XGBoost classifiers on the balanced data. 2. Processing completes within the agreed time budget. 3. The module has unit tests covering its main paths. 4. The step is documented in the project README. | High | 8 | D. CHANDRIKA | Sprint 3 | To Do | fraud,transactions,ml
US-112 | Story | Fraud Detection | Evaluate using precision, recall | As a developer, I want to evaluate using precision, recall, F1-score and ROC-AUC rather than accuracy alone so that later features can build on a dependable output. | 1. The team has evaluated using precision, recall, F1-score and ROC-AUC rather than accuracy alone. 2. Invalid or missing card transaction records are rejected with a clear message. 3. Behaviour is verified on a representative sample of card transaction records. 4. Errors are logged with enough context to debug them. | High | 8 | B. VIJAY | Sprint 3 | To Do | fraud,transactions,ml
US-113 | Story | Fraud Detection | Deploy the best model behind an interface | As a developer, I want to deploy the best model behind an interface that flags a transaction as genuine or fraudulent so that the requirement can be demonstrated at review. | 1. The delivered system provides the best model behind an interface that flags a transaction as genuine or fraudulent. 2. The step runs end to end on the full project dataset. 3. Results are persisted and can be retrieved later. 4. The run is reproducible from a fixed configuration. | High | 8 | A. PRAVEEN KUMAR | Sprint 3 | To Do | fraud,transactions,ml
US-114 | Story | Fraud Detection | Review fraud detection output | As a cardholder, I want to review the fraud detection output in the interface so that I can confirm it before acting on it. | 1. The most recent output is shown together with its inputs. 2. The cardholder can flag an incorrect result. 3. Flagged items are queued for the fraud analyst to check. | Medium | 5 | B. AJAY KUMAR | Sprint 2 | To Do | fraud,backend
US-115 | Task | Fraud Detection | Retry and logging for fraud detection | As a system, I want to retry and log failures in fraud detection so that a transient error does not lose data. | 1. Failed operations retry with backoff. 2. Repeated failures raise an alert. 3. Every failure is logged with its input reference. | Medium | 5 | D. CHANDRIKA | Sprint 3 | To Do | fraud,backend
US-116 | Story | Fraud Detection | Tune fraud detection | As a developer, I want to tune fraud detection on validation data so that accuracy improves before release. | 1. A parameter search is run and recorded. 2. Before and after metrics are compared. 3. The chosen settings are committed to the repository. | Medium | 5 | B. VIJAY | Sprint 3 | To Do | fraud,backend
US-117 | Task | Fraud Detection | Expose fraud detection through an API | As a developer, I want to expose fraud detection through an internal API so that the interface and other modules can consume it. | 1. Endpoint documented with request and response examples. 2. Errors return meaningful status codes. 3. The endpoint is covered by an integration test. | Medium | 5 | A. PRAVEEN KUMAR | Sprint 3 | To Do | fraud,backend
US-118 | Story | Results and Reporting | Results dashboard | As a cardholder, I want a dashboard summarising the latest results so that I can understand the outcome at a glance. | 1. Key figures are shown with the date of the run. 2. Charts render correctly for an empty and a full dataset. 3. The dashboard loads within an acceptable time. | High | 5 | B. AJAY KUMAR | Sprint 4 | To Do | dashboard,frontend
US-119 | Story | Results and Reporting | Export report | As a fraud analyst, I want to export the results as PDF or CSV so that I can share them outside the system. | 1. The export includes the figures shown on screen. 2. The file name carries the project and the date. 3. Large exports complete without timing out. | Medium | 3 | D. CHANDRIKA | Sprint 4 | To Do | export,reporting
US-120 | Story | Results and Reporting | History and search | As a cardholder, I want to search past records so that I can compare an earlier result with the current one. | 1. Records can be filtered by date and by status. 2. Search returns promptly on the full dataset. 3. An empty result set is shown clearly. | Medium | 3 | B. VIJAY | Sprint 4 | To Do | search,frontend
US-121 | Story | Notifications | Notify cardholder of an important outcome | As a cardholder, I want to be notified when the system produces an outcome needing my attention so that I can respond promptly. | 1. A notification is raised when the configured condition is met. 2. The cardholder can see the notification history. 3. Repeated notifications for the same event are suppressed. | Medium | 3 | A. PRAVEEN KUMAR | Sprint 4 | To Do | notification,alerts
US-122 | Spike | Evaluation | Define and measure evaluation metrics | Decide which metrics judge this project and measure the current build against them. | 1. Metrics chosen and justified for this problem. 2. Current scores recorded as a baseline. 3. A target for the final review is agreed. | Low | 3 | B. AJAY KUMAR | Sprint 5 | To Do | evaluation,research
US-123 | Task | Release | Deployment and user documentation | As a developer, I want the system deployed with setup and usage documentation so that the evaluators can run and demonstrate it. | 1. The application runs on the target environment. 2. Setup steps are documented and verified from scratch. 3. A short user guide covers the main workflow. | Low | 2 | D. CHANDRIKA | Sprint 5 | To Do | deployment,docs

## Field Guide
BharatBuild — User Stories Excel Import Guide
Fields marked with * are mandatory. Assignee Roll No and Assignee Name must match a registered student in the selected batch.
Field | Mandatory | Example | Validation / Usage
Story ID | No | US-101 | Optional unique reference. BharatBuild may generate one if blank.
Work Type | Yes | Story | Allowed: Story, Task, Spike.
Epic | No | Authentication | Existing or importable epic/feature grouping.
Summary | Yes | Student Login and Authentication | Short title of the user story.
Description | Yes | As a student, I want to... | Detailed functional/user-story description.
Acceptance Criteria | Yes | 1. Valid login... | Use numbered lines in one cell.
Priority | Yes | High | Highest, High, Medium, Low, Lowest.
Story Points | Yes | 5 | Numeric estimate; recommended Fibonacci values such as 1,2,3,5,8,13.
Assignee Roll No | Yes | 23K91A05L5 | Must belong to the currently selected project batch.
Assignee Name | Yes | Royyala Sindhuja | Must match the student identified by Assignee Roll No.
Sprint | No | Sprint 1 | If blank, story remains unscheduled/backlog.
Status | Yes | To Do | Allowed: To Do, In Progress, In Review, Done.
Labels | No | authentication,frontend | Comma-separated tags.

## Import Process
Trainer Import Workflow
Step | Action | Expected Result
1 | Select Department → Section → Batch → Project | BharatBuild establishes project context.
2 | Open User Stories → Import Stories | Import wizard opens.
3 | Upload this Excel file | Columns are detected automatically.
4 | Map Excel columns | Excel fields are mapped to BharatBuild story fields.
5 | Validate | Missing mandatory data, duplicate IDs and invalid assignees are flagged.
6 | Preview | Trainer reviews stories and student assignments.
7 | Confirm Import | Valid stories are created under the selected project.