## User Stories Import
Story ID | Work Type * | Epic | Summary * | Description * | Acceptance Criteria * | Priority * | Story Points * | Assignee Name * | Sprint | Status * | Labels
US-101 | Story | Platform Access | Data owner registration and login | As a data owner, I want to register and sign in with my own credentials so that I can reach my workspace securely. | 1. Valid credentials sign the data owner in. 2. Invalid credentials show a clear error. 3. A session is created and expires after inactivity. 4. Passwords are stored only as salted hashes. | High | 5 | Sandhya | Sprint 1 | To Do | cloud,auth,frontend
US-102 | Story | Platform Access | Password reset | As a data owner, I want to reset a forgotten password so that I can regain access without an administrator. | 1. A reset link or OTP is sent to the registered contact. 2. The link expires after a set time. 3. A new password can be saved and used to sign in. 4. Reset attempts are recorded in the audit log. | Medium | 3 | Indhu | Sprint 1 | To Do | auth,security
US-103 | Story | Platform Access | Role-based access for cloud administrator | As a cloud administrator, I want a separate privileged view so that I can manage records without using a data owner account. | 1. Data owner and cloud administrator roles see different menus. 2. Privileged actions are refused for a normal data owner. 3. Every privileged action is written to an audit trail. | High | 5 | Vaishnavi | Sprint 1 | To Do | auth,rbac
US-104 | Story | Files Intake | Submit uploaded files | As a data owner, I want to submit uploaded files to the system so that they can be processed. | 1. Supported formats are accepted and stored. 2. Unsupported or oversized input is refused with a reason. 3. Each submission is timestamped and linked to its owner. 4. A confirmation is shown once the upload completes. | Highest | 5 | Sriteja | Sprint 1 | To Do | cloud,ingestion
US-105 | Story | Files Intake | Validate and clean uploaded files | As a system, I want to validate and clean incoming uploaded files so that poor quality input does not corrupt later stages. | 1. Missing and malformed fields are detected. 2. Duplicates are removed before processing. 3. A validation summary is available for each batch. 4. Rejected records are retained for review. | High | 5 | Sandhya | Sprint 1 | To Do | validation,data
US-106 | Task | Files Intake | Project repository and environment setup | As a developer, I want a version-controlled repository with a reproducible environment so that the whole team builds on the same base. | 1. Repository created and branch rules agreed. 2. Dependencies pinned in a requirements file. 3. The project runs from a clean checkout by following the README. | Medium | 3 | Indhu | Sprint 1 | To Do | setup,devops
US-107 | Spike | Encryption and Transmission | Evaluate approaches for encryption and transmission | Research candidate approaches for encryption and transmission and record which one this project adopts. The surveyed work treats cryptography and intrusion detection as separate concerns. The gap is a single transmission path where both operate together and the combined overhead is. | 1. At least three approaches are compared. 2. Strengths and limits of each are written up. 3. A recommendation with reasons is recorded. | Low | 3 | Vaishnavi | Sprint 2 | To Do | research,spike
US-108 | Story | Encryption and Transmission | Design a hybrid encryption scheme | As a developer, I want to design a hybrid encryption scheme using AES for the payload and RSA for key exchange so that the rest of the encryption and transmission pipeline can depend on it. | 1. The delivered system provides a hybrid encryption scheme using AES for the payload and RSA for key exchange. 2. Invalid or missing uploaded files are rejected with a clear message. 3. Behaviour is verified on a representative sample of uploaded files. 4. Errors are logged with enough context to debug them. | Highest | 8 | Sriteja | Sprint 2 | To Do | cloud,encryption,security
US-109 | Story | Encryption and Transmission | Implement secure key generation | As a developer, I want to implement secure key generation, distribution and storage between sender and receiver so that the capability is available to the modules that follow. | 1. The delivered system provides secure key generation, distribution and storage between sender and receiver. 2. The step runs end to end on the full project dataset. 3. Results are persisted and can be retrieved later. 4. The run is reproducible from a fixed configuration. | High | 8 | Sandhya | Sprint 2 | To Do | cloud,encryption,security
US-110 | Story | Encryption and Transmission | Build a transmission module | As a developer, I want to build a transmission module that encrypts before upload and decrypts after download so that uploaded files are processed consistently. | 1. The delivered system provides a transmission module that encrypts before upload and decrypts after download. 2. Configuration values are read from settings rather than hard-coded. 3. Edge cases found during testing are handled. 4. The cloud administrator can inspect the outcome. | High | 8 | Indhu | Sprint 2 | To Do | cloud,encryption,security
US-111 | Story | Encryption and Transmission | Train a machine learning classifier | As a developer, I want to train a machine learning classifier on a benchmark intrusion dataset to detect anomalous access so that the behaviour is correct for both typical and edge inputs. | 1. The team has trained a machine learning classifier on a benchmark intrusion dataset to detect anomalous access. 2. Processing completes within the agreed time budget. 3. The module has unit tests covering its main paths. 4. The step is documented in the project README. | High | 8 | Vaishnavi | Sprint 3 | To Do | cloud,encryption,security
US-112 | Story | Encryption and Transmission | Integrate the detection layer | As a developer, I want to integrate the detection layer so that suspicious sessions are flagged and logged during transfer. | 1. The delivered system provides the detection layer. 2. Invalid or missing uploaded files are rejected with a clear message. 3. Behaviour is verified on a representative sample of uploaded files. 4. Errors are logged with enough context to debug them. | High | 8 | Sriteja | Sprint 3 | To Do | cloud,encryption,security
US-113 | Story | Encryption and Transmission | Evaluate encryption and decryption time | As a developer, I want to evaluate encryption and decryption time, throughput overhead and intrusion detection accuracy so that the requirement can be demonstrated at review. | 1. The team has evaluated encryption and decryption time, throughput overhead and intrusion detection accuracy. 2. The step runs end to end on the full project dataset. 3. Results are persisted and can be retrieved later. 4. The run is reproducible from a fixed configuration. | High | 8 | Sandhya | Sprint 3 | To Do | cloud,encryption,security
US-114 | Story | Encryption and Transmission | Review encryption and transmission output | As a data owner, I want to review the encryption and transmission output in the interface so that I can confirm it before acting on it. | 1. The most recent output is shown together with its inputs. 2. The data owner can flag an incorrect result. 3. Flagged items are queued for the cloud administrator to check. | Medium | 5 | Indhu | Sprint 2 | To Do | cloud,backend
US-115 | Task | Encryption and Transmission | Retry and logging for encryption and transmission | As a system, I want to retry and log failures in encryption and transmission so that a transient error does not lose data. | 1. Failed operations retry with backoff. 2. Repeated failures raise an alert. 3. Every failure is logged with its input reference. | Medium | 5 | Vaishnavi | Sprint 3 | To Do | cloud,backend
US-116 | Story | Encryption and Transmission | Tune encryption and transmission | As a developer, I want to tune encryption and transmission on validation data so that accuracy improves before release. | 1. A parameter search is run and recorded. 2. Before and after metrics are compared. 3. The chosen settings are committed to the repository. | Medium | 5 | Sriteja | Sprint 3 | To Do | cloud,backend
US-117 | Task | Encryption and Transmission | Expose encryption and transmission through an API | As a developer, I want to expose encryption and transmission through an internal API so that the interface and other modules can consume it. | 1. Endpoint documented with request and response examples. 2. Errors return meaningful status codes. 3. The endpoint is covered by an integration test. | Medium | 5 | Sandhya | Sprint 3 | To Do | cloud,backend
US-118 | Story | Results and Reporting | Results dashboard | As a data owner, I want a dashboard summarising the latest results so that I can understand the outcome at a glance. | 1. Key figures are shown with the date of the run. 2. Charts render correctly for an empty and a full dataset. 3. The dashboard loads within an acceptable time. | High | 5 | Indhu | Sprint 4 | To Do | dashboard,frontend
US-119 | Story | Results and Reporting | Export report | As a cloud administrator, I want to export the results as PDF or CSV so that I can share them outside the system. | 1. The export includes the figures shown on screen. 2. The file name carries the project and the date. 3. Large exports complete without timing out. | Medium | 3 | Vaishnavi | Sprint 4 | To Do | export,reporting
US-120 | Story | Results and Reporting | History and search | As a data owner, I want to search past records so that I can compare an earlier result with the current one. | 1. Records can be filtered by date and by status. 2. Search returns promptly on the full dataset. 3. An empty result set is shown clearly. | Medium | 3 | Sriteja | Sprint 4 | To Do | search,frontend
US-121 | Story | Notifications | Notify data owner of an important outcome | As a data owner, I want to be notified when the system produces an outcome needing my attention so that I can respond promptly. | 1. A notification is raised when the configured condition is met. 2. The data owner can see the notification history. 3. Repeated notifications for the same event are suppressed. | Medium | 3 | Sandhya | Sprint 4 | To Do | notification,alerts
US-122 | Spike | Evaluation | Define and measure evaluation metrics | Decide which metrics judge this project and measure the current build against them. | 1. Metrics chosen and justified for this problem. 2. Current scores recorded as a baseline. 3. A target for the final review is agreed. | Low | 3 | Indhu | Sprint 5 | To Do | evaluation,research
US-123 | Task | Release | Deployment and user documentation | As a developer, I want the system deployed with setup and usage documentation so that the evaluators can run and demonstrate it. | 1. The application runs on the target environment. 2. Setup steps are documented and verified from scratch. 3. A short user guide covers the main workflow. | Low | 2 | Vaishnavi | Sprint 5 | To Do | deployment,docs

## Field Guide
BharatBuild — User Stories Excel Import Guide
Fields marked with * are mandatory. Assignee Roll No and Assignee Name must match a registered student in the selected batch.
Field | Mandatory | Example | Validation / Usage
Story ID | No | US-101 | Optional unique reference. BharatBuild may generate one if blank.
Work Type | Yes | Story | Allowed: Story, Task, Spike.
Epic | No | Authentication | Existing or importable epic/feature grouping.
Summary | Yes | Student Login and Authentication | Short title of the user story.
Description | Yes | As a student, I want to... | Detailed functional/user-story description.
Acceptance Criteria | Yes | 1. Valid login... | Use numbered lines in one cell.
Priority | Yes | High | Highest, High, Medium, Low, Lowest.
Story Points | Yes | 5 | Numeric estimate; recommended Fibonacci values such as 1,2,3,5,8,13.
Assignee Roll No | Yes | 23K91A05L5 | Must belong to the currently selected project batch.
Assignee Name | Yes | Royyala Sindhuja | Must match the student identified by Assignee Roll No.
Sprint | No | Sprint 1 | If blank, story remains unscheduled/backlog.
Status | Yes | To Do | Allowed: To Do, In Progress, In Review, Done.
Labels | No | authentication,frontend | Comma-separated tags.

## Import Process
Trainer Import Workflow
Step | Action | Expected Result
1 | Select Department → Section → Batch → Project | BharatBuild establishes project context.
2 | Open User Stories → Import Stories | Import wizard opens.
3 | Upload this Excel file | Columns are detected automatically.
4 | Map Excel columns | Excel fields are mapped to BharatBuild story fields.
5 | Validate | Missing mandatory data, duplicate IDs and invalid assignees are flagged.
6 | Preview | Trainer reviews stories and student assignments.
7 | Confirm Import | Valid stories are created under the selected project.