## User Stories Import
Story ID | Work Type * | Epic | Summary * | Description * | Acceptance Criteria * | Priority * | Story Points * | Assignee Name * | Sprint | Status * | Labels
US-101 | Story | Platform Access | Driver registration and login | As a driver, I want to register and sign in with my own credentials so that I can reach my workspace securely. | 1. Valid credentials sign the driver in. 2. Invalid credentials show a clear error. 3. A session is created and expires after inactivity. 4. Passwords are stored only as salted hashes. | High | 5 | B. Pranitha | Sprint 1 | To Do | sensors,auth,frontend
US-102 | Story | Platform Access | Password reset | As a driver, I want to reset a forgotten password so that I can regain access without an administrator. | 1. A reset link or OTP is sent to the registered contact. 2. The link expires after a set time. 3. A new password can be saved and used to sign in. 4. Reset attempts are recorded in the audit log. | Medium | 3 | Bantu Kavya | Sprint 1 | To Do | auth,security
US-103 | Story | Platform Access | Role-based access for fleet supervisor | As a fleet supervisor, I want a separate privileged view so that I can manage records without using a driver account. | 1. Driver and fleet supervisor roles see different menus. 2. Privileged actions are refused for a normal driver. 3. Every privileged action is written to an audit trail. | High | 5 | Dasari Viveka Sarveshwari | Sprint 1 | To Do | auth,rbac
US-104 | Story | Readings Intake | Submit sensor and camera readings | As a driver, I want to submit sensor and camera readings to the system so that they can be processed. | 1. Supported formats are accepted and stored. 2. Unsupported or oversized input is refused with a reason. 3. Each submission is timestamped and linked to its owner. 4. A confirmation is shown once the upload completes. | Highest | 5 | Bekkam Vamshi | Sprint 1 | To Do | sensors,ingestion
US-105 | Story | Readings Intake | Validate and clean sensor and camera readings | As a system, I want to validate and clean incoming sensor and camera readings so that poor quality input does not corrupt later stages. | 1. Missing and malformed fields are detected. 2. Duplicates are removed before processing. 3. A validation summary is available for each batch. 4. Rejected records are retained for review. | High | 5 | B. Pranitha | Sprint 1 | To Do | validation,data
US-106 | Task | Readings Intake | Project repository and environment setup | As a developer, I want a version-controlled repository with a reproducible environment so that the whole team builds on the same base. | 1. Repository created and branch rules agreed. 2. Dependencies pinned in a requirements file. 3. The project runs from a clean checkout by following the README. | Medium | 3 | Bantu Kavya | Sprint 1 | To Do | setup,devops
US-107 | Spike | Intoxication Detection | Evaluate approaches for intoxication detection | Research candidate approaches for intoxication detection and record which one this project adopts. The surveyed work concentrates on drowsiness and embedded driver-state assessment. The gap is an intoxication-specific vision model coupled to a prevention action rather than a warning. | 1. At least three approaches are compared. 2. Strengths and limits of each are written up. 3. A recommendation with reasons is recorded. | Low | 3 | Dasari Viveka Sarveshwari | Sprint 2 | To Do | research,spike
US-108 | Story | Intoxication Detection | Capture driver facial video | As a system, I want to capture driver facial video using a webcam and detect the face and key landmarks in real time so that the rest of the intoxication detection pipeline can depend on it. | 1. The system captures driver facial video using a webcam and detect the face and key landmarks in real time. 2. Invalid or missing sensor and camera readings are rejected with a clear message. 3. Behaviour is verified on a representative sample of sensor and camera readings. 4. Errors are logged with enough context to debug them. | Highest | 8 | Bekkam Vamshi | Sprint 2 | To Do | sensors,safety,ml
US-109 | Story | Intoxication Detection | Extract impairment cues such as eye closure ratio | As a system, I want to extract impairment cues such as eye closure ratio, blink frequency, gaze deviation and head movement so that the capability is available to the modules that follow. | 1. The system extracts impairment cues such as eye closure ratio, blink frequency, gaze deviation and head movement. 2. The step runs end to end on the full project dataset. 3. Results are persisted and can be retrieved later. 4. The run is reproducible from a fixed configuration. | High | 8 | B. Pranitha | Sprint 2 | To Do | sensors,safety,ml
US-110 | Story | Intoxication Detection | Train a deep learning classifier | As a developer, I want to train a deep learning classifier to distinguish a sober driver from an intoxicated one so that sensor and camera readings are processed consistently. | 1. The team has trained a deep learning classifier to distinguish a sober driver from an intoxicated one. 2. Configuration values are read from settings rather than hard-coded. 3. Edge cases found during testing are handled. 4. The fleet supervisor can inspect the outcome. | High | 8 | Bantu Kavya | Sprint 2 | To Do | sensors,safety,ml
US-111 | Story | Intoxication Detection | Run inference continuously | As a system, I want to run inference continuously and raise an alert when the impairment score crosses a threshold so that the behaviour is correct for both typical and edge inputs. | 1. The system runs inference continuously and raise an alert when the impairment score crosses a threshold. 2. Processing completes within the agreed time budget. 3. The module has unit tests covering its main paths. 4. The step is documented in the project README. | High | 8 | Dasari Viveka Sarveshwari | Sprint 3 | To Do | sensors,safety,ml
US-112 | Story | Intoxication Detection | Integrate a prevention action such as an ignition warning | As a developer, I want to integrate a prevention action such as an ignition warning or notification to a registered contact so that later features can build on a dependable output. | 1. The delivered system provides a prevention action such as an ignition warning or notification to a registered contact. 2. Invalid or missing sensor and camera readings are rejected with a clear message. 3. Behaviour is verified on a representative sample of sensor and camera readings. 4. Errors are logged with enough context to debug them. | High | 8 | Bekkam Vamshi | Sprint 3 | To Do | sensors,safety,ml
US-113 | Story | Intoxication Detection | Evaluate accuracy, false positive rate | As a developer, I want to evaluate accuracy, false positive rate and performance under low light and partial occlusion so that the requirement can be demonstrated at review. | 1. The team has evaluated accuracy, false positive rate and performance under low light and partial occlusion. 2. The step runs end to end on the full project dataset. 3. Results are persisted and can be retrieved later. 4. The run is reproducible from a fixed configuration. | High | 8 | B. Pranitha | Sprint 3 | To Do | sensors,safety,ml
US-114 | Story | Intoxication Detection | Review intoxication detection output | As a driver, I want to review the intoxication detection output in the interface so that I can confirm it before acting on it. | 1. The most recent output is shown together with its inputs. 2. The driver can flag an incorrect result. 3. Flagged items are queued for the fleet supervisor to check. | Medium | 5 | Bantu Kavya | Sprint 2 | To Do | sensors,backend
US-115 | Task | Intoxication Detection | Retry and logging for intoxication detection | As a system, I want to retry and log failures in intoxication detection so that a transient error does not lose data. | 1. Failed operations retry with backoff. 2. Repeated failures raise an alert. 3. Every failure is logged with its input reference. | Medium | 5 | Dasari Viveka Sarveshwari | Sprint 3 | To Do | sensors,backend
US-116 | Story | Intoxication Detection | Tune intoxication detection | As a developer, I want to tune intoxication detection on validation data so that accuracy improves before release. | 1. A parameter search is run and recorded. 2. Before and after metrics are compared. 3. The chosen settings are committed to the repository. | Medium | 5 | Bekkam Vamshi | Sprint 3 | To Do | sensors,backend
US-117 | Task | Intoxication Detection | Expose intoxication detection through an API | As a developer, I want to expose intoxication detection through an internal API so that the interface and other modules can consume it. | 1. Endpoint documented with request and response examples. 2. Errors return meaningful status codes. 3. The endpoint is covered by an integration test. | Medium | 5 | B. Pranitha | Sprint 3 | To Do | sensors,backend
US-118 | Story | Results and Reporting | Results dashboard | As a driver, I want a dashboard summarising the latest results so that I can understand the outcome at a glance. | 1. Key figures are shown with the date of the run. 2. Charts render correctly for an empty and a full dataset. 3. The dashboard loads within an acceptable time. | High | 5 | Bantu Kavya | Sprint 4 | To Do | dashboard,frontend
US-119 | Story | Results and Reporting | Export report | As a fleet supervisor, I want to export the results as PDF or CSV so that I can share them outside the system. | 1. The export includes the figures shown on screen. 2. The file name carries the project and the date. 3. Large exports complete without timing out. | Medium | 3 | Dasari Viveka Sarveshwari | Sprint 4 | To Do | export,reporting
US-120 | Story | Results and Reporting | History and search | As a driver, I want to search past records so that I can compare an earlier result with the current one. | 1. Records can be filtered by date and by status. 2. Search returns promptly on the full dataset. 3. An empty result set is shown clearly. | Medium | 3 | Bekkam Vamshi | Sprint 4 | To Do | search,frontend
US-121 | Story | Notifications | Notify driver of an important outcome | As a driver, I want to be notified when the system produces an outcome needing my attention so that I can respond promptly. | 1. A notification is raised when the configured condition is met. 2. The driver can see the notification history. 3. Repeated notifications for the same event are suppressed. | Medium | 3 | B. Pranitha | Sprint 4 | To Do | notification,alerts
US-122 | Spike | Evaluation | Define and measure evaluation metrics | Decide which metrics judge this project and measure the current build against them. | 1. Metrics chosen and justified for this problem. 2. Current scores recorded as a baseline. 3. A target for the final review is agreed. | Low | 3 | Bantu Kavya | Sprint 5 | To Do | evaluation,research
US-123 | Task | Release | Deployment and user documentation | As a developer, I want the system deployed with setup and usage documentation so that the evaluators can run and demonstrate it. | 1. The application runs on the target environment. 2. Setup steps are documented and verified from scratch. 3. A short user guide covers the main workflow. | Low | 2 | Dasari Viveka Sarveshwari | Sprint 5 | To Do | deployment,docs

## Field Guide
BharatBuild — User Stories Excel Import Guide
Fields marked with * are mandatory. Assignee Roll No and Assignee Name must match a registered student in the selected batch.
Field | Mandatory | Example | Validation / Usage
Story ID | No | US-101 | Optional unique reference. BharatBuild may generate one if blank.
Work Type | Yes | Story | Allowed: Story, Task, Spike.
Epic | No | Authentication | Existing or importable epic/feature grouping.
Summary | Yes | Student Login and Authentication | Short title of the user story.
Description | Yes | As a student, I want to... | Detailed functional/user-story description.
Acceptance Criteria | Yes | 1. Valid login... | Use numbered lines in one cell.
Priority | Yes | High | Highest, High, Medium, Low, Lowest.
Story Points | Yes | 5 | Numeric estimate; recommended Fibonacci values such as 1,2,3,5,8,13.
Assignee Roll No | Yes | 23K91A05L5 | Must belong to the currently selected project batch.
Assignee Name | Yes | Royyala Sindhuja | Must match the student identified by Assignee Roll No.
Sprint | No | Sprint 1 | If blank, story remains unscheduled/backlog.
Status | Yes | To Do | Allowed: To Do, In Progress, In Review, Done.
Labels | No | authentication,frontend | Comma-separated tags.

## Import Process
Trainer Import Workflow
Step | Action | Expected Result
1 | Select Department → Section → Batch → Project | BharatBuild establishes project context.
2 | Open User Stories → Import Stories | Import wizard opens.
3 | Upload this Excel file | Columns are detected automatically.
4 | Map Excel columns | Excel fields are mapped to BharatBuild story fields.
5 | Validate | Missing mandatory data, duplicate IDs and invalid assignees are flagged.
6 | Preview | Trainer reviews stories and student assignments.
7 | Confirm Import | Valid stories are created under the selected project.