## User Stories Import
Story ID | Work Type * | Epic | Summary * | Description * | Acceptance Criteria * | Priority * | Story Points * | Assignee Name * | Sprint | Status * | Labels
US-101 | Story | Platform Access | Patient registration and login | As a patient, I want to register and sign in with my own credentials so that I can reach my workspace securely. | 1. Valid credentials sign the patient in. 2. Invalid credentials show a clear error. 3. A session is created and expires after inactivity. 4. Passwords are stored only as salted hashes. | High | 5 | BADAVENI SRINATH | Sprint 1 | To Do | triage,auth,frontend
US-102 | Story | Platform Access | Password reset | As a patient, I want to reset a forgotten password so that I can regain access without an administrator. | 1. A reset link or OTP is sent to the registered contact. 2. The link expires after a set time. 3. A new password can be saved and used to sign in. 4. Reset attempts are recorded in the audit log. | Medium | 3 | BASANI AVINASH | Sprint 1 | To Do | auth,security
US-103 | Story | Platform Access | Role-based access for triage nurse | As a triage nurse, I want a separate privileged view so that I can manage records without using a patient account. | 1. Patient and triage nurse roles see different menus. 2. Privileged actions are refused for a normal patient. 3. Every privileged action is written to an audit trail. | High | 5 | DEGALA PRANEETH | Sprint 1 | To Do | auth,rbac
US-104 | Story | Vitals Intake | Submit reported symptoms and vitals | As a patient, I want to submit reported symptoms and vitals to the system so that they can be processed. | 1. Supported formats are accepted and stored. 2. Unsupported or oversized input is refused with a reason. 3. Each submission is timestamped and linked to its owner. 4. A confirmation is shown once the upload completes. | Highest | 5 | BONTHA SAISREE | Sprint 1 | To Do | triage,ingestion
US-105 | Story | Vitals Intake | Validate and clean reported symptoms and vitals | As a system, I want to validate and clean incoming reported symptoms and vitals so that poor quality input does not corrupt later stages. | 1. Missing and malformed fields are detected. 2. Duplicates are removed before processing. 3. A validation summary is available for each batch. 4. Rejected records are retained for review. | High | 5 | BADAVENI SRINATH | Sprint 1 | To Do | validation,data
US-106 | Task | Vitals Intake | Project repository and environment setup | As a developer, I want a version-controlled repository with a reproducible environment so that the whole team builds on the same base. | 1. Repository created and branch rules agreed. 2. Dependencies pinned in a requirements file. 3. The project runs from a clean checkout by following the README. | Medium | 3 | BASANI AVINASH | Sprint 1 | To Do | setup,devops
US-107 | Spike | Triage Engine | Evaluate approaches for triage engine | Research candidate approaches for triage engine and record which one this project adopts. The surveyed models are evaluated on single-modality structured data. The gap is a multi-agent pipeline that fuses OCR, clinical text and tabular vitals and exposes the reasoning. | 1. At least three approaches are compared. 2. Strengths and limits of each are written up. 3. A recommendation with reasons is recorded. | Low | 3 | DEGALA PRANEETH | Sprint 2 | To Do | research,spike
US-108 | Story | Triage Engine | Build an OCR stage that converts scanned medical reports | As a developer, I want to build an OCR stage that converts scanned medical reports into machine-readable clinical text so that the rest of the triage engine pipeline can depend on it. | 1. The delivered system provides an OCR stage that converts scanned medical reports into machine-readable clinical text. 2. Invalid or missing reported symptoms and vitals are rejected with a clear message. 3. Behaviour is verified on a representative sample of reported symptoms and vitals. 4. Errors are logged with enough context to debug them. | Highest | 8 | BONTHA SAISREE | Sprint 2 | To Do | triage,healthcare,ai
US-109 | Story | Triage Engine | Apply a medical language model to extract symptoms | As a system, I want to apply a medical language model to extract symptoms, findings and history from that text so that the capability is available to the modules that follow. | 1. The system applies a medical language model to extract symptoms, findings and history from that text. 2. The step runs end to end on the full project dataset. 3. Results are persisted and can be retrieved later. 4. The run is reproducible from a fixed configuration. | High | 8 | BADAVENI SRINATH | Sprint 2 | To Do | triage,healthcare,ai
US-110 | Story | Triage Engine | Combine text-derived features with tabular vitals | As a system, I want to combine text-derived features with tabular vitals in a single patient representation so that reported symptoms and vitals are processed consistently. | 1. The system combines text-derived features with tabular vitals in a single patient representation. 2. Configuration values are read from settings rather than hard-coded. 3. Edge cases found during testing are handled. 4. The triage nurse can inspect the outcome. | High | 8 | BASANI AVINASH | Sprint 2 | To Do | triage,healthcare,ai
US-111 | Story | Triage Engine | Train a model that assigns a clinical risk level | As a developer, I want to train a model that assigns a clinical risk level and a triage priority to each patient so that the behaviour is correct for both typical and edge inputs. | 1. The team has trained a model that assigns a clinical risk level and a triage priority to each patient. 2. Processing completes within the agreed time budget. 3. The module has unit tests covering its main paths. 4. The step is documented in the project README. | High | 8 | DEGALA PRANEETH | Sprint 3 | To Do | triage,healthcare,ai
US-112 | Story | Triage Engine | Add an explainability layer | As a developer, I want to add an explainability layer that shows which findings drove the assigned priority so that later features can build on a dependable output. | 1. The delivered system provides an explainability layer that shows which findings drove the assigned priority. 2. Invalid or missing reported symptoms and vitals are rejected with a clear message. 3. Behaviour is verified on a representative sample of reported symptoms and vitals. 4. Errors are logged with enough context to debug them. | High | 8 | BONTHA SAISREE | Sprint 3 | To Do | triage,healthcare,ai
US-113 | Story | Triage Engine | Evaluate triage accuracy against clinician-assigned priority | As a developer, I want to evaluate triage accuracy against clinician-assigned priority and measure processing time per patient so that the requirement can be demonstrated at review. | 1. The team has evaluated triage accuracy against clinician-assigned priority and measure processing time per patient. 2. The step runs end to end on the full project dataset. 3. Results are persisted and can be retrieved later. 4. The run is reproducible from a fixed configuration. | High | 8 | BADAVENI SRINATH | Sprint 3 | To Do | triage,healthcare,ai
US-114 | Story | Triage Engine | Review triage engine output | As a patient, I want to review the triage engine output in the interface so that I can confirm it before acting on it. | 1. The most recent output is shown together with its inputs. 2. The patient can flag an incorrect result. 3. Flagged items are queued for the triage nurse to check. | Medium | 5 | BASANI AVINASH | Sprint 2 | To Do | triage,backend
US-115 | Task | Triage Engine | Retry and logging for triage engine | As a system, I want to retry and log failures in triage engine so that a transient error does not lose data. | 1. Failed operations retry with backoff. 2. Repeated failures raise an alert. 3. Every failure is logged with its input reference. | Medium | 5 | DEGALA PRANEETH | Sprint 3 | To Do | triage,backend
US-116 | Story | Triage Engine | Tune triage engine | As a developer, I want to tune triage engine on validation data so that accuracy improves before release. | 1. A parameter search is run and recorded. 2. Before and after metrics are compared. 3. The chosen settings are committed to the repository. | Medium | 5 | BONTHA SAISREE | Sprint 3 | To Do | triage,backend
US-117 | Task | Triage Engine | Expose triage engine through an API | As a developer, I want to expose triage engine through an internal API so that the interface and other modules can consume it. | 1. Endpoint documented with request and response examples. 2. Errors return meaningful status codes. 3. The endpoint is covered by an integration test. | Medium | 5 | BADAVENI SRINATH | Sprint 3 | To Do | triage,backend
US-118 | Story | Results and Reporting | Results dashboard | As a patient, I want a dashboard summarising the latest results so that I can understand the outcome at a glance. | 1. Key figures are shown with the date of the run. 2. Charts render correctly for an empty and a full dataset. 3. The dashboard loads within an acceptable time. | High | 5 | BASANI AVINASH | Sprint 4 | To Do | dashboard,frontend
US-119 | Story | Results and Reporting | Export report | As a triage nurse, I want to export the results as PDF or CSV so that I can share them outside the system. | 1. The export includes the figures shown on screen. 2. The file name carries the project and the date. 3. Large exports complete without timing out. | Medium | 3 | DEGALA PRANEETH | Sprint 4 | To Do | export,reporting
US-120 | Story | Results and Reporting | History and search | As a patient, I want to search past records so that I can compare an earlier result with the current one. | 1. Records can be filtered by date and by status. 2. Search returns promptly on the full dataset. 3. An empty result set is shown clearly. | Medium | 3 | BONTHA SAISREE | Sprint 4 | To Do | search,frontend
US-121 | Story | Notifications | Notify patient of an important outcome | As a patient, I want to be notified when the system produces an outcome needing my attention so that I can respond promptly. | 1. A notification is raised when the configured condition is met. 2. The patient can see the notification history. 3. Repeated notifications for the same event are suppressed. | Medium | 3 | BADAVENI SRINATH | Sprint 4 | To Do | notification,alerts
US-122 | Spike | Evaluation | Define and measure evaluation metrics | Decide which metrics judge this project and measure the current build against them. | 1. Metrics chosen and justified for this problem. 2. Current scores recorded as a baseline. 3. A target for the final review is agreed. | Low | 3 | BASANI AVINASH | Sprint 5 | To Do | evaluation,research
US-123 | Task | Release | Deployment and user documentation | As a developer, I want the system deployed with setup and usage documentation so that the evaluators can run and demonstrate it. | 1. The application runs on the target environment. 2. Setup steps are documented and verified from scratch. 3. A short user guide covers the main workflow. | Low | 2 | DEGALA PRANEETH | Sprint 5 | To Do | deployment,docs

## Field Guide
BharatBuild — User Stories Excel Import Guide
Fields marked with * are mandatory. Assignee Roll No and Assignee Name must match a registered student in the selected batch.
Field | Mandatory | Example | Validation / Usage
Story ID | No | US-101 | Optional unique reference. BharatBuild may generate one if blank.
Work Type | Yes | Story | Allowed: Story, Task, Spike.
Epic | No | Authentication | Existing or importable epic/feature grouping.
Summary | Yes | Student Login and Authentication | Short title of the user story.
Description | Yes | As a student, I want to... | Detailed functional/user-story description.
Acceptance Criteria | Yes | 1. Valid login... | Use numbered lines in one cell.
Priority | Yes | High | Highest, High, Medium, Low, Lowest.
Story Points | Yes | 5 | Numeric estimate; recommended Fibonacci values such as 1,2,3,5,8,13.
Assignee Roll No | Yes | 23K91A05L5 | Must belong to the currently selected project batch.
Assignee Name | Yes | Royyala Sindhuja | Must match the student identified by Assignee Roll No.
Sprint | No | Sprint 1 | If blank, story remains unscheduled/backlog.
Status | Yes | To Do | Allowed: To Do, In Progress, In Review, Done.
Labels | No | authentication,frontend | Comma-separated tags.

## Import Process
Trainer Import Workflow
Step | Action | Expected Result
1 | Select Department → Section → Batch → Project | BharatBuild establishes project context.
2 | Open User Stories → Import Stories | Import wizard opens.
3 | Upload this Excel file | Columns are detected automatically.
4 | Map Excel columns | Excel fields are mapped to BharatBuild story fields.
5 | Validate | Missing mandatory data, duplicate IDs and invalid assignees are flagged.
6 | Preview | Trainer reviews stories and student assignments.
7 | Confirm Import | Valid stories are created under the selected project.