## User Stories Import
Story ID | Work Type * | Epic | Summary * | Description * | Acceptance Criteria * | Priority * | Story Points * | Assignee Name * | Sprint | Status * | Labels
US-101 | Story | Platform Access | Patient registration and login | As a patient, I want to register and sign in with my own credentials so that I can reach my workspace securely. | 1. Valid credentials sign the patient in. 2. Invalid credentials show a clear error. 3. A session is created and expires after inactivity. 4. Passwords are stored only as salted hashes. | High | 5 | Banoth Swapna | Sprint 1 | To Do | nlp,auth,frontend
US-102 | Story | Platform Access | Password reset | As a patient, I want to reset a forgotten password so that I can regain access without an administrator. | 1. A reset link or OTP is sent to the registered contact. 2. The link expires after a set time. 3. A new password can be saved and used to sign in. 4. Reset attempts are recorded in the audit log. | Medium | 3 | Bekkam Varshitha | Sprint 1 | To Do | auth,security
US-103 | Story | Platform Access | Role-based access for physician | As a physician, I want a separate privileged view so that I can manage records without using a patient account. | 1. Patient and physician roles see different menus. 2. Privileged actions are refused for a normal patient. 3. Every privileged action is written to an audit trail. | High | 5 | A Navadeep Reddy | Sprint 1 | To Do | auth,rbac
US-104 | Story | Documents Intake | Submit lab report documents | As a patient, I want to submit lab report documents to the system so that they can be processed. | 1. Supported formats are accepted and stored. 2. Unsupported or oversized input is refused with a reason. 3. Each submission is timestamped and linked to its owner. 4. A confirmation is shown once the upload completes. | Highest | 5 | Budigam Manoj | Sprint 1 | To Do | nlp,ingestion
US-105 | Story | Documents Intake | Validate and clean lab report documents | As a system, I want to validate and clean incoming lab report documents so that poor quality input does not corrupt later stages. | 1. Missing and malformed fields are detected. 2. Duplicates are removed before processing. 3. A validation summary is available for each batch. 4. Rejected records are retained for review. | High | 5 | Banoth Swapna | Sprint 1 | To Do | validation,data
US-106 | Task | Documents Intake | Project repository and environment setup | As a developer, I want a version-controlled repository with a reproducible environment so that the whole team builds on the same base. | 1. Repository created and branch rules agreed. 2. Dependencies pinned in a requirements file. 3. The project runs from a clean checkout by following the README. | Medium | 3 | Bekkam Varshitha | Sprint 1 | To Do | setup,devops
US-107 | Spike | Report Extraction | Evaluate approaches for report extraction | Research candidate approaches for report extraction and record which one this project adopts. The base paper applies RAG to blood report interpretation for a single condition. The gap is a general report-analysis platform covering arbitrary lab parameters with extraction,. | 1. At least three approaches are compared. 2. Strengths and limits of each are written up. 3. A recommendation with reasons is recorded. | Low | 3 | A Navadeep Reddy | Sprint 2 | To Do | research,spike
US-108 | Story | Report Extraction | Accept lab reports in PDF or scanned image form | As a system, I want to accept lab reports in PDF or scanned image form and extract text using high-speed OCR so that the rest of the report extraction pipeline can depend on it. | 1. The system accepts lab reports in PDF or scanned image form and extract text using high-speed OCR. 2. Invalid or missing lab report documents are rejected with a clear message. 3. Behaviour is verified on a representative sample of lab report documents. 4. Errors are logged with enough context to debug them. | Highest | 8 | Budigam Manoj | Sprint 2 | To Do | nlp,healthcare,ocr
US-109 | Story | Report Extraction | Apply named entity recognition to identify test parameters | As a system, I want to apply named entity recognition to identify test parameters, values, units and reference ranges so that the capability is available to the modules that follow. | 1. The system applies named entity recognition to identify test parameters, values, units and reference ranges. 2. The step runs end to end on the full project dataset. 3. Results are persisted and can be retrieved later. 4. The run is reproducible from a fixed configuration. | High | 8 | Banoth Swapna | Sprint 2 | To Do | nlp,healthcare,ocr
US-110 | Story | Report Extraction | Compare each extracted value against its reference range | As a developer, I want to compare each extracted value against its reference range and flag abnormal results so that lab report documents are processed consistently. | 1. The team has compared each extracted value against its reference range and flag abnormal results. 2. Configuration values are read from settings rather than hard-coded. 3. Edge cases found during testing are handled. 4. The physician can inspect the outcome. | High | 8 | Bekkam Varshitha | Sprint 2 | To Do | nlp,healthcare,ocr
US-111 | Story | Report Extraction | Generate plain-language explanations for abnormal findings | As a system, I want to generate plain-language explanations for abnormal findings, grounded in trusted medical sources so that the behaviour is correct for both typical and edge inputs. | 1. The system generates plain-language explanations for abnormal findings, grounded in trusted medical sources. 2. Processing completes within the agreed time budget. 3. The module has unit tests covering its main paths. 4. The step is documented in the project README. | High | 8 | A Navadeep Reddy | Sprint 3 | To Do | nlp,healthcare,ocr
US-112 | Story | Report Extraction | Track parameters across successive reports | As a system, I want to track parameters across successive reports to display health trends over time so that later features can build on a dependable output. | 1. The system tracks parameters across successive reports to display health trends over time. 2. Invalid or missing lab report documents are rejected with a clear message. 3. Behaviour is verified on a representative sample of lab report documents. 4. Errors are logged with enough context to debug them. | High | 8 | Budigam Manoj | Sprint 3 | To Do | nlp,healthcare,ocr
US-113 | Story | Report Extraction | Present results through a dashboard | As a system, I want to present results through a dashboard and evaluate extraction accuracy against manually labelled reports so that the requirement can be demonstrated at review. | 1. The system presents results through a dashboard and evaluate extraction accuracy against manually labelled reports. 2. The step runs end to end on the full project dataset. 3. Results are persisted and can be retrieved later. 4. The run is reproducible from a fixed configuration. | High | 8 | Banoth Swapna | Sprint 3 | To Do | nlp,healthcare,ocr
US-114 | Story | Report Extraction | Review report extraction output | As a patient, I want to review the report extraction output in the interface so that I can confirm it before acting on it. | 1. The most recent output is shown together with its inputs. 2. The patient can flag an incorrect result. 3. Flagged items are queued for the physician to check. | Medium | 5 | Bekkam Varshitha | Sprint 2 | To Do | nlp,backend
US-115 | Task | Report Extraction | Retry and logging for report extraction | As a system, I want to retry and log failures in report extraction so that a transient error does not lose data. | 1. Failed operations retry with backoff. 2. Repeated failures raise an alert. 3. Every failure is logged with its input reference. | Medium | 5 | A Navadeep Reddy | Sprint 3 | To Do | nlp,backend
US-116 | Story | Report Extraction | Tune report extraction | As a developer, I want to tune report extraction on validation data so that accuracy improves before release. | 1. A parameter search is run and recorded. 2. Before and after metrics are compared. 3. The chosen settings are committed to the repository. | Medium | 5 | Budigam Manoj | Sprint 3 | To Do | nlp,backend
US-117 | Task | Report Extraction | Expose report extraction through an API | As a developer, I want to expose report extraction through an internal API so that the interface and other modules can consume it. | 1. Endpoint documented with request and response examples. 2. Errors return meaningful status codes. 3. The endpoint is covered by an integration test. | Medium | 5 | Banoth Swapna | Sprint 3 | To Do | nlp,backend
US-118 | Story | Results and Reporting | Results dashboard | As a patient, I want a dashboard summarising the latest results so that I can understand the outcome at a glance. | 1. Key figures are shown with the date of the run. 2. Charts render correctly for an empty and a full dataset. 3. The dashboard loads within an acceptable time. | High | 5 | Bekkam Varshitha | Sprint 4 | To Do | dashboard,frontend
US-119 | Story | Results and Reporting | Export report | As a physician, I want to export the results as PDF or CSV so that I can share them outside the system. | 1. The export includes the figures shown on screen. 2. The file name carries the project and the date. 3. Large exports complete without timing out. | Medium | 3 | A Navadeep Reddy | Sprint 4 | To Do | export,reporting
US-120 | Story | Results and Reporting | History and search | As a patient, I want to search past records so that I can compare an earlier result with the current one. | 1. Records can be filtered by date and by status. 2. Search returns promptly on the full dataset. 3. An empty result set is shown clearly. | Medium | 3 | Budigam Manoj | Sprint 4 | To Do | search,frontend
US-121 | Story | Notifications | Notify patient of an important outcome | As a patient, I want to be notified when the system produces an outcome needing my attention so that I can respond promptly. | 1. A notification is raised when the configured condition is met. 2. The patient can see the notification history. 3. Repeated notifications for the same event are suppressed. | Medium | 3 | Banoth Swapna | Sprint 4 | To Do | notification,alerts
US-122 | Spike | Evaluation | Define and measure evaluation metrics | Decide which metrics judge this project and measure the current build against them. | 1. Metrics chosen and justified for this problem. 2. Current scores recorded as a baseline. 3. A target for the final review is agreed. | Low | 3 | Bekkam Varshitha | Sprint 5 | To Do | evaluation,research
US-123 | Task | Release | Deployment and user documentation | As a developer, I want the system deployed with setup and usage documentation so that the evaluators can run and demonstrate it. | 1. The application runs on the target environment. 2. Setup steps are documented and verified from scratch. 3. A short user guide covers the main workflow. | Low | 2 | A Navadeep Reddy | Sprint 5 | To Do | deployment,docs

## Field Guide
BharatBuild — User Stories Excel Import Guide
Fields marked with * are mandatory. Assignee Roll No and Assignee Name must match a registered student in the selected batch.
Field | Mandatory | Example | Validation / Usage
Story ID | No | US-101 | Optional unique reference. BharatBuild may generate one if blank.
Work Type | Yes | Story | Allowed: Story, Task, Spike.
Epic | No | Authentication | Existing or importable epic/feature grouping.
Summary | Yes | Student Login and Authentication | Short title of the user story.
Description | Yes | As a student, I want to... | Detailed functional/user-story description.
Acceptance Criteria | Yes | 1. Valid login... | Use numbered lines in one cell.
Priority | Yes | High | Highest, High, Medium, Low, Lowest.
Story Points | Yes | 5 | Numeric estimate; recommended Fibonacci values such as 1,2,3,5,8,13.
Assignee Roll No | Yes | 23K91A05L5 | Must belong to the currently selected project batch.
Assignee Name | Yes | Royyala Sindhuja | Must match the student identified by Assignee Roll No.
Sprint | No | Sprint 1 | If blank, story remains unscheduled/backlog.
Status | Yes | To Do | Allowed: To Do, In Progress, In Review, Done.
Labels | No | authentication,frontend | Comma-separated tags.

## Import Process
Trainer Import Workflow
Step | Action | Expected Result
1 | Select Department → Section → Batch → Project | BharatBuild establishes project context.
2 | Open User Stories → Import Stories | Import wizard opens.
3 | Upload this Excel file | Columns are detected automatically.
4 | Map Excel columns | Excel fields are mapped to BharatBuild story fields.
5 | Validate | Missing mandatory data, duplicate IDs and invalid assignees are flagged.
6 | Preview | Trainer reviews stories and student assignments.
7 | Confirm Import | Valid stories are created under the selected project.