## User Stories Import
Story ID | Work Type * | Epic | Summary * | Description * | Acceptance Criteria * | Priority * | Story Points * | Assignee Name * | Sprint | Status * | Labels
US-101 | Story | Platform Access | Platform moderator registration and login | As a platform moderator, I want to register and sign in with my own credentials so that I can reach my workspace securely. | 1. Valid credentials sign the platform moderator in. 2. Invalid credentials show a clear error. 3. A session is created and expires after inactivity. 4. Passwords are stored only as salted hashes. | High | 5 | B. NagaLakshmi | Sprint 1 | To Do | gnn,auth,frontend
US-102 | Story | Platform Access | Password reset | As a platform moderator, I want to reset a forgotten password so that I can regain access without an administrator. | 1. A reset link or OTP is sent to the registered contact. 2. The link expires after a set time. 3. A new password can be saved and used to sign in. 4. Reset attempts are recorded in the audit log. | Medium | 3 | D. Srivatshav | Sprint 1 | To Do | auth,security
US-103 | Story | Platform Access | Role-based access for security analyst | As a security analyst, I want a separate privileged view so that I can manage records without using a platform moderator account. | 1. Platform moderator and security analyst roles see different menus. 2. Privileged actions are refused for a normal platform moderator. 3. Every privileged action is written to an audit trail. | High | 5 | A. Durga | Sprint 1 | To Do | auth,rbac
US-104 | Story | Data Intake | Submit social graph data | As a platform moderator, I want to submit social graph data to the system so that they can be processed. | 1. Supported formats are accepted and stored. 2. Unsupported or oversized input is refused with a reason. 3. Each submission is timestamped and linked to its owner. 4. A confirmation is shown once the upload completes. | Highest | 5 | B. Koushik | Sprint 1 | To Do | gnn,ingestion
US-105 | Story | Data Intake | Validate and clean social graph data | As a system, I want to validate and clean incoming social graph data so that poor quality input does not corrupt later stages. | 1. Missing and malformed fields are detected. 2. Duplicates are removed before processing. 3. A validation summary is available for each batch. 4. Rejected records are retained for review. | High | 5 | B. NagaLakshmi | Sprint 1 | To Do | validation,data
US-106 | Task | Data Intake | Project repository and environment setup | As a developer, I want a version-controlled repository with a reproducible environment so that the whole team builds on the same base. | 1. Repository created and branch rules agreed. 2. Dependencies pinned in a requirements file. 3. The project runs from a clean checkout by following the README. | Medium | 3 | D. Srivatshav | Sprint 1 | To Do | setup,devops
US-107 | Spike | Graph Modelling | Evaluate approaches for graph modelling | Research candidate approaches for graph modelling and record which one this project adopts. The surveyed work applies GNNs to influence and node classification in social graphs. The gap is applying the same relational learning specifically to fake-profile and botnet detection. | 1. At least three approaches are compared. 2. Strengths and limits of each are written up. 3. A recommendation with reasons is recorded. | Low | 3 | A. Durga | Sprint 2 | To Do | research,spike
US-108 | Story | Graph Modelling | Construct a graph representation | As a system, I want to construct a graph representation of the social platform with accounts as nodes and interactions as edges so that the rest of the graph modelling pipeline can depend on it. | 1. The delivered system provides a graph representation of the social platform with accounts as nodes and interactions as edges. 2. Invalid or missing social graph data are rejected with a clear message. 3. Behaviour is verified on a representative sample of social graph data. 4. Errors are logged with enough context to debug them. | Highest | 8 | B. Koushik | Sprint 2 | To Do | gnn,security,graph
US-109 | Story | Graph Modelling | Engineer node features covering profile metadata | As a system, I want to engineer node features covering profile metadata, posting behaviour and interaction frequency so that the capability is available to the modules that follow. | 1. The team has engineered node features covering profile metadata, posting behaviour and interaction frequency. 2. The step runs end to end on the full project dataset. 3. Results are persisted and can be retrieved later. 4. The run is reproducible from a fixed configuration. | High | 8 | B. NagaLakshmi | Sprint 2 | To Do | gnn,security,graph
US-110 | Story | Graph Modelling | Implement and compare GCN, GAT | As a developer, I want to implement and compare GCN, GAT and GraphSAGE architectures for account classification so that social graph data are processed consistently. | 1. The team has implemented and compared GCN, GAT and GraphSAGE architectures for account classification. 2. Configuration values are read from settings rather than hard-coded. 3. Edge cases found during testing are handled. 4. The security analyst can inspect the outcome. | High | 8 | D. Srivatshav | Sprint 2 | To Do | gnn,security,graph
US-111 | Story | Graph Modelling | Detect coordinated botnet clusters | As a system, I want to detect coordinated botnet clusters from the learned graph embeddings so that the behaviour is correct for both typical and edge inputs. | 1. The system detects coordinated botnet clusters from the learned graph embeddings. 2. Processing completes within the agreed time budget. 3. The module has unit tests covering its main paths. 4. The step is documented in the project README. | High | 8 | A. Durga | Sprint 3 | To Do | gnn,security,graph
US-112 | Story | Graph Modelling | Evaluate detection accuracy | As a developer, I want to evaluate detection accuracy, precision and recall against labelled fake-account datasets so that later features can build on a dependable output. | 1. The team has evaluated detection accuracy, precision and recall against labelled fake-account datasets. 2. Invalid or missing social graph data are rejected with a clear message. 3. Behaviour is verified on a representative sample of social graph data. 4. Errors are logged with enough context to debug them. | High | 8 | B. Koushik | Sprint 3 | To Do | gnn,security,graph
US-113 | Story | Graph Modelling | Assess scalability as the number of nodes and edges grows | As a system, I want to assess scalability as the number of nodes and edges grows so that the requirement can be demonstrated at review. | 1. The team has assessed scalability as the number of nodes and edges grows. 2. The step runs end to end on the full project dataset. 3. Results are persisted and can be retrieved later. 4. The run is reproducible from a fixed configuration. | High | 8 | B. NagaLakshmi | Sprint 3 | To Do | gnn,security,graph
US-114 | Story | Graph Modelling | Review graph modelling output | As a platform moderator, I want to review the graph modelling output in the interface so that I can confirm it before acting on it. | 1. The most recent output is shown together with its inputs. 2. The platform moderator can flag an incorrect result. 3. Flagged items are queued for the security analyst to check. | Medium | 5 | D. Srivatshav | Sprint 2 | To Do | gnn,backend
US-115 | Task | Graph Modelling | Retry and logging for graph modelling | As a system, I want to retry and log failures in graph modelling so that a transient error does not lose data. | 1. Failed operations retry with backoff. 2. Repeated failures raise an alert. 3. Every failure is logged with its input reference. | Medium | 5 | A. Durga | Sprint 3 | To Do | gnn,backend
US-116 | Story | Graph Modelling | Tune graph modelling | As a developer, I want to tune graph modelling on validation data so that accuracy improves before release. | 1. A parameter search is run and recorded. 2. Before and after metrics are compared. 3. The chosen settings are committed to the repository. | Medium | 5 | B. Koushik | Sprint 3 | To Do | gnn,backend
US-117 | Task | Graph Modelling | Expose graph modelling through an API | As a developer, I want to expose graph modelling through an internal API so that the interface and other modules can consume it. | 1. Endpoint documented with request and response examples. 2. Errors return meaningful status codes. 3. The endpoint is covered by an integration test. | Medium | 5 | B. NagaLakshmi | Sprint 3 | To Do | gnn,backend
US-118 | Story | Results and Reporting | Results dashboard | As a platform moderator, I want a dashboard summarising the latest results so that I can understand the outcome at a glance. | 1. Key figures are shown with the date of the run. 2. Charts render correctly for an empty and a full dataset. 3. The dashboard loads within an acceptable time. | High | 5 | D. Srivatshav | Sprint 4 | To Do | dashboard,frontend
US-119 | Story | Results and Reporting | Export report | As a security analyst, I want to export the results as PDF or CSV so that I can share them outside the system. | 1. The export includes the figures shown on screen. 2. The file name carries the project and the date. 3. Large exports complete without timing out. | Medium | 3 | A. Durga | Sprint 4 | To Do | export,reporting
US-120 | Story | Results and Reporting | History and search | As a platform moderator, I want to search past records so that I can compare an earlier result with the current one. | 1. Records can be filtered by date and by status. 2. Search returns promptly on the full dataset. 3. An empty result set is shown clearly. | Medium | 3 | B. Koushik | Sprint 4 | To Do | search,frontend
US-121 | Story | Notifications | Notify platform moderator of an important outcome | As a platform moderator, I want to be notified when the system produces an outcome needing my attention so that I can respond promptly. | 1. A notification is raised when the configured condition is met. 2. The platform moderator can see the notification history. 3. Repeated notifications for the same event are suppressed. | Medium | 3 | B. NagaLakshmi | Sprint 4 | To Do | notification,alerts
US-122 | Spike | Evaluation | Define and measure evaluation metrics | Decide which metrics judge this project and measure the current build against them. | 1. Metrics chosen and justified for this problem. 2. Current scores recorded as a baseline. 3. A target for the final review is agreed. | Low | 3 | D. Srivatshav | Sprint 5 | To Do | evaluation,research
US-123 | Task | Release | Deployment and user documentation | As a developer, I want the system deployed with setup and usage documentation so that the evaluators can run and demonstrate it. | 1. The application runs on the target environment. 2. Setup steps are documented and verified from scratch. 3. A short user guide covers the main workflow. | Low | 2 | A. Durga | Sprint 5 | To Do | deployment,docs

## Field Guide
BharatBuild — User Stories Excel Import Guide
Fields marked with * are mandatory. Assignee Roll No and Assignee Name must match a registered student in the selected batch.
Field | Mandatory | Example | Validation / Usage
Story ID | No | US-101 | Optional unique reference. BharatBuild may generate one if blank.
Work Type | Yes | Story | Allowed: Story, Task, Spike.
Epic | No | Authentication | Existing or importable epic/feature grouping.
Summary | Yes | Student Login and Authentication | Short title of the user story.
Description | Yes | As a student, I want to... | Detailed functional/user-story description.
Acceptance Criteria | Yes | 1. Valid login... | Use numbered lines in one cell.
Priority | Yes | High | Highest, High, Medium, Low, Lowest.
Story Points | Yes | 5 | Numeric estimate; recommended Fibonacci values such as 1,2,3,5,8,13.
Assignee Roll No | Yes | 23K91A05L5 | Must belong to the currently selected project batch.
Assignee Name | Yes | Royyala Sindhuja | Must match the student identified by Assignee Roll No.
Sprint | No | Sprint 1 | If blank, story remains unscheduled/backlog.
Status | Yes | To Do | Allowed: To Do, In Progress, In Review, Done.
Labels | No | authentication,frontend | Comma-separated tags.

## Import Process
Trainer Import Workflow
Step | Action | Expected Result
1 | Select Department → Section → Batch → Project | BharatBuild establishes project context.
2 | Open User Stories → Import Stories | Import wizard opens.
3 | Upload this Excel file | Columns are detected automatically.
4 | Map Excel columns | Excel fields are mapped to BharatBuild story fields.
5 | Validate | Missing mandatory data, duplicate IDs and invalid assignees are flagged.
6 | Preview | Trainer reviews stories and student assignments.
7 | Confirm Import | Valid stories are created under the selected project.