## User Stories Import
Story ID | Work Type * | Epic | Summary * | Description * | Acceptance Criteria * | Priority * | Story Points * | Assignee Name * | Sprint | Status * | Labels
US-101 | Story | Platform Access | Voter registration and login | As a voter, I want to register and sign in with my own credentials so that I can reach my workspace securely. | 1. Valid credentials sign the voter in. 2. Invalid credentials show a clear error. 3. A session is created and expires after inactivity. 4. Passwords are stored only as salted hashes. | High | 5 | <Student 1> | Sprint 1 | To Do | blockchain,auth,frontend
US-102 | Story | Platform Access | Password reset | As a voter, I want to reset a forgotten password so that I can regain access without an administrator. | 1. A reset link or OTP is sent to the registered contact. 2. The link expires after a set time. 3. A new password can be saved and used to sign in. 4. Reset attempts are recorded in the audit log. | Medium | 3 | <Student 2> | Sprint 1 | To Do | auth,security
US-103 | Story | Platform Access | Role-based access for election officer | As a election officer, I want a separate privileged view so that I can manage records without using a voter account. | 1. Voter and election officer roles see different menus. 2. Privileged actions are refused for a normal voter. 3. Every privileged action is written to an audit trail. | High | 5 | <Student 3> | Sprint 1 | To Do | auth,rbac
US-104 | Story | Ballots Intake | Submit cast ballots | As a voter, I want to submit cast ballots to the system so that they can be processed. | 1. Supported formats are accepted and stored. 2. Unsupported or oversized input is refused with a reason. 3. Each submission is timestamped and linked to its owner. 4. A confirmation is shown once the upload completes. | Highest | 5 | <Student 4> | Sprint 1 | To Do | blockchain,ingestion
US-105 | Story | Ballots Intake | Validate and clean cast ballots | As a system, I want to validate and clean incoming cast ballots so that poor quality input does not corrupt later stages. | 1. Missing and malformed fields are detected. 2. Duplicates are removed before processing. 3. A validation summary is available for each batch. 4. Rejected records are retained for review. | High | 5 | <Student 1> | Sprint 1 | To Do | validation,data
US-106 | Task | Ballots Intake | Project repository and environment setup | As a developer, I want a version-controlled repository with a reproducible environment so that the whole team builds on the same base. | 1. Repository created and branch rules agreed. 2. Dependencies pinned in a requirements file. 3. The project runs from a clean checkout by following the README. | Medium | 3 | <Student 2> | Sprint 1 | To Do | setup,devops
US-107 | Spike | Ballot Ledger | Evaluate approaches for ballot ledger | Research candidate approaches for ballot ledger and record which one this project adopts. The surveyed work establishes blockchain models for electoral integrity. The gap is combining that ledger with national identity verification and a full election administration. | 1. At least three approaches are compared. 2. Strengths and limits of each are written up. 3. A recommendation with reasons is recorded. | Low | 3 | <Student 3> | Sprint 2 | To Do | research,spike
US-108 | Story | Ballot Ledger | Build voter registration | As a developer, I want to build voter registration and authentication with Aadhaar-based identity verification so that the rest of the ballot ledger pipeline can depend on it. | 1. The delivered system provides voter registration and authentication with Aadhaar-based identity verification. 2. Invalid or missing cast ballots are rejected with a clear message. 3. Behaviour is verified on a representative sample of cast ballots. 4. Errors are logged with enough context to debug them. | Highest | 8 | <Student 4> | Sprint 2 | To Do | blockchain,voting,security
US-109 | Story | Ballot Ledger | Enforce the one-voter-one-vote constraint | As a system, I want to enforce the one-voter-one-vote constraint through identity binding and duplicate checks so that the capability is available to the modules that follow. | 1. The system enforces the one-voter-one-vote constraint through identity binding and duplicate checks. 2. The step runs end to end on the full project dataset. 3. Results are persisted and can be retrieved later. 4. The run is reproducible from a fixed configuration. | High | 8 | <Student 1> | Sprint 2 | To Do | blockchain,voting,security
US-110 | Story | Ballot Ledger | Record each cast ballot immutably | As a system, I want to record each cast ballot immutably using blockchain and cryptographic hashing so that cast ballots are processed consistently. | 1. The system records each cast ballot immutably using blockchain and cryptographic hashing. 2. Configuration values are read from settings rather than hard-coded. 3. Edge cases found during testing are handled. 4. The election officer can inspect the outcome. | High | 8 | <Student 2> | Sprint 2 | To Do | blockchain,voting,security
US-111 | Story | Ballot Ledger | Provide an administration portal to configure elections | As a system, I want to provide an administration portal to configure elections, candidates and polling windows so that the behaviour is correct for both typical and edge inputs. | 1. The system provides an administration portal to configure elections, candidates and polling windows. 2. Processing completes within the agreed time budget. 3. The module has unit tests covering its main paths. 4. The step is documented in the project README. | High | 8 | <Student 3> | Sprint 3 | To Do | blockchain,voting,security
US-112 | Story | Ballot Ledger | Generate results automatically when the poll closes | As a system, I want to generate results automatically when the poll closes, with a complete chronological audit trail so that later features can build on a dependable output. | 1. The system generates results automatically when the poll closes, with a complete chronological audit trail. 2. Invalid or missing cast ballots are rejected with a clear message. 3. Behaviour is verified on a representative sample of cast ballots. 4. Errors are logged with enough context to debug them. | High | 8 | <Student 4> | Sprint 3 | To Do | blockchain,voting,security
US-113 | Story | Ballot Ledger | Apply role-based access control, input validation and TLS | As a system, I want to apply role-based access control, input validation and TLS, and evaluate integrity and performance so that the requirement can be demonstrated at review. | 1. The system applies role-based access control, input validation and TLS, and evaluate integrity and performance. 2. The step runs end to end on the full project dataset. 3. Results are persisted and can be retrieved later. 4. The run is reproducible from a fixed configuration. | High | 8 | <Student 1> | Sprint 3 | To Do | blockchain,voting,security
US-114 | Story | Ballot Ledger | Review ballot ledger output | As a voter, I want to review the ballot ledger output in the interface so that I can confirm it before acting on it. | 1. The most recent output is shown together with its inputs. 2. The voter can flag an incorrect result. 3. Flagged items are queued for the election officer to check. | Medium | 5 | <Student 2> | Sprint 2 | To Do | blockchain,backend
US-115 | Task | Ballot Ledger | Retry and logging for ballot ledger | As a system, I want to retry and log failures in ballot ledger so that a transient error does not lose data. | 1. Failed operations retry with backoff. 2. Repeated failures raise an alert. 3. Every failure is logged with its input reference. | Medium | 5 | <Student 3> | Sprint 3 | To Do | blockchain,backend
US-116 | Story | Ballot Ledger | Tune ballot ledger | As a developer, I want to tune ballot ledger on validation data so that accuracy improves before release. | 1. A parameter search is run and recorded. 2. Before and after metrics are compared. 3. The chosen settings are committed to the repository. | Medium | 5 | <Student 4> | Sprint 3 | To Do | blockchain,backend
US-117 | Task | Ballot Ledger | Expose ballot ledger through an API | As a developer, I want to expose ballot ledger through an internal API so that the interface and other modules can consume it. | 1. Endpoint documented with request and response examples. 2. Errors return meaningful status codes. 3. The endpoint is covered by an integration test. | Medium | 5 | <Student 1> | Sprint 3 | To Do | blockchain,backend
US-118 | Story | Results and Reporting | Results dashboard | As a voter, I want a dashboard summarising the latest results so that I can understand the outcome at a glance. | 1. Key figures are shown with the date of the run. 2. Charts render correctly for an empty and a full dataset. 3. The dashboard loads within an acceptable time. | High | 5 | <Student 2> | Sprint 4 | To Do | dashboard,frontend
US-119 | Story | Results and Reporting | Export report | As a election officer, I want to export the results as PDF or CSV so that I can share them outside the system. | 1. The export includes the figures shown on screen. 2. The file name carries the project and the date. 3. Large exports complete without timing out. | Medium | 3 | <Student 3> | Sprint 4 | To Do | export,reporting
US-120 | Story | Results and Reporting | History and search | As a voter, I want to search past records so that I can compare an earlier result with the current one. | 1. Records can be filtered by date and by status. 2. Search returns promptly on the full dataset. 3. An empty result set is shown clearly. | Medium | 3 | <Student 4> | Sprint 4 | To Do | search,frontend
US-121 | Story | Notifications | Notify voter of an important outcome | As a voter, I want to be notified when the system produces an outcome needing my attention so that I can respond promptly. | 1. A notification is raised when the configured condition is met. 2. The voter can see the notification history. 3. Repeated notifications for the same event are suppressed. | Medium | 3 | <Student 1> | Sprint 4 | To Do | notification,alerts
US-122 | Spike | Evaluation | Define and measure evaluation metrics | Decide which metrics judge this project and measure the current build against them. | 1. Metrics chosen and justified for this problem. 2. Current scores recorded as a baseline. 3. A target for the final review is agreed. | Low | 3 | <Student 2> | Sprint 5 | To Do | evaluation,research
US-123 | Task | Release | Deployment and user documentation | As a developer, I want the system deployed with setup and usage documentation so that the evaluators can run and demonstrate it. | 1. The application runs on the target environment. 2. Setup steps are documented and verified from scratch. 3. A short user guide covers the main workflow. | Low | 2 | <Student 3> | Sprint 5 | To Do | deployment,docs

## Field Guide
BharatBuild — User Stories Excel Import Guide
Fields marked with * are mandatory. Assignee Roll No and Assignee Name must match a registered student in the selected batch.
Field | Mandatory | Example | Validation / Usage
Story ID | No | US-101 | Optional unique reference. BharatBuild may generate one if blank.
Work Type | Yes | Story | Allowed: Story, Task, Spike.
Epic | No | Authentication | Existing or importable epic/feature grouping.
Summary | Yes | Student Login and Authentication | Short title of the user story.
Description | Yes | As a student, I want to... | Detailed functional/user-story description.
Acceptance Criteria | Yes | 1. Valid login... | Use numbered lines in one cell.
Priority | Yes | High | Highest, High, Medium, Low, Lowest.
Story Points | Yes | 5 | Numeric estimate; recommended Fibonacci values such as 1,2,3,5,8,13.
Assignee Roll No | Yes | 23K91A05L5 | Must belong to the currently selected project batch.
Assignee Name | Yes | Royyala Sindhuja | Must match the student identified by Assignee Roll No.
Sprint | No | Sprint 1 | If blank, story remains unscheduled/backlog.
Status | Yes | To Do | Allowed: To Do, In Progress, In Review, Done.
Labels | No | authentication,frontend | Comma-separated tags.

## Import Process
Trainer Import Workflow
Step | Action | Expected Result
1 | Select Department → Section → Batch → Project | BharatBuild establishes project context.
2 | Open User Stories → Import Stories | Import wizard opens.
3 | Upload this Excel file | Columns are detected automatically.
4 | Map Excel columns | Excel fields are mapped to BharatBuild story fields.
5 | Validate | Missing mandatory data, duplicate IDs and invalid assignees are flagged.
6 | Preview | Trainer reviews stories and student assignments.
7 | Confirm Import | Valid stories are created under the selected project.