## User Stories Import
Story ID | Work Type * | Epic | Summary * | Description * | Acceptance Criteria * | Priority * | Story Points * | Assignee Name * | Sprint | Status * | Labels
US-101 | Story | Platform Access | File owner registration and login | As a file owner, I want to register and sign in with my own credentials so that I can reach my workspace securely. | 1. Valid credentials sign the file owner in. 2. Invalid credentials show a clear error. 3. A session is created and expires after inactivity. 4. Passwords are stored only as salted hashes. | High | 5 | Pendela Vyshnavi | Sprint 1 | To Do | crypto,auth,frontend
US-102 | Story | Platform Access | Password reset | As a file owner, I want to reset a forgotten password so that I can regain access without an administrator. | 1. A reset link or OTP is sent to the registered contact. 2. The link expires after a set time. 3. A new password can be saved and used to sign in. 4. Reset attempts are recorded in the audit log. | Medium | 3 | Luke Abraham Sam | Sprint 1 | To Do | auth,security
US-103 | Story | Platform Access | Role-based access for system administrator | As a system administrator, I want a separate privileged view so that I can manage records without using a file owner account. | 1. File owner and system administrator roles see different menus. 2. Privileged actions are refused for a normal file owner. 3. Every privileged action is written to an audit trail. | High | 5 | Mudavath Suresh | Sprint 1 | To Do | auth,rbac
US-104 | Story | Files Intake | Submit stored files | As a file owner, I want to submit stored files to the system so that they can be processed. | 1. Supported formats are accepted and stored. 2. Unsupported or oversized input is refused with a reason. 3. Each submission is timestamped and linked to its owner. 4. A confirmation is shown once the upload completes. | Highest | 5 | Ponugoti Viduranandan | Sprint 1 | To Do | crypto,ingestion
US-105 | Story | Files Intake | Validate and clean stored files | As a system, I want to validate and clean incoming stored files so that poor quality input does not corrupt later stages. | 1. Missing and malformed fields are detected. 2. Duplicates are removed before processing. 3. A validation summary is available for each batch. 4. Rejected records are retained for review. | High | 5 | Pendela Vyshnavi | Sprint 1 | To Do | validation,data
US-106 | Task | Files Intake | Project repository and environment setup | As a developer, I want a version-controlled repository with a reproducible environment so that the whole team builds on the same base. | 1. Repository created and branch rules agreed. 2. Dependencies pinned in a requirements file. 3. The project runs from a clean checkout by following the README. | Medium | 3 | Luke Abraham Sam | Sprint 1 | To Do | setup,devops
US-107 | Spike | Encryption and Access Control | Evaluate approaches for encryption and access control | Research candidate approaches for encryption and access control and record which one this project adopts. The surveyed work applies attribute-based encryption and access control to health records. The gap is a general-purpose secure file store combining AES-256-GCM, RBAC, integrity. | 1. At least three approaches are compared. 2. Strengths and limits of each are written up. 3. A recommendation with reasons is recorded. | Low | 3 | Mudavath Suresh | Sprint 2 | To Do | research,spike
US-108 | Story | Encryption and Access Control | Implement user registration and authentication | As a developer, I want to implement user registration and authentication with securely hashed credentials and JWT sessions so that the rest of the encryption and access control pipeline can depend on it. | 1. The delivered system provides user registration and authentication with securely hashed credentials and JWT sessions. 2. Invalid or missing stored files are rejected with a clear message. 3. Behaviour is verified on a representative sample of stored files. 4. Errors are logged with enough context to debug them. | Highest | 8 | Ponugoti Viduranandan | Sprint 2 | To Do | crypto,rbac,security
US-109 | Story | Encryption and Access Control | Encrypt every uploaded file | As a system, I want to encrypt every uploaded file using AES-256-GCM before it reaches storage so that the capability is available to the modules that follow. | 1. The system encrypts every uploaded file using AES-256-GCM before it reaches storage. 2. The step runs end to end on the full project dataset. 3. Results are persisted and can be retrieved later. 4. The run is reproducible from a fixed configuration. | High | 8 | Pendela Vyshnavi | Sprint 2 | To Do | crypto,rbac,security
US-110 | Story | Encryption and Access Control | Implement role-based access control together | As a developer, I want to implement role-based access control together with file-ownership verification so that stored files are processed consistently. | 1. The delivered system provides role-based access control together with file-ownership verification. 2. Configuration values are read from settings rather than hard-coded. 3. Edge cases found during testing are handled. 4. The system administrator can inspect the outcome. | High | 8 | Luke Abraham Sam | Sprint 2 | To Do | crypto,rbac,security
US-111 | Story | Encryption and Access Control | Verify file integrity on download | As a system, I want to verify file integrity on download using cryptographic hashing so that the behaviour is correct for both typical and edge inputs. | 1. The system verifies file integrity on download using cryptographic hashing. 2. Processing completes within the agreed time budget. 3. The module has unit tests covering its main paths. 4. The step is documented in the project README. | High | 8 | Mudavath Suresh | Sprint 3 | To Do | crypto,rbac,security
US-112 | Story | Encryption and Access Control | Maintain structured audit logs of every upload, download | As a system, I want to maintain structured audit logs of every upload, download, delete and access denial so that later features can build on a dependable output. | 1. The system maintains structured audit logs of every upload, download, delete and access denial. 2. Invalid or missing stored files are rejected with a clear message. 3. Behaviour is verified on a representative sample of stored files. 4. Errors are logged with enough context to debug them. | High | 8 | Ponugoti Viduranandan | Sprint 3 | To Do | crypto,rbac,security
US-113 | Story | Encryption and Access Control | Evaluate encryption overhead | As a developer, I want to evaluate encryption overhead, access-control correctness and integrity verification so that the requirement can be demonstrated at review. | 1. The team has evaluated encryption overhead, access-control correctness and integrity verification. 2. The step runs end to end on the full project dataset. 3. Results are persisted and can be retrieved later. 4. The run is reproducible from a fixed configuration. | High | 8 | Pendela Vyshnavi | Sprint 3 | To Do | crypto,rbac,security
US-114 | Story | Encryption and Access Control | Review encryption and access control output | As a file owner, I want to review the encryption and access control output in the interface so that I can confirm it before acting on it. | 1. The most recent output is shown together with its inputs. 2. The file owner can flag an incorrect result. 3. Flagged items are queued for the system administrator to check. | Medium | 5 | Luke Abraham Sam | Sprint 2 | To Do | crypto,backend
US-115 | Task | Encryption and Access Control | Retry and logging for encryption and access control | As a system, I want to retry and log failures in encryption and access control so that a transient error does not lose data. | 1. Failed operations retry with backoff. 2. Repeated failures raise an alert. 3. Every failure is logged with its input reference. | Medium | 5 | Mudavath Suresh | Sprint 3 | To Do | crypto,backend
US-116 | Story | Encryption and Access Control | Tune encryption and access control | As a developer, I want to tune encryption and access control on validation data so that accuracy improves before release. | 1. A parameter search is run and recorded. 2. Before and after metrics are compared. 3. The chosen settings are committed to the repository. | Medium | 5 | Ponugoti Viduranandan | Sprint 3 | To Do | crypto,backend
US-117 | Task | Encryption and Access Control | Expose encryption and access control through an API | As a developer, I want to expose encryption and access control through an internal API so that the interface and other modules can consume it. | 1. Endpoint documented with request and response examples. 2. Errors return meaningful status codes. 3. The endpoint is covered by an integration test. | Medium | 5 | Pendela Vyshnavi | Sprint 3 | To Do | crypto,backend
US-118 | Story | Results and Reporting | Results dashboard | As a file owner, I want a dashboard summarising the latest results so that I can understand the outcome at a glance. | 1. Key figures are shown with the date of the run. 2. Charts render correctly for an empty and a full dataset. 3. The dashboard loads within an acceptable time. | High | 5 | Luke Abraham Sam | Sprint 4 | To Do | dashboard,frontend
US-119 | Story | Results and Reporting | Export report | As a system administrator, I want to export the results as PDF or CSV so that I can share them outside the system. | 1. The export includes the figures shown on screen. 2. The file name carries the project and the date. 3. Large exports complete without timing out. | Medium | 3 | Mudavath Suresh | Sprint 4 | To Do | export,reporting
US-120 | Story | Results and Reporting | History and search | As a file owner, I want to search past records so that I can compare an earlier result with the current one. | 1. Records can be filtered by date and by status. 2. Search returns promptly on the full dataset. 3. An empty result set is shown clearly. | Medium | 3 | Ponugoti Viduranandan | Sprint 4 | To Do | search,frontend
US-121 | Story | Notifications | Notify file owner of an important outcome | As a file owner, I want to be notified when the system produces an outcome needing my attention so that I can respond promptly. | 1. A notification is raised when the configured condition is met. 2. The file owner can see the notification history. 3. Repeated notifications for the same event are suppressed. | Medium | 3 | Pendela Vyshnavi | Sprint 4 | To Do | notification,alerts
US-122 | Spike | Evaluation | Define and measure evaluation metrics | Decide which metrics judge this project and measure the current build against them. | 1. Metrics chosen and justified for this problem. 2. Current scores recorded as a baseline. 3. A target for the final review is agreed. | Low | 3 | Luke Abraham Sam | Sprint 5 | To Do | evaluation,research
US-123 | Task | Release | Deployment and user documentation | As a developer, I want the system deployed with setup and usage documentation so that the evaluators can run and demonstrate it. | 1. The application runs on the target environment. 2. Setup steps are documented and verified from scratch. 3. A short user guide covers the main workflow. | Low | 2 | Mudavath Suresh | Sprint 5 | To Do | deployment,docs

## Field Guide
BharatBuild — User Stories Excel Import Guide
Fields marked with * are mandatory. Assignee Roll No and Assignee Name must match a registered student in the selected batch.
Field | Mandatory | Example | Validation / Usage
Story ID | No | US-101 | Optional unique reference. BharatBuild may generate one if blank.
Work Type | Yes | Story | Allowed: Story, Task, Spike.
Epic | No | Authentication | Existing or importable epic/feature grouping.
Summary | Yes | Student Login and Authentication | Short title of the user story.
Description | Yes | As a student, I want to... | Detailed functional/user-story description.
Acceptance Criteria | Yes | 1. Valid login... | Use numbered lines in one cell.
Priority | Yes | High | Highest, High, Medium, Low, Lowest.
Story Points | Yes | 5 | Numeric estimate; recommended Fibonacci values such as 1,2,3,5,8,13.
Assignee Roll No | Yes | 23K91A05L5 | Must belong to the currently selected project batch.
Assignee Name | Yes | Royyala Sindhuja | Must match the student identified by Assignee Roll No.
Sprint | No | Sprint 1 | If blank, story remains unscheduled/backlog.
Status | Yes | To Do | Allowed: To Do, In Progress, In Review, Done.
Labels | No | authentication,frontend | Comma-separated tags.

## Import Process
Trainer Import Workflow
Step | Action | Expected Result
1 | Select Department → Section → Batch → Project | BharatBuild establishes project context.
2 | Open User Stories → Import Stories | Import wizard opens.
3 | Upload this Excel file | Columns are detected automatically.
4 | Map Excel columns | Excel fields are mapped to BharatBuild story fields.
5 | Validate | Missing mandatory data, duplicate IDs and invalid assignees are flagged.
6 | Preview | Trainer reviews stories and student assignments.
7 | Confirm Import | Valid stories are created under the selected project.