## User Stories Import
Story ID | Work Type * | Epic | Summary * | Description * | Acceptance Criteria * | Priority * | Story Points * | Assignee Name * | Sprint | Status * | Labels
US-101 | Story | Platform Access | Content moderator registration and login | As a content moderator, I want to register and sign in with my own credentials so that I can reach my workspace securely. | 1. Valid credentials sign the content moderator in. 2. Invalid credentials show a clear error. 3. A session is created and expires after inactivity. 4. Passwords are stored only as salted hashes. | High | 5 | <Student 1> | Sprint 1 | To Do | cnn,auth,frontend
US-102 | Story | Platform Access | Password reset | As a content moderator, I want to reset a forgotten password so that I can regain access without an administrator. | 1. A reset link or OTP is sent to the registered contact. 2. The link expires after a set time. 3. A new password can be saved and used to sign in. 4. Reset attempts are recorded in the audit log. | Medium | 3 | <Student 2> | Sprint 1 | To Do | auth,security
US-103 | Story | Platform Access | Role-based access for forensic analyst | As a forensic analyst, I want a separate privileged view so that I can manage records without using a content moderator account. | 1. Content moderator and forensic analyst roles see different menus. 2. Privileged actions are refused for a normal content moderator. 3. Every privileged action is written to an audit trail. | High | 5 | <Student 3> | Sprint 1 | To Do | auth,rbac
US-104 | Story | Images Intake | Submit uploaded images | As a content moderator, I want to submit uploaded images to the system so that they can be processed. | 1. Supported formats are accepted and stored. 2. Unsupported or oversized input is refused with a reason. 3. Each submission is timestamped and linked to its owner. 4. A confirmation is shown once the upload completes. | Highest | 5 | <Student 4> | Sprint 1 | To Do | cnn,ingestion
US-105 | Story | Images Intake | Validate and clean uploaded images | As a system, I want to validate and clean incoming uploaded images so that poor quality input does not corrupt later stages. | 1. Missing and malformed fields are detected. 2. Duplicates are removed before processing. 3. A validation summary is available for each batch. 4. Rejected records are retained for review. | High | 5 | <Student 1> | Sprint 1 | To Do | validation,data
US-106 | Task | Images Intake | Project repository and environment setup | As a developer, I want a version-controlled repository with a reproducible environment so that the whole team builds on the same base. | 1. Repository created and branch rules agreed. 2. Dependencies pinned in a requirements file. 3. The project runs from a clean checkout by following the README. | Medium | 3 | <Student 2> | Sprint 1 | To Do | setup,devops
US-107 | Spike | Image Authenticity | Evaluate approaches for image authenticity | Research candidate approaches for image authenticity and record which one this project adopts. The surveyed work learns representations that separate authentic from generated images. The gap is pairing that detection with Grad-CAM explanation and testing generalisation across. | 1. At least three approaches are compared. 2. Strengths and limits of each are written up. 3. A recommendation with reasons is recorded. | Low | 3 | <Student 3> | Sprint 2 | To Do | research,spike
US-108 | Story | Image Authenticity | Assemble a dataset of real photographs | As a developer, I want to assemble a dataset of real photographs and images produced by several generative models so that the rest of the image authenticity pipeline can depend on it. | 1. The team has assembled a dataset of real photographs and images produced by several generative models. 2. Invalid or missing uploaded images are rejected with a clear message. 3. Behaviour is verified on a representative sample of uploaded images. 4. Errors are logged with enough context to debug them. | Highest | 8 | <Student 4> | Sprint 2 | To Do | cnn,xai,forensics
US-109 | Story | Image Authenticity | Preprocess and augment the images | As a developer, I want to preprocess and augment the images to improve robustness across sources so that the capability is available to the modules that follow. | 1. The team has preprocessed and augment the images to improve robustness across sources. 2. The step runs end to end on the full project dataset. 3. Results are persisted and can be retrieved later. 4. The run is reproducible from a fixed configuration. | High | 8 | <Student 1> | Sprint 2 | To Do | cnn,xai,forensics
US-110 | Story | Image Authenticity | Train a CNN classifier to separate authentic images | As a developer, I want to train a CNN classifier to separate authentic images from generated ones so that uploaded images are processed consistently. | 1. The team has trained a CNN classifier to separate authentic images from generated ones. 2. Configuration values are read from settings rather than hard-coded. 3. Edge cases found during testing are handled. 4. The forensic analyst can inspect the outcome. | High | 8 | <Student 2> | Sprint 2 | To Do | cnn,xai,forensics
US-111 | Story | Image Authenticity | Evaluate cross-generator performance | As a developer, I want to evaluate cross-generator performance to test generalisation beyond the training set so that the behaviour is correct for both typical and edge inputs. | 1. The team has evaluated cross-generator performance to test generalisation beyond the training set. 2. Processing completes within the agreed time budget. 3. The module has unit tests covering its main paths. 4. The step is documented in the project README. | High | 8 | <Student 3> | Sprint 3 | To Do | cnn,xai,forensics
US-112 | Story | Image Authenticity | Apply Grad-CAM to highlight the regions driving each | As a system, I want to apply Grad-CAM to highlight the regions driving each classification so that later features can build on a dependable output. | 1. The system applies Grad-CAM to highlight the regions driving each classification. 2. Invalid or missing uploaded images are rejected with a clear message. 3. Behaviour is verified on a representative sample of uploaded images. 4. Errors are logged with enough context to debug them. | High | 8 | <Student 4> | Sprint 3 | To Do | cnn,xai,forensics
US-113 | Story | Image Authenticity | Deploy the model behind an interface returning the verdict | As a developer, I want to deploy the model behind an interface returning the verdict, confidence and visual explanation so that the requirement can be demonstrated at review. | 1. The delivered system provides the model behind an interface returning the verdict, confidence and visual explanation. 2. The step runs end to end on the full project dataset. 3. Results are persisted and can be retrieved later. 4. The run is reproducible from a fixed configuration. | High | 8 | <Student 1> | Sprint 3 | To Do | cnn,xai,forensics
US-114 | Story | Image Authenticity | Review image authenticity output | As a content moderator, I want to review the image authenticity output in the interface so that I can confirm it before acting on it. | 1. The most recent output is shown together with its inputs. 2. The content moderator can flag an incorrect result. 3. Flagged items are queued for the forensic analyst to check. | Medium | 5 | <Student 2> | Sprint 2 | To Do | cnn,backend
US-115 | Task | Image Authenticity | Retry and logging for image authenticity | As a system, I want to retry and log failures in image authenticity so that a transient error does not lose data. | 1. Failed operations retry with backoff. 2. Repeated failures raise an alert. 3. Every failure is logged with its input reference. | Medium | 5 | <Student 3> | Sprint 3 | To Do | cnn,backend
US-116 | Story | Image Authenticity | Tune image authenticity | As a developer, I want to tune image authenticity on validation data so that accuracy improves before release. | 1. A parameter search is run and recorded. 2. Before and after metrics are compared. 3. The chosen settings are committed to the repository. | Medium | 5 | <Student 4> | Sprint 3 | To Do | cnn,backend
US-117 | Task | Image Authenticity | Expose image authenticity through an API | As a developer, I want to expose image authenticity through an internal API so that the interface and other modules can consume it. | 1. Endpoint documented with request and response examples. 2. Errors return meaningful status codes. 3. The endpoint is covered by an integration test. | Medium | 5 | <Student 1> | Sprint 3 | To Do | cnn,backend
US-118 | Story | Results and Reporting | Results dashboard | As a content moderator, I want a dashboard summarising the latest results so that I can understand the outcome at a glance. | 1. Key figures are shown with the date of the run. 2. Charts render correctly for an empty and a full dataset. 3. The dashboard loads within an acceptable time. | High | 5 | <Student 2> | Sprint 4 | To Do | dashboard,frontend
US-119 | Story | Results and Reporting | Export report | As a forensic analyst, I want to export the results as PDF or CSV so that I can share them outside the system. | 1. The export includes the figures shown on screen. 2. The file name carries the project and the date. 3. Large exports complete without timing out. | Medium | 3 | <Student 3> | Sprint 4 | To Do | export,reporting
US-120 | Story | Results and Reporting | History and search | As a content moderator, I want to search past records so that I can compare an earlier result with the current one. | 1. Records can be filtered by date and by status. 2. Search returns promptly on the full dataset. 3. An empty result set is shown clearly. | Medium | 3 | <Student 4> | Sprint 4 | To Do | search,frontend
US-121 | Story | Notifications | Notify content moderator of an important outcome | As a content moderator, I want to be notified when the system produces an outcome needing my attention so that I can respond promptly. | 1. A notification is raised when the configured condition is met. 2. The content moderator can see the notification history. 3. Repeated notifications for the same event are suppressed. | Medium | 3 | <Student 1> | Sprint 4 | To Do | notification,alerts
US-122 | Spike | Evaluation | Define and measure evaluation metrics | Decide which metrics judge this project and measure the current build against them. | 1. Metrics chosen and justified for this problem. 2. Current scores recorded as a baseline. 3. A target for the final review is agreed. | Low | 3 | <Student 2> | Sprint 5 | To Do | evaluation,research
US-123 | Task | Release | Deployment and user documentation | As a developer, I want the system deployed with setup and usage documentation so that the evaluators can run and demonstrate it. | 1. The application runs on the target environment. 2. Setup steps are documented and verified from scratch. 3. A short user guide covers the main workflow. | Low | 2 | <Student 3> | Sprint 5 | To Do | deployment,docs

## Field Guide
BharatBuild — User Stories Excel Import Guide
Fields marked with * are mandatory. Assignee Roll No and Assignee Name must match a registered student in the selected batch.
Field | Mandatory | Example | Validation / Usage
Story ID | No | US-101 | Optional unique reference. BharatBuild may generate one if blank.
Work Type | Yes | Story | Allowed: Story, Task, Spike.
Epic | No | Authentication | Existing or importable epic/feature grouping.
Summary | Yes | Student Login and Authentication | Short title of the user story.
Description | Yes | As a student, I want to... | Detailed functional/user-story description.
Acceptance Criteria | Yes | 1. Valid login... | Use numbered lines in one cell.
Priority | Yes | High | Highest, High, Medium, Low, Lowest.
Story Points | Yes | 5 | Numeric estimate; recommended Fibonacci values such as 1,2,3,5,8,13.
Assignee Roll No | Yes | 23K91A05L5 | Must belong to the currently selected project batch.
Assignee Name | Yes | Royyala Sindhuja | Must match the student identified by Assignee Roll No.
Sprint | No | Sprint 1 | If blank, story remains unscheduled/backlog.
Status | Yes | To Do | Allowed: To Do, In Progress, In Review, Done.
Labels | No | authentication,frontend | Comma-separated tags.

## Import Process
Trainer Import Workflow
Step | Action | Expected Result
1 | Select Department → Section → Batch → Project | BharatBuild establishes project context.
2 | Open User Stories → Import Stories | Import wizard opens.
3 | Upload this Excel file | Columns are detected automatically.
4 | Map Excel columns | Excel fields are mapped to BharatBuild story fields.
5 | Validate | Missing mandatory data, duplicate IDs and invalid assignees are flagged.
6 | Preview | Trainer reviews stories and student assignments.
7 | Confirm Import | Valid stories are created under the selected project.