## User Stories Import
Story ID | Work Type * | Epic | Summary * | Description * | Acceptance Criteria * | Priority * | Story Points * | Assignee Name * | Sprint | Status * | Labels
US-101 | Story | Platform Access | Network administrator registration and login | As a network administrator, I want to register and sign in with my own credentials so that I can reach my workspace securely. | 1. Valid credentials sign the network administrator in. 2. Invalid credentials show a clear error. 3. A session is created and expires after inactivity. 4. Passwords are stored only as salted hashes. | High | 5 | K. DurgaBhavani | Sprint 1 | To Do | ddos,auth,frontend
US-102 | Story | Platform Access | Password reset | As a network administrator, I want to reset a forgotten password so that I can regain access without an administrator. | 1. A reset link or OTP is sent to the registered contact. 2. The link expires after a set time. 3. A new password can be saved and used to sign in. 4. Reset attempts are recorded in the audit log. | Medium | 3 | N. Rakshitha | Sprint 1 | To Do | auth,security
US-103 | Story | Platform Access | Role-based access for security operations analyst | As a security operations analyst, I want a separate privileged view so that I can manage records without using a network administrator account. | 1. Network administrator and security operations analyst roles see different menus. 2. Privileged actions are refused for a normal network administrator. 3. Every privileged action is written to an audit trail. | High | 5 | P. Shashi Preetham | Sprint 1 | To Do | auth,rbac
US-104 | Story | Flows Intake | Submit network traffic flows | As a network administrator, I want to submit network traffic flows to the system so that they can be processed. | 1. Supported formats are accepted and stored. 2. Unsupported or oversized input is refused with a reason. 3. Each submission is timestamped and linked to its owner. 4. A confirmation is shown once the upload completes. | Highest | 5 | P. Vishal | Sprint 1 | To Do | ddos,ingestion
US-105 | Story | Flows Intake | Validate and clean network traffic flows | As a system, I want to validate and clean incoming network traffic flows so that poor quality input does not corrupt later stages. | 1. Missing and malformed fields are detected. 2. Duplicates are removed before processing. 3. A validation summary is available for each batch. 4. Rejected records are retained for review. | High | 5 | K. DurgaBhavani | Sprint 1 | To Do | validation,data
US-106 | Task | Flows Intake | Project repository and environment setup | As a developer, I want a version-controlled repository with a reproducible environment so that the whole team builds on the same base. | 1. Repository created and branch rules agreed. 2. Dependencies pinned in a requirements file. 3. The project runs from a clean checkout by following the README. | Medium | 3 | N. Rakshitha | Sprint 1 | To Do | setup,devops
US-107 | Spike | Detection and Mitigation | Evaluate approaches for detection and mitigation | Research candidate approaches for detection and mitigation and record which one this project adopts. The surveyed work applies ensemble detection within software-defined networks. The gap is closing the loop from real-time detection to automatic adaptive mitigation with measured. | 1. At least three approaches are compared. 2. Strengths and limits of each are written up. 3. A recommendation with reasons is recorded. | Low | 3 | P. Shashi Preetham | Sprint 2 | To Do | research,spike
US-108 | Story | Detection and Mitigation | Acquire a benchmark intrusion dataset | As a system, I want to acquire a benchmark intrusion dataset and extract network flow features so that the rest of the detection and mitigation pipeline can depend on it. | 1. The team has acquired a benchmark intrusion dataset and extract network flow features. 2. Invalid or missing network traffic flows are rejected with a clear message. 3. Behaviour is verified on a representative sample of network traffic flows. 4. Errors are logged with enough context to debug them. | Highest | 8 | P. Vishal | Sprint 2 | To Do | ddos,network,security
US-109 | Story | Detection and Mitigation | Capture live traffic and compute the same features | As a system, I want to capture live traffic and compute the same features in real time so that the capability is available to the modules that follow. | 1. The system captures live traffic and compute the same features in real time. 2. The step runs end to end on the full project dataset. 3. Results are persisted and can be retrieved later. 4. The run is reproducible from a fixed configuration. | High | 8 | K. DurgaBhavani | Sprint 2 | To Do | ddos,network,security
US-110 | Story | Detection and Mitigation | Train a classifier to distinguish DDoS traffic | As a developer, I want to train a classifier to distinguish DDoS traffic from legitimate traffic so that network traffic flows are processed consistently. | 1. The team has trained a classifier to distinguish DDoS traffic from legitimate traffic. 2. Configuration values are read from settings rather than hard-coded. 3. Edge cases found during testing are handled. 4. The security operations analyst can inspect the outcome. | High | 8 | N. Rakshitha | Sprint 2 | To Do | ddos,network,security
US-111 | Story | Detection and Mitigation | Implement adaptive mitigation | As a developer, I want to implement adaptive mitigation that rate-limits or blocks identified attack sources so that the behaviour is correct for both typical and edge inputs. | 1. The delivered system provides adaptive mitigation that rate-limits or blocks identified attack sources. 2. Processing completes within the agreed time budget. 3. The module has unit tests covering its main paths. 4. The step is documented in the project README. | High | 8 | P. Shashi Preetham | Sprint 3 | To Do | ddos,network,security
US-112 | Story | Detection and Mitigation | Build a dashboard showing live traffic | As a developer, I want to build a dashboard showing live traffic, detection events and mitigation actions so that later features can build on a dependable output. | 1. The delivered system provides a dashboard showing live traffic, detection events and mitigation actions. 2. Invalid or missing network traffic flows are rejected with a clear message. 3. Behaviour is verified on a representative sample of network traffic flows. 4. Errors are logged with enough context to debug them. | High | 8 | P. Vishal | Sprint 3 | To Do | ddos,network,security
US-113 | Story | Detection and Mitigation | Evaluate detection accuracy | As a developer, I want to evaluate detection accuracy, false positive rate and time from detection to mitigation so that the requirement can be demonstrated at review. | 1. The team has evaluated detection accuracy, false positive rate and time from detection to mitigation. 2. The step runs end to end on the full project dataset. 3. Results are persisted and can be retrieved later. 4. The run is reproducible from a fixed configuration. | High | 8 | K. DurgaBhavani | Sprint 3 | To Do | ddos,network,security
US-114 | Story | Detection and Mitigation | Review detection and mitigation output | As a network administrator, I want to review the detection and mitigation output in the interface so that I can confirm it before acting on it. | 1. The most recent output is shown together with its inputs. 2. The network administrator can flag an incorrect result. 3. Flagged items are queued for the security operations analyst to check. | Medium | 5 | N. Rakshitha | Sprint 2 | To Do | ddos,backend
US-115 | Task | Detection and Mitigation | Retry and logging for detection and mitigation | As a system, I want to retry and log failures in detection and mitigation so that a transient error does not lose data. | 1. Failed operations retry with backoff. 2. Repeated failures raise an alert. 3. Every failure is logged with its input reference. | Medium | 5 | P. Shashi Preetham | Sprint 3 | To Do | ddos,backend
US-116 | Story | Detection and Mitigation | Tune detection and mitigation | As a developer, I want to tune detection and mitigation on validation data so that accuracy improves before release. | 1. A parameter search is run and recorded. 2. Before and after metrics are compared. 3. The chosen settings are committed to the repository. | Medium | 5 | P. Vishal | Sprint 3 | To Do | ddos,backend
US-117 | Task | Detection and Mitigation | Expose detection and mitigation through an API | As a developer, I want to expose detection and mitigation through an internal API so that the interface and other modules can consume it. | 1. Endpoint documented with request and response examples. 2. Errors return meaningful status codes. 3. The endpoint is covered by an integration test. | Medium | 5 | K. DurgaBhavani | Sprint 3 | To Do | ddos,backend
US-118 | Story | Results and Reporting | Results dashboard | As a network administrator, I want a dashboard summarising the latest results so that I can understand the outcome at a glance. | 1. Key figures are shown with the date of the run. 2. Charts render correctly for an empty and a full dataset. 3. The dashboard loads within an acceptable time. | High | 5 | N. Rakshitha | Sprint 4 | To Do | dashboard,frontend
US-119 | Story | Results and Reporting | Export report | As a security operations analyst, I want to export the results as PDF or CSV so that I can share them outside the system. | 1. The export includes the figures shown on screen. 2. The file name carries the project and the date. 3. Large exports complete without timing out. | Medium | 3 | P. Shashi Preetham | Sprint 4 | To Do | export,reporting
US-120 | Story | Results and Reporting | History and search | As a network administrator, I want to search past records so that I can compare an earlier result with the current one. | 1. Records can be filtered by date and by status. 2. Search returns promptly on the full dataset. 3. An empty result set is shown clearly. | Medium | 3 | P. Vishal | Sprint 4 | To Do | search,frontend
US-121 | Story | Notifications | Notify network administrator of an important outcome | As a network administrator, I want to be notified when the system produces an outcome needing my attention so that I can respond promptly. | 1. A notification is raised when the configured condition is met. 2. The network administrator can see the notification history. 3. Repeated notifications for the same event are suppressed. | Medium | 3 | K. DurgaBhavani | Sprint 4 | To Do | notification,alerts
US-122 | Spike | Evaluation | Define and measure evaluation metrics | Decide which metrics judge this project and measure the current build against them. | 1. Metrics chosen and justified for this problem. 2. Current scores recorded as a baseline. 3. A target for the final review is agreed. | Low | 3 | N. Rakshitha | Sprint 5 | To Do | evaluation,research
US-123 | Task | Release | Deployment and user documentation | As a developer, I want the system deployed with setup and usage documentation so that the evaluators can run and demonstrate it. | 1. The application runs on the target environment. 2. Setup steps are documented and verified from scratch. 3. A short user guide covers the main workflow. | Low | 2 | P. Shashi Preetham | Sprint 5 | To Do | deployment,docs

## Field Guide
BharatBuild — User Stories Excel Import Guide
Fields marked with * are mandatory. Assignee Roll No and Assignee Name must match a registered student in the selected batch.
Field | Mandatory | Example | Validation / Usage
Story ID | No | US-101 | Optional unique reference. BharatBuild may generate one if blank.
Work Type | Yes | Story | Allowed: Story, Task, Spike.
Epic | No | Authentication | Existing or importable epic/feature grouping.
Summary | Yes | Student Login and Authentication | Short title of the user story.
Description | Yes | As a student, I want to... | Detailed functional/user-story description.
Acceptance Criteria | Yes | 1. Valid login... | Use numbered lines in one cell.
Priority | Yes | High | Highest, High, Medium, Low, Lowest.
Story Points | Yes | 5 | Numeric estimate; recommended Fibonacci values such as 1,2,3,5,8,13.
Assignee Roll No | Yes | 23K91A05L5 | Must belong to the currently selected project batch.
Assignee Name | Yes | Royyala Sindhuja | Must match the student identified by Assignee Roll No.
Sprint | No | Sprint 1 | If blank, story remains unscheduled/backlog.
Status | Yes | To Do | Allowed: To Do, In Progress, In Review, Done.
Labels | No | authentication,frontend | Comma-separated tags.

## Import Process
Trainer Import Workflow
Step | Action | Expected Result
1 | Select Department → Section → Batch → Project | BharatBuild establishes project context.
2 | Open User Stories → Import Stories | Import wizard opens.
3 | Upload this Excel file | Columns are detected automatically.
4 | Map Excel columns | Excel fields are mapped to BharatBuild story fields.
5 | Validate | Missing mandatory data, duplicate IDs and invalid assignees are flagged.
6 | Preview | Trainer reviews stories and student assignments.
7 | Confirm Import | Valid stories are created under the selected project.