## User Stories Import
Story ID | Work Type * | Epic | Summary * | Description * | Acceptance Criteria * | Priority * | Story Points * | Assignee Name * | Sprint | Status * | Labels
US-101 | Story | Platform Access | Reader registration and login | As a reader, I want to register and sign in with my own credentials so that I can reach my workspace securely. | 1. Valid credentials sign the reader in. 2. Invalid credentials show a clear error. 3. A session is created and expires after inactivity. 4. Passwords are stored only as salted hashes. | High | 5 | <Student 1> | Sprint 1 | To Do | nlp,auth,frontend
US-102 | Story | Platform Access | Password reset | As a reader, I want to reset a forgotten password so that I can regain access without an administrator. | 1. A reset link or OTP is sent to the registered contact. 2. The link expires after a set time. 3. A new password can be saved and used to sign in. 4. Reset attempts are recorded in the audit log. | Medium | 3 | <Student 2> | Sprint 1 | To Do | auth,security
US-103 | Story | Platform Access | Role-based access for content administrator | As a content administrator, I want a separate privileged view so that I can manage records without using a reader account. | 1. Reader and content administrator roles see different menus. 2. Privileged actions are refused for a normal reader. 3. Every privileged action is written to an audit trail. | High | 5 | <Student 3> | Sprint 1 | To Do | auth,rbac
US-104 | Story | Prompts Intake | Submit story prompts | As a reader, I want to submit story prompts to the system so that they can be processed. | 1. Supported formats are accepted and stored. 2. Unsupported or oversized input is refused with a reason. 3. Each submission is timestamped and linked to its owner. 4. A confirmation is shown once the upload completes. | Highest | 5 | <Student 4> | Sprint 1 | To Do | nlp,ingestion
US-105 | Story | Prompts Intake | Validate and clean story prompts | As a system, I want to validate and clean incoming story prompts so that poor quality input does not corrupt later stages. | 1. Missing and malformed fields are detected. 2. Duplicates are removed before processing. 3. A validation summary is available for each batch. 4. Rejected records are retained for review. | High | 5 | <Student 1> | Sprint 1 | To Do | validation,data
US-106 | Task | Prompts Intake | Project repository and environment setup | As a developer, I want a version-controlled repository with a reproducible environment so that the whole team builds on the same base. | 1. Repository created and branch rules agreed. 2. Dependencies pinned in a requirements file. 3. The project runs from a clean checkout by following the README. | Medium | 3 | <Student 2> | Sprint 1 | To Do | setup,devops
US-107 | Spike | Story Generation | Evaluate approaches for story generation | Research candidate approaches for story generation and record which one this project adopts. The surveyed work advances cross-lingual text-to-speech and multilingual NLP. The gap is joining controllable story generation to multilingual narration in one pipeline aimed at. | 1. At least three approaches are compared. 2. Strengths and limits of each are written up. 3. A recommendation with reasons is recorded. | Low | 3 | <Student 3> | Sprint 2 | To Do | research,spike
US-108 | Story | Story Generation | Accept a user prompt specifying theme | As a system, I want to accept a user prompt specifying theme, characters and target language so that the rest of the story generation pipeline can depend on it. | 1. The system accepts a user prompt specifying theme, characters and target language. 2. Invalid or missing story prompts are rejected with a clear message. 3. Behaviour is verified on a representative sample of story prompts. 4. Errors are logged with enough context to debug them. | Highest | 8 | <Student 4> | Sprint 2 | To Do | nlp,tts,multilingual
US-109 | Story | Story Generation | Generate coherent narrative text | As a system, I want to generate coherent narrative text using a language model, with controls for length and reading level so that the capability is available to the modules that follow. | 1. The system generates coherent narrative text using a language model, with controls for length and reading level. 2. The step runs end to end on the full project dataset. 3. Results are persisted and can be retrieved later. 4. The run is reproducible from a fixed configuration. | High | 8 | <Student 1> | Sprint 2 | To Do | nlp,tts,multilingual
US-110 | Story | Story Generation | Translate the generated story into the selected target | As a system, I want to translate the generated story into the selected target languages while preserving meaning so that story prompts are processed consistently. | 1. The system translates the generated story into the selected target languages while preserving meaning. 2. Configuration values are read from settings rather than hard-coded. 3. Edge cases found during testing are handled. 4. The content administrator can inspect the outcome. | High | 8 | <Student 2> | Sprint 2 | To Do | nlp,tts,multilingual
US-111 | Story | Story Generation | Convert the story text into natural speech | As a system, I want to convert the story text into natural speech using multilingual text-to-speech synthesis so that the behaviour is correct for both typical and edge inputs. | 1. The system converts the story text into natural speech using multilingual text-to-speech synthesis. 2. Processing completes within the agreed time budget. 3. The module has unit tests covering its main paths. 4. The step is documented in the project README. | High | 8 | <Student 3> | Sprint 3 | To Do | nlp,tts,multilingual
US-112 | Story | Story Generation | Provide playback with adjustable voice | As a system, I want to provide playback with adjustable voice, speed and language selection so that later features can build on a dependable output. | 1. The system provides playback with adjustable voice, speed and language selection. 2. Invalid or missing story prompts are rejected with a clear message. 3. Behaviour is verified on a representative sample of story prompts. 4. Errors are logged with enough context to debug them. | High | 8 | <Student 4> | Sprint 3 | To Do | nlp,tts,multilingual
US-113 | Story | Story Generation | Evaluate narrative coherence | As a developer, I want to evaluate narrative coherence, translation quality and speech naturalness through user rating so that the requirement can be demonstrated at review. | 1. The team has evaluated narrative coherence, translation quality and speech naturalness through user rating. 2. The step runs end to end on the full project dataset. 3. Results are persisted and can be retrieved later. 4. The run is reproducible from a fixed configuration. | High | 8 | <Student 1> | Sprint 3 | To Do | nlp,tts,multilingual
US-114 | Story | Story Generation | Review story generation output | As a reader, I want to review the story generation output in the interface so that I can confirm it before acting on it. | 1. The most recent output is shown together with its inputs. 2. The reader can flag an incorrect result. 3. Flagged items are queued for the content administrator to check. | Medium | 5 | <Student 2> | Sprint 2 | To Do | nlp,backend
US-115 | Task | Story Generation | Retry and logging for story generation | As a system, I want to retry and log failures in story generation so that a transient error does not lose data. | 1. Failed operations retry with backoff. 2. Repeated failures raise an alert. 3. Every failure is logged with its input reference. | Medium | 5 | <Student 3> | Sprint 3 | To Do | nlp,backend
US-116 | Story | Story Generation | Tune story generation | As a developer, I want to tune story generation on validation data so that accuracy improves before release. | 1. A parameter search is run and recorded. 2. Before and after metrics are compared. 3. The chosen settings are committed to the repository. | Medium | 5 | <Student 4> | Sprint 3 | To Do | nlp,backend
US-117 | Task | Story Generation | Expose story generation through an API | As a developer, I want to expose story generation through an internal API so that the interface and other modules can consume it. | 1. Endpoint documented with request and response examples. 2. Errors return meaningful status codes. 3. The endpoint is covered by an integration test. | Medium | 5 | <Student 1> | Sprint 3 | To Do | nlp,backend
US-118 | Story | Results and Reporting | Results dashboard | As a reader, I want a dashboard summarising the latest results so that I can understand the outcome at a glance. | 1. Key figures are shown with the date of the run. 2. Charts render correctly for an empty and a full dataset. 3. The dashboard loads within an acceptable time. | High | 5 | <Student 2> | Sprint 4 | To Do | dashboard,frontend
US-119 | Story | Results and Reporting | Export report | As a content administrator, I want to export the results as PDF or CSV so that I can share them outside the system. | 1. The export includes the figures shown on screen. 2. The file name carries the project and the date. 3. Large exports complete without timing out. | Medium | 3 | <Student 3> | Sprint 4 | To Do | export,reporting
US-120 | Story | Results and Reporting | History and search | As a reader, I want to search past records so that I can compare an earlier result with the current one. | 1. Records can be filtered by date and by status. 2. Search returns promptly on the full dataset. 3. An empty result set is shown clearly. | Medium | 3 | <Student 4> | Sprint 4 | To Do | search,frontend
US-121 | Story | Notifications | Notify reader of an important outcome | As a reader, I want to be notified when the system produces an outcome needing my attention so that I can respond promptly. | 1. A notification is raised when the configured condition is met. 2. The reader can see the notification history. 3. Repeated notifications for the same event are suppressed. | Medium | 3 | <Student 1> | Sprint 4 | To Do | notification,alerts
US-122 | Spike | Evaluation | Define and measure evaluation metrics | Decide which metrics judge this project and measure the current build against them. | 1. Metrics chosen and justified for this problem. 2. Current scores recorded as a baseline. 3. A target for the final review is agreed. | Low | 3 | <Student 2> | Sprint 5 | To Do | evaluation,research
US-123 | Task | Release | Deployment and user documentation | As a developer, I want the system deployed with setup and usage documentation so that the evaluators can run and demonstrate it. | 1. The application runs on the target environment. 2. Setup steps are documented and verified from scratch. 3. A short user guide covers the main workflow. | Low | 2 | <Student 3> | Sprint 5 | To Do | deployment,docs

## Field Guide
BharatBuild — User Stories Excel Import Guide
Fields marked with * are mandatory. Assignee Roll No and Assignee Name must match a registered student in the selected batch.
Field | Mandatory | Example | Validation / Usage
Story ID | No | US-101 | Optional unique reference. BharatBuild may generate one if blank.
Work Type | Yes | Story | Allowed: Story, Task, Spike.
Epic | No | Authentication | Existing or importable epic/feature grouping.
Summary | Yes | Student Login and Authentication | Short title of the user story.
Description | Yes | As a student, I want to... | Detailed functional/user-story description.
Acceptance Criteria | Yes | 1. Valid login... | Use numbered lines in one cell.
Priority | Yes | High | Highest, High, Medium, Low, Lowest.
Story Points | Yes | 5 | Numeric estimate; recommended Fibonacci values such as 1,2,3,5,8,13.
Assignee Roll No | Yes | 23K91A05L5 | Must belong to the currently selected project batch.
Assignee Name | Yes | Royyala Sindhuja | Must match the student identified by Assignee Roll No.
Sprint | No | Sprint 1 | If blank, story remains unscheduled/backlog.
Status | Yes | To Do | Allowed: To Do, In Progress, In Review, Done.
Labels | No | authentication,frontend | Comma-separated tags.

## Import Process
Trainer Import Workflow
Step | Action | Expected Result
1 | Select Department → Section → Batch → Project | BharatBuild establishes project context.
2 | Open User Stories → Import Stories | Import wizard opens.
3 | Upload this Excel file | Columns are detected automatically.
4 | Map Excel columns | Excel fields are mapped to BharatBuild story fields.
5 | Validate | Missing mandatory data, duplicate IDs and invalid assignees are flagged.
6 | Preview | Trainer reviews stories and student assignments.
7 | Confirm Import | Valid stories are created under the selected project.