## User Stories Import
Story ID | Work Type * | Epic | Summary * | Description * | Acceptance Criteria * | Priority * | Story Points * | Assignee Name * | Sprint | Status * | Labels
US-101 | Story | Platform Access | Driver registration and login | As a driver, I want to register and sign in with my own credentials so that I can reach my workspace securely. | 1. Valid credentials sign the driver in. 2. Invalid credentials show a clear error. 3. A session is created and expires after inactivity. 4. Passwords are stored only as salted hashes. | High | 5 | <Student 1> | Sprint 1 | To Do | booking,auth,frontend
US-102 | Story | Platform Access | Password reset | As a driver, I want to reset a forgotten password so that I can regain access without an administrator. | 1. A reset link or OTP is sent to the registered contact. 2. The link expires after a set time. 3. A new password can be saved and used to sign in. 4. Reset attempts are recorded in the audit log. | Medium | 3 | <Student 2> | Sprint 1 | To Do | auth,security
US-103 | Story | Platform Access | Role-based access for parking operator | As a parking operator, I want a separate privileged view so that I can manage records without using a driver account. | 1. Driver and parking operator roles see different menus. 2. Privileged actions are refused for a normal driver. 3. Every privileged action is written to an audit trail. | High | 5 | <Student 3> | Sprint 1 | To Do | auth,rbac
US-104 | Story | Data Intake | Submit parking slot data | As a driver, I want to submit parking slot data to the system so that they can be processed. | 1. Supported formats are accepted and stored. 2. Unsupported or oversized input is refused with a reason. 3. Each submission is timestamped and linked to its owner. 4. A confirmation is shown once the upload completes. | Highest | 5 | <Student 4> | Sprint 1 | To Do | booking,ingestion
US-105 | Story | Data Intake | Validate and clean parking slot data | As a system, I want to validate and clean incoming parking slot data so that poor quality input does not corrupt later stages. | 1. Missing and malformed fields are detected. 2. Duplicates are removed before processing. 3. A validation summary is available for each batch. 4. Rejected records are retained for review. | High | 5 | <Student 1> | Sprint 1 | To Do | validation,data
US-106 | Task | Data Intake | Project repository and environment setup | As a developer, I want a version-controlled repository with a reproducible environment so that the whole team builds on the same base. | 1. Repository created and branch rules agreed. 2. Dependencies pinned in a requirements file. 3. The project runs from a clean checkout by following the README. | Medium | 3 | <Student 2> | Sprint 1 | To Do | setup,devops
US-107 | Spike | Slot Reservation | Evaluate approaches for slot reservation | Research candidate approaches for slot reservation and record which one this project adopts. The surveyed work optimises allocation within large managed facilities. The gap is a general reservation platform covering search, booking, payment and operator analytics for ordinary. | 1. At least three approaches are compared. 2. Strengths and limits of each are written up. 3. A recommendation with reasons is recorded. | Low | 3 | <Student 3> | Sprint 2 | To Do | research,spike
US-108 | Story | Slot Reservation | Build user registration, authentication | As a developer, I want to build user registration, authentication and vehicle profile management so that the rest of the slot reservation pipeline can depend on it. | 1. The delivered system provides user registration, authentication and vehicle profile management. 2. Invalid or missing parking slot data are rejected with a clear message. 3. Behaviour is verified on a representative sample of parking slot data. 4. Errors are logged with enough context to debug them. | Highest | 8 | <Student 4> | Sprint 2 | To Do | booking,web,payments
US-109 | Story | Slot Reservation | Maintain real-time parking slot availability across | As a system, I want to maintain real-time parking slot availability across registered parking facilities so that the capability is available to the modules that follow. | 1. The system maintains real-time parking slot availability across registered parking facilities. 2. The step runs end to end on the full project dataset. 3. Results are persisted and can be retrieved later. 4. The run is reproducible from a fixed configuration. | High | 8 | <Student 1> | Sprint 2 | To Do | booking,web,payments
US-110 | Story | Slot Reservation | Implement slot search, advance reservation | As a developer, I want to implement slot search, advance reservation and booking cancellation so that parking slot data are processed consistently. | 1. The delivered system provides slot search, advance reservation and booking cancellation. 2. Configuration values are read from settings rather than hard-coded. 3. Edge cases found during testing are handled. 4. The parking operator can inspect the outcome. | High | 8 | <Student 2> | Sprint 2 | To Do | booking,web,payments
US-111 | Story | Slot Reservation | Integrate secure online payment and generate digital receipts | As a developer, I want to integrate secure online payment and generate digital receipts so that the behaviour is correct for both typical and edge inputs. | 1. The delivered system provides secure online payment and generate digital receipts. 2. Processing completes within the agreed time budget. 3. The module has unit tests covering its main paths. 4. The step is documented in the project README. | High | 8 | <Student 3> | Sprint 3 | To Do | booking,web,payments
US-112 | Story | Slot Reservation | Provide an administrator dashboard for slots, bookings | As a system, I want to provide an administrator dashboard for slots, bookings, occupancy and revenue so that later features can build on a dependable output. | 1. The system provides an administrator dashboard for slots, bookings, occupancy and revenue. 2. Invalid or missing parking slot data are rejected with a clear message. 3. Behaviour is verified on a representative sample of parking slot data. 4. Errors are logged with enough context to debug them. | High | 8 | <Student 4> | Sprint 3 | To Do | booking,web,payments
US-113 | Story | Slot Reservation | Evaluate booking success rate | As a developer, I want to evaluate booking success rate, allocation efficiency and system response time so that the requirement can be demonstrated at review. | 1. The team has evaluated booking success rate, allocation efficiency and system response time. 2. The step runs end to end on the full project dataset. 3. Results are persisted and can be retrieved later. 4. The run is reproducible from a fixed configuration. | High | 8 | <Student 1> | Sprint 3 | To Do | booking,web,payments
US-114 | Story | Slot Reservation | Review slot reservation output | As a driver, I want to review the slot reservation output in the interface so that I can confirm it before acting on it. | 1. The most recent output is shown together with its inputs. 2. The driver can flag an incorrect result. 3. Flagged items are queued for the parking operator to check. | Medium | 5 | <Student 2> | Sprint 2 | To Do | booking,backend
US-115 | Task | Slot Reservation | Retry and logging for slot reservation | As a system, I want to retry and log failures in slot reservation so that a transient error does not lose data. | 1. Failed operations retry with backoff. 2. Repeated failures raise an alert. 3. Every failure is logged with its input reference. | Medium | 5 | <Student 3> | Sprint 3 | To Do | booking,backend
US-116 | Story | Slot Reservation | Tune slot reservation | As a developer, I want to tune slot reservation on validation data so that accuracy improves before release. | 1. A parameter search is run and recorded. 2. Before and after metrics are compared. 3. The chosen settings are committed to the repository. | Medium | 5 | <Student 4> | Sprint 3 | To Do | booking,backend
US-117 | Task | Slot Reservation | Expose slot reservation through an API | As a developer, I want to expose slot reservation through an internal API so that the interface and other modules can consume it. | 1. Endpoint documented with request and response examples. 2. Errors return meaningful status codes. 3. The endpoint is covered by an integration test. | Medium | 5 | <Student 1> | Sprint 3 | To Do | booking,backend
US-118 | Story | Results and Reporting | Results dashboard | As a driver, I want a dashboard summarising the latest results so that I can understand the outcome at a glance. | 1. Key figures are shown with the date of the run. 2. Charts render correctly for an empty and a full dataset. 3. The dashboard loads within an acceptable time. | High | 5 | <Student 2> | Sprint 4 | To Do | dashboard,frontend
US-119 | Story | Results and Reporting | Export report | As a parking operator, I want to export the results as PDF or CSV so that I can share them outside the system. | 1. The export includes the figures shown on screen. 2. The file name carries the project and the date. 3. Large exports complete without timing out. | Medium | 3 | <Student 3> | Sprint 4 | To Do | export,reporting
US-120 | Story | Results and Reporting | History and search | As a driver, I want to search past records so that I can compare an earlier result with the current one. | 1. Records can be filtered by date and by status. 2. Search returns promptly on the full dataset. 3. An empty result set is shown clearly. | Medium | 3 | <Student 4> | Sprint 4 | To Do | search,frontend
US-121 | Story | Notifications | Notify driver of an important outcome | As a driver, I want to be notified when the system produces an outcome needing my attention so that I can respond promptly. | 1. A notification is raised when the configured condition is met. 2. The driver can see the notification history. 3. Repeated notifications for the same event are suppressed. | Medium | 3 | <Student 1> | Sprint 4 | To Do | notification,alerts
US-122 | Spike | Evaluation | Define and measure evaluation metrics | Decide which metrics judge this project and measure the current build against them. | 1. Metrics chosen and justified for this problem. 2. Current scores recorded as a baseline. 3. A target for the final review is agreed. | Low | 3 | <Student 2> | Sprint 5 | To Do | evaluation,research
US-123 | Task | Release | Deployment and user documentation | As a developer, I want the system deployed with setup and usage documentation so that the evaluators can run and demonstrate it. | 1. The application runs on the target environment. 2. Setup steps are documented and verified from scratch. 3. A short user guide covers the main workflow. | Low | 2 | <Student 3> | Sprint 5 | To Do | deployment,docs

## Field Guide
BharatBuild — User Stories Excel Import Guide
Fields marked with * are mandatory. Assignee Roll No and Assignee Name must match a registered student in the selected batch.
Field | Mandatory | Example | Validation / Usage
Story ID | No | US-101 | Optional unique reference. BharatBuild may generate one if blank.
Work Type | Yes | Story | Allowed: Story, Task, Spike.
Epic | No | Authentication | Existing or importable epic/feature grouping.
Summary | Yes | Student Login and Authentication | Short title of the user story.
Description | Yes | As a student, I want to... | Detailed functional/user-story description.
Acceptance Criteria | Yes | 1. Valid login... | Use numbered lines in one cell.
Priority | Yes | High | Highest, High, Medium, Low, Lowest.
Story Points | Yes | 5 | Numeric estimate; recommended Fibonacci values such as 1,2,3,5,8,13.
Assignee Roll No | Yes | 23K91A05L5 | Must belong to the currently selected project batch.
Assignee Name | Yes | Royyala Sindhuja | Must match the student identified by Assignee Roll No.
Sprint | No | Sprint 1 | If blank, story remains unscheduled/backlog.
Status | Yes | To Do | Allowed: To Do, In Progress, In Review, Done.
Labels | No | authentication,frontend | Comma-separated tags.

## Import Process
Trainer Import Workflow
Step | Action | Expected Result
1 | Select Department → Section → Batch → Project | BharatBuild establishes project context.
2 | Open User Stories → Import Stories | Import wizard opens.
3 | Upload this Excel file | Columns are detected automatically.
4 | Map Excel columns | Excel fields are mapped to BharatBuild story fields.
5 | Validate | Missing mandatory data, duplicate IDs and invalid assignees are flagged.
6 | Preview | Trainer reviews stories and student assignments.
7 | Confirm Import | Valid stories are created under the selected project.