## User Stories Import
Story ID | Work Type * | Epic | Summary * | Description * | Acceptance Criteria * | Priority * | Story Points * | Assignee Name * | Sprint | Status * | Labels
US-101 | Story | Platform Access | Investor registration and login | As a investor, I want to register and sign in with my own credentials so that I can reach my workspace securely. | 1. Valid credentials sign the investor in. 2. Invalid credentials show a clear error. 3. A session is created and expires after inactivity. 4. Passwords are stored only as salted hashes. | High | 5 | POTTEPAKA LINGASWAMY | Sprint 1 | To Do | fintech,auth,frontend
US-102 | Story | Platform Access | Password reset | As a investor, I want to reset a forgotten password so that I can regain access without an administrator. | 1. A reset link or OTP is sent to the registered contact. 2. The link expires after a set time. 3. A new password can be saved and used to sign in. 4. Reset attempts are recorded in the audit log. | Medium | 3 | MADUNA NAVEEN KUMAR | Sprint 1 | To Do | auth,security
US-103 | Story | Platform Access | Role-based access for portfolio analyst | As a portfolio analyst, I want a separate privileged view so that I can manage records without using a investor account. | 1. Investor and portfolio analyst roles see different menus. 2. Privileged actions are refused for a normal investor. 3. Every privileged action is written to an audit trail. | High | 5 | MEDDIGERI KEERTHI | Sprint 1 | To Do | auth,rbac
US-104 | Story | Data Intake | Submit market and news data | As a investor, I want to submit market and news data to the system so that they can be processed. | 1. Supported formats are accepted and stored. 2. Unsupported or oversized input is refused with a reason. 3. Each submission is timestamped and linked to its owner. 4. A confirmation is shown once the upload completes. | Highest | 5 | MAREDDY SAI KARTHIK | Sprint 1 | To Do | fintech,ingestion
US-105 | Story | Data Intake | Validate and clean market and news data | As a system, I want to validate and clean incoming market and news data so that poor quality input does not corrupt later stages. | 1. Missing and malformed fields are detected. 2. Duplicates are removed before processing. 3. A validation summary is available for each batch. 4. Rejected records are retained for review. | High | 5 | POTTEPAKA LINGASWAMY | Sprint 1 | To Do | validation,data
US-106 | Task | Data Intake | Project repository and environment setup | As a developer, I want a version-controlled repository with a reproducible environment so that the whole team builds on the same base. | 1. Repository created and branch rules agreed. 2. Dependencies pinned in a requirements file. 3. The project runs from a clean checkout by following the README. | Medium | 3 | MADUNA NAVEEN KUMAR | Sprint 1 | To Do | setup,devops
US-107 | Spike | Prediction Engine | Evaluate approaches for prediction engine | Research candidate approaches for prediction engine and record which one this project adopts. The surveyed work integrates sequence models with news fusion for price prediction. The gap is the explicit multiple-instance treatment of daily news, which removes the need for. | 1. At least three approaches are compared. 2. Strengths and limits of each are written up. 3. A recommendation with reasons is recorded. | Low | 3 | MEDDIGERI KEERTHI | Sprint 2 | To Do | research,spike
US-108 | Story | Prediction Engine | Collect historical price data together | As a system, I want to collect historical price data together with financial news and social media text for the target stocks so that the rest of the prediction engine pipeline can depend on it. | 1. The system collects historical price data together with financial news and social media text for the target stocks. 2. Invalid or missing market and news data are rejected with a clear message. 3. Behaviour is verified on a representative sample of market and news data. 4. Errors are logged with enough context to debug them. | Highest | 8 | MAREDDY SAI KARTHIK | Sprint 2 | To Do | fintech,ml,forecasting
US-109 | Story | Prediction Engine | Preprocess and align the multi-source data into daily | As a developer, I want to preprocess and align the multi-source data into daily instances grouped per trading day so that the capability is available to the modules that follow. | 1. The team has preprocessed and align the multi-source data into daily instances grouped per trading day. 2. The step runs end to end on the full project dataset. 3. Results are persisted and can be retrieved later. 4. The run is reproducible from a fixed configuration. | High | 8 | POTTEPAKA LINGASWAMY | Sprint 2 | To Do | fintech,ml,forecasting
US-110 | Story | Prediction Engine | Represent each trading day as a bag | As a system, I want to represent each trading day as a bag of news instances under the Multiple Instance Learning formulation so that market and news data are processed consistently. | 1. The system represents each trading day as a bag of news instances under the Multiple Instance Learning formulation. 2. Configuration values are read from settings rather than hard-coded. 3. Edge cases found during testing are handled. 4. The portfolio analyst can inspect the outcome. | High | 8 | MADUNA NAVEEN KUMAR | Sprint 2 | To Do | fintech,ml,forecasting
US-111 | Story | Prediction Engine | Train a hybrid model combining sequence learning over prices | As a developer, I want to train a hybrid model combining sequence learning over prices with attention over news content so that the behaviour is correct for both typical and edge inputs. | 1. The team has trained a hybrid model combining sequence learning over prices with attention over news content. 2. Processing completes within the agreed time budget. 3. The module has unit tests covering its main paths. 4. The step is documented in the project README. | High | 8 | MEDDIGERI KEERTHI | Sprint 3 | To Do | fintech,ml,forecasting
US-112 | Story | Prediction Engine | Predict directional movement and evaluate | As a system, I want to predict directional movement and evaluate using accuracy, precision, recall and F1-score so that later features can build on a dependable output. | 1. The system predicts directional movement and evaluate using accuracy, precision, recall and F1-score. 2. Invalid or missing market and news data are rejected with a clear message. 3. Behaviour is verified on a representative sample of market and news data. 4. Errors are logged with enough context to debug them. | High | 8 | MAREDDY SAI KARTHIK | Sprint 3 | To Do | fintech,ml,forecasting
US-113 | Story | Prediction Engine | Compare multi-source performance against a price-only baseline | As a developer, I want to compare multi-source performance against a price-only baseline so that the requirement can be demonstrated at review. | 1. The team has compared multi-source performance against a price-only baseline. 2. The step runs end to end on the full project dataset. 3. Results are persisted and can be retrieved later. 4. The run is reproducible from a fixed configuration. | High | 8 | POTTEPAKA LINGASWAMY | Sprint 3 | To Do | fintech,ml,forecasting
US-114 | Story | Prediction Engine | Review prediction engine output | As a investor, I want to review the prediction engine output in the interface so that I can confirm it before acting on it. | 1. The most recent output is shown together with its inputs. 2. The investor can flag an incorrect result. 3. Flagged items are queued for the portfolio analyst to check. | Medium | 5 | MADUNA NAVEEN KUMAR | Sprint 2 | To Do | fintech,backend
US-115 | Task | Prediction Engine | Retry and logging for prediction engine | As a system, I want to retry and log failures in prediction engine so that a transient error does not lose data. | 1. Failed operations retry with backoff. 2. Repeated failures raise an alert. 3. Every failure is logged with its input reference. | Medium | 5 | MEDDIGERI KEERTHI | Sprint 3 | To Do | fintech,backend
US-116 | Story | Prediction Engine | Tune prediction engine | As a developer, I want to tune prediction engine on validation data so that accuracy improves before release. | 1. A parameter search is run and recorded. 2. Before and after metrics are compared. 3. The chosen settings are committed to the repository. | Medium | 5 | MAREDDY SAI KARTHIK | Sprint 3 | To Do | fintech,backend
US-117 | Task | Prediction Engine | Expose prediction engine through an API | As a developer, I want to expose prediction engine through an internal API so that the interface and other modules can consume it. | 1. Endpoint documented with request and response examples. 2. Errors return meaningful status codes. 3. The endpoint is covered by an integration test. | Medium | 5 | POTTEPAKA LINGASWAMY | Sprint 3 | To Do | fintech,backend
US-118 | Story | Results and Reporting | Results dashboard | As a investor, I want a dashboard summarising the latest results so that I can understand the outcome at a glance. | 1. Key figures are shown with the date of the run. 2. Charts render correctly for an empty and a full dataset. 3. The dashboard loads within an acceptable time. | High | 5 | MADUNA NAVEEN KUMAR | Sprint 4 | To Do | dashboard,frontend
US-119 | Story | Results and Reporting | Export report | As a portfolio analyst, I want to export the results as PDF or CSV so that I can share them outside the system. | 1. The export includes the figures shown on screen. 2. The file name carries the project and the date. 3. Large exports complete without timing out. | Medium | 3 | MEDDIGERI KEERTHI | Sprint 4 | To Do | export,reporting
US-120 | Story | Results and Reporting | History and search | As a investor, I want to search past records so that I can compare an earlier result with the current one. | 1. Records can be filtered by date and by status. 2. Search returns promptly on the full dataset. 3. An empty result set is shown clearly. | Medium | 3 | MAREDDY SAI KARTHIK | Sprint 4 | To Do | search,frontend
US-121 | Story | Notifications | Notify investor of an important outcome | As a investor, I want to be notified when the system produces an outcome needing my attention so that I can respond promptly. | 1. A notification is raised when the configured condition is met. 2. The investor can see the notification history. 3. Repeated notifications for the same event are suppressed. | Medium | 3 | POTTEPAKA LINGASWAMY | Sprint 4 | To Do | notification,alerts
US-122 | Spike | Evaluation | Define and measure evaluation metrics | Decide which metrics judge this project and measure the current build against them. | 1. Metrics chosen and justified for this problem. 2. Current scores recorded as a baseline. 3. A target for the final review is agreed. | Low | 3 | MADUNA NAVEEN KUMAR | Sprint 5 | To Do | evaluation,research
US-123 | Task | Release | Deployment and user documentation | As a developer, I want the system deployed with setup and usage documentation so that the evaluators can run and demonstrate it. | 1. The application runs on the target environment. 2. Setup steps are documented and verified from scratch. 3. A short user guide covers the main workflow. | Low | 2 | MEDDIGERI KEERTHI | Sprint 5 | To Do | deployment,docs

## Field Guide
BharatBuild — User Stories Excel Import Guide
Fields marked with * are mandatory. Assignee Roll No and Assignee Name must match a registered student in the selected batch.
Field | Mandatory | Example | Validation / Usage
Story ID | No | US-101 | Optional unique reference. BharatBuild may generate one if blank.
Work Type | Yes | Story | Allowed: Story, Task, Spike.
Epic | No | Authentication | Existing or importable epic/feature grouping.
Summary | Yes | Student Login and Authentication | Short title of the user story.
Description | Yes | As a student, I want to... | Detailed functional/user-story description.
Acceptance Criteria | Yes | 1. Valid login... | Use numbered lines in one cell.
Priority | Yes | High | Highest, High, Medium, Low, Lowest.
Story Points | Yes | 5 | Numeric estimate; recommended Fibonacci values such as 1,2,3,5,8,13.
Assignee Roll No | Yes | 23K91A05L5 | Must belong to the currently selected project batch.
Assignee Name | Yes | Royyala Sindhuja | Must match the student identified by Assignee Roll No.
Sprint | No | Sprint 1 | If blank, story remains unscheduled/backlog.
Status | Yes | To Do | Allowed: To Do, In Progress, In Review, Done.
Labels | No | authentication,frontend | Comma-separated tags.

## Import Process
Trainer Import Workflow
Step | Action | Expected Result
1 | Select Department → Section → Batch → Project | BharatBuild establishes project context.
2 | Open User Stories → Import Stories | Import wizard opens.
3 | Upload this Excel file | Columns are detected automatically.
4 | Map Excel columns | Excel fields are mapped to BharatBuild story fields.
5 | Validate | Missing mandatory data, duplicate IDs and invalid assignees are flagged.
6 | Preview | Trainer reviews stories and student assignments.
7 | Confirm Import | Valid stories are created under the selected project.