## User Stories Import
Story ID | Work Type * | Epic | Summary * | Description * | Acceptance Criteria * | Priority * | Story Points * | Assignee Name * | Sprint | Status * | Labels
US-101 | Story | Platform Access | Student registration and login | As a student, I want to register and sign in with my own credentials so that I can reach my workspace securely. | 1. Valid credentials sign the student in. 2. Invalid credentials show a clear error. 3. A session is created and expires after inactivity. 4. Passwords are stored only as salted hashes. | High | 5 | Mopidevi Bhagyasri | Sprint 1 | To Do | placement,auth,frontend
US-102 | Story | Platform Access | Password reset | As a student, I want to reset a forgotten password so that I can regain access without an administrator. | 1. A reset link or OTP is sent to the registered contact. 2. The link expires after a set time. 3. A new password can be saved and used to sign in. 4. Reset attempts are recorded in the audit log. | Medium | 3 | P Harsha Vardan Reddy | Sprint 1 | To Do | auth,security
US-103 | Story | Platform Access | Role-based access for placement officer | As a placement officer, I want a separate privileged view so that I can manage records without using a student account. | 1. Student and placement officer roles see different menus. 2. Privileged actions are refused for a normal student. 3. Every privileged action is written to an audit trail. | High | 5 | Mohammad Faruk Baba | Sprint 1 | To Do | auth,rbac
US-104 | Story | Profiles Intake | Submit student academic profiles | As a student, I want to submit student academic profiles to the system so that they can be processed. | 1. Supported formats are accepted and stored. 2. Unsupported or oversized input is refused with a reason. 3. Each submission is timestamped and linked to its owner. 4. A confirmation is shown once the upload completes. | Highest | 5 | Prahalladh Terati | Sprint 1 | To Do | placement,ingestion
US-105 | Story | Profiles Intake | Validate and clean student academic profiles | As a system, I want to validate and clean incoming student academic profiles so that poor quality input does not corrupt later stages. | 1. Missing and malformed fields are detected. 2. Duplicates are removed before processing. 3. A validation summary is available for each batch. 4. Rejected records are retained for review. | High | 5 | Mopidevi Bhagyasri | Sprint 1 | To Do | validation,data
US-106 | Task | Profiles Intake | Project repository and environment setup | As a developer, I want a version-controlled repository with a reproducible environment so that the whole team builds on the same base. | 1. Repository created and branch rules agreed. 2. Dependencies pinned in a requirements file. 3. The project runs from a clean checkout by following the README. | Medium | 3 | P Harsha Vardan Reddy | Sprint 1 | To Do | setup,devops
US-107 | Spike | Placement Prediction | Evaluate approaches for placement prediction | Research candidate approaches for placement prediction and record which one this project adopts. The surveyed work predicts placement outcomes from academic records. The gap is extending prediction into company recommendation and actionable skill-gap feedback for the student. | 1. At least three approaches are compared. 2. Strengths and limits of each are written up. 3. A recommendation with reasons is recorded. | Low | 3 | Mohammad Faruk Baba | Sprint 2 | To Do | research,spike
US-108 | Story | Placement Prediction | Collect student academic records, technical skills | As a system, I want to collect student academic records, technical skills, aptitude scores and historical placement outcomes so that the rest of the placement prediction pipeline can depend on it. | 1. The system collects student academic records, technical skills, aptitude scores and historical placement outcomes. 2. Invalid or missing student academic profiles are rejected with a clear message. 3. Behaviour is verified on a representative sample of student academic profiles. 4. Errors are logged with enough context to debug them. | Highest | 8 | Prahalladh Terati | Sprint 2 | To Do | placement,ml,analytics
US-109 | Story | Placement Prediction | Clean and encode the data | As a system, I want to clean and encode the data and address imbalance between placed and unplaced students so that the capability is available to the modules that follow. | 1. The system cleans and encode the data and address imbalance between placed and unplaced students. 2. The step runs end to end on the full project dataset. 3. Results are persisted and can be retrieved later. 4. The run is reproducible from a fixed configuration. | High | 8 | Mopidevi Bhagyasri | Sprint 2 | To Do | placement,ml,analytics
US-110 | Story | Placement Prediction | Train and compare classifiers | As a developer, I want to train and compare classifiers to predict placement eligibility for each student so that student academic profiles are processed consistently. | 1. The team has trained and compared classifiers to predict placement eligibility for each student. 2. Configuration values are read from settings rather than hard-coded. 3. Edge cases found during testing are handled. 4. The placement officer can inspect the outcome. | High | 8 | P Harsha Vardan Reddy | Sprint 2 | To Do | placement,ml,analytics
US-111 | Story | Placement Prediction | Recommend suitable companies | As a system, I want to recommend suitable companies by matching student profiles against recruiter requirements so that the behaviour is correct for both typical and edge inputs. | 1. The system recommends suitable companies by matching student profiles against recruiter requirements. 2. Processing completes within the agreed time budget. 3. The module has unit tests covering its main paths. 4. The step is documented in the project README. | High | 8 | Mohammad Faruk Baba | Sprint 3 | To Do | placement,ml,analytics
US-112 | Story | Placement Prediction | Identify the skill gaps | As a system, I want to identify the skill gaps that most reduce a student's placement probability so that later features can build on a dependable output. | 1. The system identifies the skill gaps that most reduce a student's placement probability. 2. Invalid or missing student academic profiles are rejected with a clear message. 3. Behaviour is verified on a representative sample of student academic profiles. 4. Errors are logged with enough context to debug them. | High | 8 | Prahalladh Terati | Sprint 3 | To Do | placement,ml,analytics
US-113 | Story | Placement Prediction | Provide dashboards for placement officers and evaluate | As a system, I want to provide dashboards for placement officers and evaluate using accuracy, precision and recall so that the requirement can be demonstrated at review. | 1. The system provides dashboards for placement officers and evaluate using accuracy, precision and recall. 2. The step runs end to end on the full project dataset. 3. Results are persisted and can be retrieved later. 4. The run is reproducible from a fixed configuration. | High | 8 | Mopidevi Bhagyasri | Sprint 3 | To Do | placement,ml,analytics
US-114 | Story | Placement Prediction | Review placement prediction output | As a student, I want to review the placement prediction output in the interface so that I can confirm it before acting on it. | 1. The most recent output is shown together with its inputs. 2. The student can flag an incorrect result. 3. Flagged items are queued for the placement officer to check. | Medium | 5 | P Harsha Vardan Reddy | Sprint 2 | To Do | placement,backend
US-115 | Task | Placement Prediction | Retry and logging for placement prediction | As a system, I want to retry and log failures in placement prediction so that a transient error does not lose data. | 1. Failed operations retry with backoff. 2. Repeated failures raise an alert. 3. Every failure is logged with its input reference. | Medium | 5 | Mohammad Faruk Baba | Sprint 3 | To Do | placement,backend
US-116 | Story | Placement Prediction | Tune placement prediction | As a developer, I want to tune placement prediction on validation data so that accuracy improves before release. | 1. A parameter search is run and recorded. 2. Before and after metrics are compared. 3. The chosen settings are committed to the repository. | Medium | 5 | Prahalladh Terati | Sprint 3 | To Do | placement,backend
US-117 | Task | Placement Prediction | Expose placement prediction through an API | As a developer, I want to expose placement prediction through an internal API so that the interface and other modules can consume it. | 1. Endpoint documented with request and response examples. 2. Errors return meaningful status codes. 3. The endpoint is covered by an integration test. | Medium | 5 | Mopidevi Bhagyasri | Sprint 3 | To Do | placement,backend
US-118 | Story | Results and Reporting | Results dashboard | As a student, I want a dashboard summarising the latest results so that I can understand the outcome at a glance. | 1. Key figures are shown with the date of the run. 2. Charts render correctly for an empty and a full dataset. 3. The dashboard loads within an acceptable time. | High | 5 | P Harsha Vardan Reddy | Sprint 4 | To Do | dashboard,frontend
US-119 | Story | Results and Reporting | Export report | As a placement officer, I want to export the results as PDF or CSV so that I can share them outside the system. | 1. The export includes the figures shown on screen. 2. The file name carries the project and the date. 3. Large exports complete without timing out. | Medium | 3 | Mohammad Faruk Baba | Sprint 4 | To Do | export,reporting
US-120 | Story | Results and Reporting | History and search | As a student, I want to search past records so that I can compare an earlier result with the current one. | 1. Records can be filtered by date and by status. 2. Search returns promptly on the full dataset. 3. An empty result set is shown clearly. | Medium | 3 | Prahalladh Terati | Sprint 4 | To Do | search,frontend
US-121 | Story | Notifications | Notify student of an important outcome | As a student, I want to be notified when the system produces an outcome needing my attention so that I can respond promptly. | 1. A notification is raised when the configured condition is met. 2. The student can see the notification history. 3. Repeated notifications for the same event are suppressed. | Medium | 3 | Mopidevi Bhagyasri | Sprint 4 | To Do | notification,alerts
US-122 | Spike | Evaluation | Define and measure evaluation metrics | Decide which metrics judge this project and measure the current build against them. | 1. Metrics chosen and justified for this problem. 2. Current scores recorded as a baseline. 3. A target for the final review is agreed. | Low | 3 | P Harsha Vardan Reddy | Sprint 5 | To Do | evaluation,research
US-123 | Task | Release | Deployment and user documentation | As a developer, I want the system deployed with setup and usage documentation so that the evaluators can run and demonstrate it. | 1. The application runs on the target environment. 2. Setup steps are documented and verified from scratch. 3. A short user guide covers the main workflow. | Low | 2 | Mohammad Faruk Baba | Sprint 5 | To Do | deployment,docs

## Field Guide
BharatBuild — User Stories Excel Import Guide
Fields marked with * are mandatory. Assignee Roll No and Assignee Name must match a registered student in the selected batch.
Field | Mandatory | Example | Validation / Usage
Story ID | No | US-101 | Optional unique reference. BharatBuild may generate one if blank.
Work Type | Yes | Story | Allowed: Story, Task, Spike.
Epic | No | Authentication | Existing or importable epic/feature grouping.
Summary | Yes | Student Login and Authentication | Short title of the user story.
Description | Yes | As a student, I want to... | Detailed functional/user-story description.
Acceptance Criteria | Yes | 1. Valid login... | Use numbered lines in one cell.
Priority | Yes | High | Highest, High, Medium, Low, Lowest.
Story Points | Yes | 5 | Numeric estimate; recommended Fibonacci values such as 1,2,3,5,8,13.
Assignee Roll No | Yes | 23K91A05L5 | Must belong to the currently selected project batch.
Assignee Name | Yes | Royyala Sindhuja | Must match the student identified by Assignee Roll No.
Sprint | No | Sprint 1 | If blank, story remains unscheduled/backlog.
Status | Yes | To Do | Allowed: To Do, In Progress, In Review, Done.
Labels | No | authentication,frontend | Comma-separated tags.

## Import Process
Trainer Import Workflow
Step | Action | Expected Result
1 | Select Department → Section → Batch → Project | BharatBuild establishes project context.
2 | Open User Stories → Import Stories | Import wizard opens.
3 | Upload this Excel file | Columns are detected automatically.
4 | Map Excel columns | Excel fields are mapped to BharatBuild story fields.
5 | Validate | Missing mandatory data, duplicate IDs and invalid assignees are flagged.
6 | Preview | Trainer reviews stories and student assignments.
7 | Confirm Import | Valid stories are created under the selected project.