## User Stories Import
Story ID | Work Type * | Epic | Summary * | Description * | Acceptance Criteria * | Priority * | Story Points * | Assignee Name * | Sprint | Status * | Labels
US-101 | Story | Platform Access | Reader registration and login | As a reader, I want to register and sign in with my own credentials so that I can reach my workspace securely. | 1. Valid credentials sign the reader in. 2. Invalid credentials show a clear error. 3. A session is created and expires after inactivity. 4. Passwords are stored only as salted hashes. | High | 5 | N. MOJES | Sprint 1 | To Do | nlp,auth,frontend
US-102 | Story | Platform Access | Password reset | As a reader, I want to reset a forgotten password so that I can regain access without an administrator. | 1. A reset link or OTP is sent to the registered contact. 2. The link expires after a set time. 3. A new password can be saved and used to sign in. 4. Reset attempts are recorded in the audit log. | Medium | 3 | NOOR SANIYA | Sprint 1 | To Do | auth,security
US-103 | Story | Platform Access | Role-based access for content moderator | As a content moderator, I want a separate privileged view so that I can manage records without using a reader account. | 1. Reader and content moderator roles see different menus. 2. Privileged actions are refused for a normal reader. 3. Every privileged action is written to an audit trail. | High | 5 | M. AKSHITHA | Sprint 1 | To Do | auth,rbac
US-104 | Story | Articles Intake | Submit news articles | As a reader, I want to submit news articles to the system so that they can be processed. | 1. Supported formats are accepted and stored. 2. Unsupported or oversized input is refused with a reason. 3. Each submission is timestamped and linked to its owner. 4. A confirmation is shown once the upload completes. | Highest | 5 | M. AASHRITHA | Sprint 1 | To Do | nlp,ingestion
US-105 | Story | Articles Intake | Validate and clean news articles | As a system, I want to validate and clean incoming news articles so that poor quality input does not corrupt later stages. | 1. Missing and malformed fields are detected. 2. Duplicates are removed before processing. 3. A validation summary is available for each batch. 4. Rejected records are retained for review. | High | 5 | N. MOJES | Sprint 1 | To Do | validation,data
US-106 | Task | Articles Intake | Project repository and environment setup | As a developer, I want a version-controlled repository with a reproducible environment so that the whole team builds on the same base. | 1. Repository created and branch rules agreed. 2. Dependencies pinned in a requirements file. 3. The project runs from a clean checkout by following the README. | Medium | 3 | NOOR SANIYA | Sprint 1 | To Do | setup,devops
US-107 | Spike | Classification Engine | Evaluate approaches for classification engine | Research candidate approaches for classification engine and record which one this project adopts. The surveyed work applies neural and transformer models to fake news detection. The gap is a computationally light pipeline where feature reduction and metaheuristic parameter tuning. | 1. At least three approaches are compared. 2. Strengths and limits of each are written up. 3. A recommendation with reasons is recorded. | Low | 3 | M. AKSHITHA | Sprint 2 | To Do | research,spike
US-108 | Story | Classification Engine | Assemble a labelled dataset of genuine | As a developer, I want to assemble a labelled dataset of genuine and fabricated news articles so that the rest of the classification engine pipeline can depend on it. | 1. The team has assembled a labelled dataset of genuine and fabricated news articles. 2. Invalid or missing news articles are rejected with a clear message. 3. Behaviour is verified on a representative sample of news articles. 4. Errors are logged with enough context to debug them. | Highest | 8 | M. AASHRITHA | Sprint 2 | To Do | nlp,svm,classification
US-109 | Story | Classification Engine | Preprocess the text with tokenisation, stop-word removal | As a developer, I want to preprocess the text with tokenisation, stop-word removal, stemming and vectorisation so that the capability is available to the modules that follow. | 1. The team has preprocessed the text with tokenisation, stop-word removal, stemming and vectorisation. 2. The step runs end to end on the full project dataset. 3. Results are persisted and can be retrieved later. 4. The run is reproducible from a fixed configuration. | High | 8 | N. MOJES | Sprint 2 | To Do | nlp,svm,classification
US-110 | Story | Classification Engine | Apply Principal Component Analysis | As a system, I want to apply Principal Component Analysis to reduce feature dimensionality so that news articles are processed consistently. | 1. The system applies Principal Component Analysis to reduce feature dimensionality. 2. Configuration values are read from settings rather than hard-coded. 3. Edge cases found during testing are handled. 4. The content moderator can inspect the outcome. | High | 8 | NOOR SANIYA | Sprint 2 | To Do | nlp,svm,classification
US-111 | Story | Classification Engine | Use the Firefly algorithm | As a system, I want to use the Firefly algorithm to optimise feature selection and MSVM parameters so that the behaviour is correct for both typical and edge inputs. | 1. The system uses the Firefly algorithm to optimise feature selection and MSVM parameters. 2. Processing completes within the agreed time budget. 3. The module has unit tests covering its main paths. 4. The step is documented in the project README. | High | 8 | M. AKSHITHA | Sprint 3 | To Do | nlp,svm,classification
US-112 | Story | Classification Engine | Train a Multi-class Support Vector Machine classifier | As a developer, I want to train a Multi-class Support Vector Machine classifier on the optimised feature set so that later features can build on a dependable output. | 1. The team has trained a Multi-class Support Vector Machine classifier on the optimised feature set. 2. Invalid or missing news articles are rejected with a clear message. 3. Behaviour is verified on a representative sample of news articles. 4. Errors are logged with enough context to debug them. | High | 8 | M. AASHRITHA | Sprint 3 | To Do | nlp,svm,classification
US-113 | Story | Classification Engine | Evaluate accuracy, precision | As a developer, I want to evaluate accuracy, precision, recall and F1-score against unoptimised baselines so that the requirement can be demonstrated at review. | 1. The team has evaluated accuracy, precision, recall and F1-score against unoptimised baselines. 2. The step runs end to end on the full project dataset. 3. Results are persisted and can be retrieved later. 4. The run is reproducible from a fixed configuration. | High | 8 | N. MOJES | Sprint 3 | To Do | nlp,svm,classification
US-114 | Story | Classification Engine | Review classification engine output | As a reader, I want to review the classification engine output in the interface so that I can confirm it before acting on it. | 1. The most recent output is shown together with its inputs. 2. The reader can flag an incorrect result. 3. Flagged items are queued for the content moderator to check. | Medium | 5 | NOOR SANIYA | Sprint 2 | To Do | nlp,backend
US-115 | Task | Classification Engine | Retry and logging for classification engine | As a system, I want to retry and log failures in classification engine so that a transient error does not lose data. | 1. Failed operations retry with backoff. 2. Repeated failures raise an alert. 3. Every failure is logged with its input reference. | Medium | 5 | M. AKSHITHA | Sprint 3 | To Do | nlp,backend
US-116 | Story | Classification Engine | Tune classification engine | As a developer, I want to tune classification engine on validation data so that accuracy improves before release. | 1. A parameter search is run and recorded. 2. Before and after metrics are compared. 3. The chosen settings are committed to the repository. | Medium | 5 | M. AASHRITHA | Sprint 3 | To Do | nlp,backend
US-117 | Task | Classification Engine | Expose classification engine through an API | As a developer, I want to expose classification engine through an internal API so that the interface and other modules can consume it. | 1. Endpoint documented with request and response examples. 2. Errors return meaningful status codes. 3. The endpoint is covered by an integration test. | Medium | 5 | N. MOJES | Sprint 3 | To Do | nlp,backend
US-118 | Story | Results and Reporting | Results dashboard | As a reader, I want a dashboard summarising the latest results so that I can understand the outcome at a glance. | 1. Key figures are shown with the date of the run. 2. Charts render correctly for an empty and a full dataset. 3. The dashboard loads within an acceptable time. | High | 5 | NOOR SANIYA | Sprint 4 | To Do | dashboard,frontend
US-119 | Story | Results and Reporting | Export report | As a content moderator, I want to export the results as PDF or CSV so that I can share them outside the system. | 1. The export includes the figures shown on screen. 2. The file name carries the project and the date. 3. Large exports complete without timing out. | Medium | 3 | M. AKSHITHA | Sprint 4 | To Do | export,reporting
US-120 | Story | Results and Reporting | History and search | As a reader, I want to search past records so that I can compare an earlier result with the current one. | 1. Records can be filtered by date and by status. 2. Search returns promptly on the full dataset. 3. An empty result set is shown clearly. | Medium | 3 | M. AASHRITHA | Sprint 4 | To Do | search,frontend
US-121 | Story | Notifications | Notify reader of an important outcome | As a reader, I want to be notified when the system produces an outcome needing my attention so that I can respond promptly. | 1. A notification is raised when the configured condition is met. 2. The reader can see the notification history. 3. Repeated notifications for the same event are suppressed. | Medium | 3 | N. MOJES | Sprint 4 | To Do | notification,alerts
US-122 | Spike | Evaluation | Define and measure evaluation metrics | Decide which metrics judge this project and measure the current build against them. | 1. Metrics chosen and justified for this problem. 2. Current scores recorded as a baseline. 3. A target for the final review is agreed. | Low | 3 | NOOR SANIYA | Sprint 5 | To Do | evaluation,research
US-123 | Task | Release | Deployment and user documentation | As a developer, I want the system deployed with setup and usage documentation so that the evaluators can run and demonstrate it. | 1. The application runs on the target environment. 2. Setup steps are documented and verified from scratch. 3. A short user guide covers the main workflow. | Low | 2 | M. AKSHITHA | Sprint 5 | To Do | deployment,docs

## Field Guide
BharatBuild — User Stories Excel Import Guide
Fields marked with * are mandatory. Assignee Roll No and Assignee Name must match a registered student in the selected batch.
Field | Mandatory | Example | Validation / Usage
Story ID | No | US-101 | Optional unique reference. BharatBuild may generate one if blank.
Work Type | Yes | Story | Allowed: Story, Task, Spike.
Epic | No | Authentication | Existing or importable epic/feature grouping.
Summary | Yes | Student Login and Authentication | Short title of the user story.
Description | Yes | As a student, I want to... | Detailed functional/user-story description.
Acceptance Criteria | Yes | 1. Valid login... | Use numbered lines in one cell.
Priority | Yes | High | Highest, High, Medium, Low, Lowest.
Story Points | Yes | 5 | Numeric estimate; recommended Fibonacci values such as 1,2,3,5,8,13.
Assignee Roll No | Yes | 23K91A05L5 | Must belong to the currently selected project batch.
Assignee Name | Yes | Royyala Sindhuja | Must match the student identified by Assignee Roll No.
Sprint | No | Sprint 1 | If blank, story remains unscheduled/backlog.
Status | Yes | To Do | Allowed: To Do, In Progress, In Review, Done.
Labels | No | authentication,frontend | Comma-separated tags.

## Import Process
Trainer Import Workflow
Step | Action | Expected Result
1 | Select Department → Section → Batch → Project | BharatBuild establishes project context.
2 | Open User Stories → Import Stories | Import wizard opens.
3 | Upload this Excel file | Columns are detected automatically.
4 | Map Excel columns | Excel fields are mapped to BharatBuild story fields.
5 | Validate | Missing mandatory data, duplicate IDs and invalid assignees are flagged.
6 | Preview | Trainer reviews stories and student assignments.
7 | Confirm Import | Valid stories are created under the selected project.