## User Stories Import
Story ID | Work Type * | Epic | Summary * | Description * | Acceptance Criteria * | Priority * | Story Points * | Assignee Name * | Sprint | Status * | Labels
US-101 | Story | Platform Access | Learner registration and login | As a learner, I want to register and sign in with my own credentials so that I can reach my workspace securely. | 1. Valid credentials sign the learner in. 2. Invalid credentials show a clear error. 3. A session is created and expires after inactivity. 4. Passwords are stored only as salted hashes. | High | 5 | Pittala Akhila | Sprint 1 | To Do | recsys,auth,frontend
US-102 | Story | Platform Access | Password reset | As a learner, I want to reset a forgotten password so that I can regain access without an administrator. | 1. A reset link or OTP is sent to the registered contact. 2. The link expires after a set time. 3. A new password can be saved and used to sign in. 4. Reset attempts are recorded in the audit log. | Medium | 3 | Mundala Sandhya | Sprint 1 | To Do | auth,security
US-103 | Story | Platform Access | Role-based access for course administrator | As a course administrator, I want a separate privileged view so that I can manage records without using a learner account. | 1. Learner and course administrator roles see different menus. 2. Privileged actions are refused for a normal learner. 3. Every privileged action is written to an audit trail. | High | 5 | Mula Thanuj Reddy | Sprint 1 | To Do | auth,rbac
US-104 | Story | Data Intake | Submit learner activity data | As a learner, I want to submit learner activity data to the system so that they can be processed. | 1. Supported formats are accepted and stored. 2. Unsupported or oversized input is refused with a reason. 3. Each submission is timestamped and linked to its owner. 4. A confirmation is shown once the upload completes. | Highest | 5 | Majjigapu Jagadeshwar Reddy | Sprint 1 | To Do | recsys,ingestion
US-105 | Story | Data Intake | Validate and clean learner activity data | As a system, I want to validate and clean incoming learner activity data so that poor quality input does not corrupt later stages. | 1. Missing and malformed fields are detected. 2. Duplicates are removed before processing. 3. A validation summary is available for each batch. 4. Rejected records are retained for review. | High | 5 | Pittala Akhila | Sprint 1 | To Do | validation,data
US-106 | Task | Data Intake | Project repository and environment setup | As a developer, I want a version-controlled repository with a reproducible environment so that the whole team builds on the same base. | 1. Repository created and branch rules agreed. 2. Dependencies pinned in a requirements file. 3. The project runs from a clean checkout by following the README. | Medium | 3 | Mundala Sandhya | Sprint 1 | To Do | setup,devops
US-107 | Spike | Recommendation Engine | Evaluate approaches for recommendation engine | Research candidate approaches for recommendation engine and record which one this project adopts. The surveyed work moves from prediction to prescriptive learning path optimisation. The gap is combining collaborative and content-based signals in a deployable platform that also. | 1. At least three approaches are compared. 2. Strengths and limits of each are written up. 3. A recommendation with reasons is recorded. | Low | 3 | Mula Thanuj Reddy | Sprint 2 | To Do | research,spike
US-108 | Story | Recommendation Engine | Build learner profiles capturing interests, current skills | As a developer, I want to build learner profiles capturing interests, current skills, goals and completed courses so that the rest of the recommendation engine pipeline can depend on it. | 1. The delivered system provides learner profiles capturing interests, current skills, goals and completed courses. 2. Invalid or missing learner activity data are rejected with a clear message. 3. Behaviour is verified on a representative sample of learner activity data. 4. Errors are logged with enough context to debug them. | Highest | 8 | Majjigapu Jagadeshwar Reddy | Sprint 2 | To Do | recsys,edtech,ml
US-109 | Story | Recommendation Engine | Construct a course catalogue with topic, level | As a system, I want to construct a course catalogue with topic, level, prerequisite and outcome metadata so that the capability is available to the modules that follow. | 1. The delivered system provides a course catalogue with topic, level, prerequisite and outcome metadata. 2. The step runs end to end on the full project dataset. 3. Results are persisted and can be retrieved later. 4. The run is reproducible from a fixed configuration. | High | 8 | Pittala Akhila | Sprint 2 | To Do | recsys,edtech,ml
US-110 | Story | Recommendation Engine | Implement collaborative filtering over learner interaction | As a developer, I want to implement collaborative filtering over learner interaction history so that learner activity data are processed consistently. | 1. The delivered system provides collaborative filtering over learner interaction history. 2. Configuration values are read from settings rather than hard-coded. 3. Edge cases found during testing are handled. 4. The course administrator can inspect the outcome. | High | 8 | Mundala Sandhya | Sprint 2 | To Do | recsys,edtech,ml
US-111 | Story | Recommendation Engine | Implement content-based matching between learner profile | As a developer, I want to implement content-based matching between learner profile and course metadata so that the behaviour is correct for both typical and edge inputs. | 1. The delivered system provides content-based matching between learner profile and course metadata. 2. Processing completes within the agreed time budget. 3. The module has unit tests covering its main paths. 4. The step is documented in the project README. | High | 8 | Mula Thanuj Reddy | Sprint 3 | To Do | recsys,edtech,ml
US-112 | Story | Recommendation Engine | Combine both into a hybrid recommender | As a system, I want to combine both into a hybrid recommender and order the output into a coherent learning path so that later features can build on a dependable output. | 1. The system combines both into a hybrid recommender and order the output into a coherent learning path. 2. Invalid or missing learner activity data are rejected with a clear message. 3. Behaviour is verified on a representative sample of learner activity data. 4. Errors are logged with enough context to debug them. | High | 8 | Majjigapu Jagadeshwar Reddy | Sprint 3 | To Do | recsys,edtech,ml
US-113 | Story | Recommendation Engine | Evaluate using precision, recall | As a developer, I want to evaluate using precision, recall and learner feedback on recommendation relevance so that the requirement can be demonstrated at review. | 1. The team has evaluated using precision, recall and learner feedback on recommendation relevance. 2. The step runs end to end on the full project dataset. 3. Results are persisted and can be retrieved later. 4. The run is reproducible from a fixed configuration. | High | 8 | Pittala Akhila | Sprint 3 | To Do | recsys,edtech,ml
US-114 | Story | Recommendation Engine | Review recommendation engine output | As a learner, I want to review the recommendation engine output in the interface so that I can confirm it before acting on it. | 1. The most recent output is shown together with its inputs. 2. The learner can flag an incorrect result. 3. Flagged items are queued for the course administrator to check. | Medium | 5 | Mundala Sandhya | Sprint 2 | To Do | recsys,backend
US-115 | Task | Recommendation Engine | Retry and logging for recommendation engine | As a system, I want to retry and log failures in recommendation engine so that a transient error does not lose data. | 1. Failed operations retry with backoff. 2. Repeated failures raise an alert. 3. Every failure is logged with its input reference. | Medium | 5 | Mula Thanuj Reddy | Sprint 3 | To Do | recsys,backend
US-116 | Story | Recommendation Engine | Tune recommendation engine | As a developer, I want to tune recommendation engine on validation data so that accuracy improves before release. | 1. A parameter search is run and recorded. 2. Before and after metrics are compared. 3. The chosen settings are committed to the repository. | Medium | 5 | Majjigapu Jagadeshwar Reddy | Sprint 3 | To Do | recsys,backend
US-117 | Task | Recommendation Engine | Expose recommendation engine through an API | As a developer, I want to expose recommendation engine through an internal API so that the interface and other modules can consume it. | 1. Endpoint documented with request and response examples. 2. Errors return meaningful status codes. 3. The endpoint is covered by an integration test. | Medium | 5 | Pittala Akhila | Sprint 3 | To Do | recsys,backend
US-118 | Story | Results and Reporting | Results dashboard | As a learner, I want a dashboard summarising the latest results so that I can understand the outcome at a glance. | 1. Key figures are shown with the date of the run. 2. Charts render correctly for an empty and a full dataset. 3. The dashboard loads within an acceptable time. | High | 5 | Mundala Sandhya | Sprint 4 | To Do | dashboard,frontend
US-119 | Story | Results and Reporting | Export report | As a course administrator, I want to export the results as PDF or CSV so that I can share them outside the system. | 1. The export includes the figures shown on screen. 2. The file name carries the project and the date. 3. Large exports complete without timing out. | Medium | 3 | Mula Thanuj Reddy | Sprint 4 | To Do | export,reporting
US-120 | Story | Results and Reporting | History and search | As a learner, I want to search past records so that I can compare an earlier result with the current one. | 1. Records can be filtered by date and by status. 2. Search returns promptly on the full dataset. 3. An empty result set is shown clearly. | Medium | 3 | Majjigapu Jagadeshwar Reddy | Sprint 4 | To Do | search,frontend
US-121 | Story | Notifications | Notify learner of an important outcome | As a learner, I want to be notified when the system produces an outcome needing my attention so that I can respond promptly. | 1. A notification is raised when the configured condition is met. 2. The learner can see the notification history. 3. Repeated notifications for the same event are suppressed. | Medium | 3 | Pittala Akhila | Sprint 4 | To Do | notification,alerts
US-122 | Spike | Evaluation | Define and measure evaluation metrics | Decide which metrics judge this project and measure the current build against them. | 1. Metrics chosen and justified for this problem. 2. Current scores recorded as a baseline. 3. A target for the final review is agreed. | Low | 3 | Mundala Sandhya | Sprint 5 | To Do | evaluation,research
US-123 | Task | Release | Deployment and user documentation | As a developer, I want the system deployed with setup and usage documentation so that the evaluators can run and demonstrate it. | 1. The application runs on the target environment. 2. Setup steps are documented and verified from scratch. 3. A short user guide covers the main workflow. | Low | 2 | Mula Thanuj Reddy | Sprint 5 | To Do | deployment,docs

## Field Guide
BharatBuild — User Stories Excel Import Guide
Fields marked with * are mandatory. Assignee Roll No and Assignee Name must match a registered student in the selected batch.
Field | Mandatory | Example | Validation / Usage
Story ID | No | US-101 | Optional unique reference. BharatBuild may generate one if blank.
Work Type | Yes | Story | Allowed: Story, Task, Spike.
Epic | No | Authentication | Existing or importable epic/feature grouping.
Summary | Yes | Student Login and Authentication | Short title of the user story.
Description | Yes | As a student, I want to... | Detailed functional/user-story description.
Acceptance Criteria | Yes | 1. Valid login... | Use numbered lines in one cell.
Priority | Yes | High | Highest, High, Medium, Low, Lowest.
Story Points | Yes | 5 | Numeric estimate; recommended Fibonacci values such as 1,2,3,5,8,13.
Assignee Roll No | Yes | 23K91A05L5 | Must belong to the currently selected project batch.
Assignee Name | Yes | Royyala Sindhuja | Must match the student identified by Assignee Roll No.
Sprint | No | Sprint 1 | If blank, story remains unscheduled/backlog.
Status | Yes | To Do | Allowed: To Do, In Progress, In Review, Done.
Labels | No | authentication,frontend | Comma-separated tags.

## Import Process
Trainer Import Workflow
Step | Action | Expected Result
1 | Select Department → Section → Batch → Project | BharatBuild establishes project context.
2 | Open User Stories → Import Stories | Import wizard opens.
3 | Upload this Excel file | Columns are detected automatically.
4 | Map Excel columns | Excel fields are mapped to BharatBuild story fields.
5 | Validate | Missing mandatory data, duplicate IDs and invalid assignees are flagged.
6 | Preview | Trainer reviews stories and student assignments.
7 | Confirm Import | Valid stories are created under the selected project.