## User Stories Import
Story ID | Work Type * | Epic | Summary * | Description * | Acceptance Criteria * | Priority * | Story Points * | Assignee Name * | Sprint | Status * | Labels
US-101 | Story | Platform Access | Author registration and login | As a author, I want to register and sign in with my own credentials so that I can reach my workspace securely. | 1. Valid credentials sign the author in. 2. Invalid credentials show a clear error. 3. A session is created and expires after inactivity. 4. Passwords are stored only as salted hashes. | High | 5 | <Student 1> | Sprint 1 | To Do | nlp,auth,frontend
US-102 | Story | Platform Access | Password reset | As a author, I want to reset a forgotten password so that I can regain access without an administrator. | 1. A reset link or OTP is sent to the registered contact. 2. The link expires after a set time. 3. A new password can be saved and used to sign in. 4. Reset attempts are recorded in the audit log. | Medium | 3 | <Student 2> | Sprint 1 | To Do | auth,security
US-103 | Story | Platform Access | Role-based access for reviewer | As a reviewer, I want a separate privileged view so that I can manage records without using a author account. | 1. Author and reviewer roles see different menus. 2. Privileged actions are refused for a normal author. 3. Every privileged action is written to an audit trail. | High | 5 | <Student 3> | Sprint 1 | To Do | auth,rbac
US-104 | Story | Papers Intake | Submit submitted research papers | As a author, I want to submit submitted research papers to the system so that they can be processed. | 1. Supported formats are accepted and stored. 2. Unsupported or oversized input is refused with a reason. 3. Each submission is timestamped and linked to its owner. 4. A confirmation is shown once the upload completes. | Highest | 5 | <Student 4> | Sprint 1 | To Do | nlp,ingestion
US-105 | Story | Papers Intake | Validate and clean submitted research papers | As a system, I want to validate and clean incoming submitted research papers so that poor quality input does not corrupt later stages. | 1. Missing and malformed fields are detected. 2. Duplicates are removed before processing. 3. A validation summary is available for each batch. 4. Rejected records are retained for review. | High | 5 | <Student 1> | Sprint 1 | To Do | validation,data
US-106 | Task | Papers Intake | Project repository and environment setup | As a developer, I want a version-controlled repository with a reproducible environment so that the whole team builds on the same base. | 1. Repository created and branch rules agreed. 2. Dependencies pinned in a requirements file. 3. The project runs from a clean checkout by following the README. | Medium | 3 | <Student 2> | Sprint 1 | To Do | setup,devops
US-107 | Spike | Paper Evaluation | Evaluate approaches for paper evaluation | Research candidate approaches for paper evaluation and record which one this project adopts. The surveyed work performs auditable reviewer assignment using language models. The gap is combining that assignment with preliminary paper evaluation so both halves of the editorial. | 1. At least three approaches are compared. 2. Strengths and limits of each are written up. 3. A recommendation with reasons is recorded. | Low | 3 | <Student 3> | Sprint 2 | To Do | research,spike
US-108 | Story | Paper Evaluation | Build a corpus of submitted papers | As a developer, I want to build a corpus of submitted papers and reviewer publication profiles so that the rest of the paper evaluation pipeline can depend on it. | 1. The delivered system provides a corpus of submitted papers and reviewer publication profiles. 2. Invalid or missing submitted research papers are rejected with a clear message. 3. Behaviour is verified on a representative sample of submitted research papers. 4. Errors are logged with enough context to debug them. | Highest | 8 | <Student 4> | Sprint 2 | To Do | nlp,ai,review
US-109 | Story | Paper Evaluation | Extract topics, methods and keywords from paper text | As a system, I want to extract topics, methods and keywords from paper text using natural language processing so that the capability is available to the modules that follow. | 1. The system extracts topics, methods and keywords from paper text using natural language processing. 2. The step runs end to end on the full project dataset. 3. Results are persisted and can be retrieved later. 4. The run is reproducible from a fixed configuration. | High | 8 | <Student 1> | Sprint 2 | To Do | nlp,ai,review
US-110 | Story | Paper Evaluation | Represent reviewer expertise | As a system, I want to represent reviewer expertise from their publication history as comparable vectors so that submitted research papers are processed consistently. | 1. The system represents reviewer expertise from their publication history as comparable vectors. 2. Configuration values are read from settings rather than hard-coded. 3. Edge cases found during testing are handled. 4. The reviewer can inspect the outcome. | High | 8 | <Student 2> | Sprint 2 | To Do | nlp,ai,review
US-111 | Story | Paper Evaluation | Compute semantic similarity | As a system, I want to compute semantic similarity to rank candidate reviewers for each submission so that the behaviour is correct for both typical and edge inputs. | 1. The system computes semantic similarity to rank candidate reviewers for each submission. 2. Processing completes within the agreed time budget. 3. The module has unit tests covering its main paths. 4. The step is documented in the project README. | High | 8 | <Student 3> | Sprint 3 | To Do | nlp,ai,review
US-112 | Story | Paper Evaluation | Provide a preliminary quality assessment covering structure | As a system, I want to provide a preliminary quality assessment covering structure, novelty signals and completeness so that later features can build on a dependable output. | 1. The system provides a preliminary quality assessment covering structure, novelty signals and completeness. 2. Invalid or missing submitted research papers are rejected with a clear message. 3. Behaviour is verified on a representative sample of submitted research papers. 4. Errors are logged with enough context to debug them. | High | 8 | <Student 4> | Sprint 3 | To Do | nlp,ai,review
US-113 | Story | Paper Evaluation | Evaluate assignment quality against expert judgement | As a developer, I want to evaluate assignment quality against expert judgement and measure conflict-of-interest handling so that the requirement can be demonstrated at review. | 1. The team has evaluated assignment quality against expert judgement and measure conflict-of-interest handling. 2. The step runs end to end on the full project dataset. 3. Results are persisted and can be retrieved later. 4. The run is reproducible from a fixed configuration. | High | 8 | <Student 1> | Sprint 3 | To Do | nlp,ai,review
US-114 | Story | Paper Evaluation | Review paper evaluation output | As a author, I want to review the paper evaluation output in the interface so that I can confirm it before acting on it. | 1. The most recent output is shown together with its inputs. 2. The author can flag an incorrect result. 3. Flagged items are queued for the reviewer to check. | Medium | 5 | <Student 2> | Sprint 2 | To Do | nlp,backend
US-115 | Task | Paper Evaluation | Retry and logging for paper evaluation | As a system, I want to retry and log failures in paper evaluation so that a transient error does not lose data. | 1. Failed operations retry with backoff. 2. Repeated failures raise an alert. 3. Every failure is logged with its input reference. | Medium | 5 | <Student 3> | Sprint 3 | To Do | nlp,backend
US-116 | Story | Paper Evaluation | Tune paper evaluation | As a developer, I want to tune paper evaluation on validation data so that accuracy improves before release. | 1. A parameter search is run and recorded. 2. Before and after metrics are compared. 3. The chosen settings are committed to the repository. | Medium | 5 | <Student 4> | Sprint 3 | To Do | nlp,backend
US-117 | Task | Paper Evaluation | Expose paper evaluation through an API | As a developer, I want to expose paper evaluation through an internal API so that the interface and other modules can consume it. | 1. Endpoint documented with request and response examples. 2. Errors return meaningful status codes. 3. The endpoint is covered by an integration test. | Medium | 5 | <Student 1> | Sprint 3 | To Do | nlp,backend
US-118 | Story | Results and Reporting | Results dashboard | As a author, I want a dashboard summarising the latest results so that I can understand the outcome at a glance. | 1. Key figures are shown with the date of the run. 2. Charts render correctly for an empty and a full dataset. 3. The dashboard loads within an acceptable time. | High | 5 | <Student 2> | Sprint 4 | To Do | dashboard,frontend
US-119 | Story | Results and Reporting | Export report | As a reviewer, I want to export the results as PDF or CSV so that I can share them outside the system. | 1. The export includes the figures shown on screen. 2. The file name carries the project and the date. 3. Large exports complete without timing out. | Medium | 3 | <Student 3> | Sprint 4 | To Do | export,reporting
US-120 | Story | Results and Reporting | History and search | As a author, I want to search past records so that I can compare an earlier result with the current one. | 1. Records can be filtered by date and by status. 2. Search returns promptly on the full dataset. 3. An empty result set is shown clearly. | Medium | 3 | <Student 4> | Sprint 4 | To Do | search,frontend
US-121 | Story | Notifications | Notify author of an important outcome | As a author, I want to be notified when the system produces an outcome needing my attention so that I can respond promptly. | 1. A notification is raised when the configured condition is met. 2. The author can see the notification history. 3. Repeated notifications for the same event are suppressed. | Medium | 3 | <Student 1> | Sprint 4 | To Do | notification,alerts
US-122 | Spike | Evaluation | Define and measure evaluation metrics | Decide which metrics judge this project and measure the current build against them. | 1. Metrics chosen and justified for this problem. 2. Current scores recorded as a baseline. 3. A target for the final review is agreed. | Low | 3 | <Student 2> | Sprint 5 | To Do | evaluation,research
US-123 | Task | Release | Deployment and user documentation | As a developer, I want the system deployed with setup and usage documentation so that the evaluators can run and demonstrate it. | 1. The application runs on the target environment. 2. Setup steps are documented and verified from scratch. 3. A short user guide covers the main workflow. | Low | 2 | <Student 3> | Sprint 5 | To Do | deployment,docs

## Field Guide
BharatBuild — User Stories Excel Import Guide
Fields marked with * are mandatory. Assignee Roll No and Assignee Name must match a registered student in the selected batch.
Field | Mandatory | Example | Validation / Usage
Story ID | No | US-101 | Optional unique reference. BharatBuild may generate one if blank.
Work Type | Yes | Story | Allowed: Story, Task, Spike.
Epic | No | Authentication | Existing or importable epic/feature grouping.
Summary | Yes | Student Login and Authentication | Short title of the user story.
Description | Yes | As a student, I want to... | Detailed functional/user-story description.
Acceptance Criteria | Yes | 1. Valid login... | Use numbered lines in one cell.
Priority | Yes | High | Highest, High, Medium, Low, Lowest.
Story Points | Yes | 5 | Numeric estimate; recommended Fibonacci values such as 1,2,3,5,8,13.
Assignee Roll No | Yes | 23K91A05L5 | Must belong to the currently selected project batch.
Assignee Name | Yes | Royyala Sindhuja | Must match the student identified by Assignee Roll No.
Sprint | No | Sprint 1 | If blank, story remains unscheduled/backlog.
Status | Yes | To Do | Allowed: To Do, In Progress, In Review, Done.
Labels | No | authentication,frontend | Comma-separated tags.

## Import Process
Trainer Import Workflow
Step | Action | Expected Result
1 | Select Department → Section → Batch → Project | BharatBuild establishes project context.
2 | Open User Stories → Import Stories | Import wizard opens.
3 | Upload this Excel file | Columns are detected automatically.
4 | Map Excel columns | Excel fields are mapped to BharatBuild story fields.
5 | Validate | Missing mandatory data, duplicate IDs and invalid assignees are flagged.
6 | Preview | Trainer reviews stories and student assignments.
7 | Confirm Import | Valid stories are created under the selected project.