## User Stories Import
Story ID | Work Type * | Epic | Summary * | Description * | Acceptance Criteria * | Priority * | Story Points * | Assignee Name * | Sprint | Status * | Labels
US-101 | Story | Platform Access | Customer registration and login | As a customer, I want to register and sign in with my own credentials so that I can reach my workspace securely. | 1. Valid credentials sign the customer in. 2. Invalid credentials show a clear error. 3. A session is created and expires after inactivity. 4. Passwords are stored only as salted hashes. | High | 5 | MOHD AHMED | Sprint 1 | To Do | fintech,auth,frontend
US-102 | Story | Platform Access | Password reset | As a customer, I want to reset a forgotten password so that I can regain access without an administrator. | 1. A reset link or OTP is sent to the registered contact. 2. The link expires after a set time. 3. A new password can be saved and used to sign in. 4. Reset attempts are recorded in the audit log. | Medium | 3 | MANNE UPENDER | Sprint 1 | To Do | auth,security
US-103 | Story | Platform Access | Role-based access for financial analyst | As a financial analyst, I want a separate privileged view so that I can manage records without using a customer account. | 1. Customer and financial analyst roles see different menus. 2. Privileged actions are refused for a normal customer. 3. Every privileged action is written to an audit trail. | High | 5 | PADALA RAJESH | Sprint 1 | To Do | auth,rbac
US-104 | Story | Records Intake | Submit demographic and financial records | As a customer, I want to submit demographic and financial records to the system so that they can be processed. | 1. Supported formats are accepted and stored. 2. Unsupported or oversized input is refused with a reason. 3. Each submission is timestamped and linked to its owner. 4. A confirmation is shown once the upload completes. | Highest | 5 | M HARSHAVARDHAN GOUD | Sprint 1 | To Do | fintech,ingestion
US-105 | Story | Records Intake | Validate and clean demographic and financial records | As a system, I want to validate and clean incoming demographic and financial records so that poor quality input does not corrupt later stages. | 1. Missing and malformed fields are detected. 2. Duplicates are removed before processing. 3. A validation summary is available for each batch. 4. Rejected records are retained for review. | High | 5 | MOHD AHMED | Sprint 1 | To Do | validation,data
US-106 | Task | Records Intake | Project repository and environment setup | As a developer, I want a version-controlled repository with a reproducible environment so that the whole team builds on the same base. | 1. Repository created and branch rules agreed. 2. Dependencies pinned in a requirements file. 3. The project runs from a clean checkout by following the README. | Medium | 3 | MANNE UPENDER | Sprint 1 | To Do | setup,devops
US-107 | Spike | Financial Forecasting | Evaluate approaches for financial forecasting | Research candidate approaches for financial forecasting and record which one this project adopts. The surveyed work applies explainable machine learning to organisational financial distress. The gap is extending the same approach to individual profiling where demographic context. | 1. At least three approaches are compared. 2. Strengths and limits of each are written up. 3. A recommendation with reasons is recorded. | Low | 3 | PADALA RAJESH | Sprint 2 | To Do | research,spike
US-108 | Story | Financial Forecasting | Collect a dataset combining demographic attributes | As a system, I want to collect a dataset combining demographic attributes with financial and transactional parameters so that the rest of the financial forecasting pipeline can depend on it. | 1. The system collects a dataset combining demographic attributes with financial and transactional parameters. 2. Invalid or missing demographic and financial records are rejected with a clear message. 3. Behaviour is verified on a representative sample of demographic and financial records. 4. Errors are logged with enough context to debug them. | Highest | 8 | M HARSHAVARDHAN GOUD | Sprint 2 | To Do | fintech,analytics,ml
US-109 | Story | Financial Forecasting | Preprocess the data, handle missing values | As a developer, I want to preprocess the data, handle missing values and encode categorical demographic fields so that the capability is available to the modules that follow. | 1. The team has preprocessed the data, handle missing values and encode categorical demographic fields. 2. The step runs end to end on the full project dataset. 3. Results are persisted and can be retrieved later. 4. The run is reproducible from a fixed configuration. | High | 8 | MOHD AHMED | Sprint 2 | To Do | fintech,analytics,ml
US-110 | Story | Financial Forecasting | Train models to classify financial profile | As a developer, I want to train models to classify financial profile and estimate credit or distress risk so that demographic and financial records are processed consistently. | 1. The team has trained models to classify financial profile and estimate credit or distress risk. 2. Configuration values are read from settings rather than hard-coded. 3. Edge cases found during testing are handled. 4. The financial analyst can inspect the outcome. | High | 8 | MANNE UPENDER | Sprint 2 | To Do | fintech,analytics,ml
US-111 | Story | Financial Forecasting | Build a forecasting component | As a developer, I want to build a forecasting component that projects future financial position so that the behaviour is correct for both typical and edge inputs. | 1. The delivered system provides a forecasting component that projects future financial position. 2. Processing completes within the agreed time budget. 3. The module has unit tests covering its main paths. 4. The step is documented in the project README. | High | 8 | PADALA RAJESH | Sprint 3 | To Do | fintech,analytics,ml
US-112 | Story | Financial Forecasting | Add an explainability layer showing | As a developer, I want to add an explainability layer showing which factors drove each assessment so that later features can build on a dependable output. | 1. The delivered system provides an explainability layer showing which factors drove each assessment. 2. Invalid or missing demographic and financial records are rejected with a clear message. 3. Behaviour is verified on a representative sample of demographic and financial records. 4. Errors are logged with enough context to debug them. | High | 8 | M HARSHAVARDHAN GOUD | Sprint 3 | To Do | fintech,analytics,ml
US-113 | Story | Financial Forecasting | Evaluate using accuracy, precision, recall and ROC-AUC | As a developer, I want to evaluate using accuracy, precision, recall and ROC-AUC, and deploy through a web interface so that the requirement can be demonstrated at review. | 1. The team has evaluated using accuracy, precision, recall and ROC-AUC, and deploy through a web interface. 2. The step runs end to end on the full project dataset. 3. Results are persisted and can be retrieved later. 4. The run is reproducible from a fixed configuration. | High | 8 | MOHD AHMED | Sprint 3 | To Do | fintech,analytics,ml
US-114 | Story | Financial Forecasting | Review financial forecasting output | As a customer, I want to review the financial forecasting output in the interface so that I can confirm it before acting on it. | 1. The most recent output is shown together with its inputs. 2. The customer can flag an incorrect result. 3. Flagged items are queued for the financial analyst to check. | Medium | 5 | MANNE UPENDER | Sprint 2 | To Do | fintech,backend
US-115 | Task | Financial Forecasting | Retry and logging for financial forecasting | As a system, I want to retry and log failures in financial forecasting so that a transient error does not lose data. | 1. Failed operations retry with backoff. 2. Repeated failures raise an alert. 3. Every failure is logged with its input reference. | Medium | 5 | PADALA RAJESH | Sprint 3 | To Do | fintech,backend
US-116 | Story | Financial Forecasting | Tune financial forecasting | As a developer, I want to tune financial forecasting on validation data so that accuracy improves before release. | 1. A parameter search is run and recorded. 2. Before and after metrics are compared. 3. The chosen settings are committed to the repository. | Medium | 5 | M HARSHAVARDHAN GOUD | Sprint 3 | To Do | fintech,backend
US-117 | Task | Financial Forecasting | Expose financial forecasting through an API | As a developer, I want to expose financial forecasting through an internal API so that the interface and other modules can consume it. | 1. Endpoint documented with request and response examples. 2. Errors return meaningful status codes. 3. The endpoint is covered by an integration test. | Medium | 5 | MOHD AHMED | Sprint 3 | To Do | fintech,backend
US-118 | Story | Results and Reporting | Results dashboard | As a customer, I want a dashboard summarising the latest results so that I can understand the outcome at a glance. | 1. Key figures are shown with the date of the run. 2. Charts render correctly for an empty and a full dataset. 3. The dashboard loads within an acceptable time. | High | 5 | MANNE UPENDER | Sprint 4 | To Do | dashboard,frontend
US-119 | Story | Results and Reporting | Export report | As a financial analyst, I want to export the results as PDF or CSV so that I can share them outside the system. | 1. The export includes the figures shown on screen. 2. The file name carries the project and the date. 3. Large exports complete without timing out. | Medium | 3 | PADALA RAJESH | Sprint 4 | To Do | export,reporting
US-120 | Story | Results and Reporting | History and search | As a customer, I want to search past records so that I can compare an earlier result with the current one. | 1. Records can be filtered by date and by status. 2. Search returns promptly on the full dataset. 3. An empty result set is shown clearly. | Medium | 3 | M HARSHAVARDHAN GOUD | Sprint 4 | To Do | search,frontend
US-121 | Story | Notifications | Notify customer of an important outcome | As a customer, I want to be notified when the system produces an outcome needing my attention so that I can respond promptly. | 1. A notification is raised when the configured condition is met. 2. The customer can see the notification history. 3. Repeated notifications for the same event are suppressed. | Medium | 3 | MOHD AHMED | Sprint 4 | To Do | notification,alerts
US-122 | Spike | Evaluation | Define and measure evaluation metrics | Decide which metrics judge this project and measure the current build against them. | 1. Metrics chosen and justified for this problem. 2. Current scores recorded as a baseline. 3. A target for the final review is agreed. | Low | 3 | MANNE UPENDER | Sprint 5 | To Do | evaluation,research
US-123 | Task | Release | Deployment and user documentation | As a developer, I want the system deployed with setup and usage documentation so that the evaluators can run and demonstrate it. | 1. The application runs on the target environment. 2. Setup steps are documented and verified from scratch. 3. A short user guide covers the main workflow. | Low | 2 | PADALA RAJESH | Sprint 5 | To Do | deployment,docs

## Field Guide
BharatBuild — User Stories Excel Import Guide
Fields marked with * are mandatory. Assignee Roll No and Assignee Name must match a registered student in the selected batch.
Field | Mandatory | Example | Validation / Usage
Story ID | No | US-101 | Optional unique reference. BharatBuild may generate one if blank.
Work Type | Yes | Story | Allowed: Story, Task, Spike.
Epic | No | Authentication | Existing or importable epic/feature grouping.
Summary | Yes | Student Login and Authentication | Short title of the user story.
Description | Yes | As a student, I want to... | Detailed functional/user-story description.
Acceptance Criteria | Yes | 1. Valid login... | Use numbered lines in one cell.
Priority | Yes | High | Highest, High, Medium, Low, Lowest.
Story Points | Yes | 5 | Numeric estimate; recommended Fibonacci values such as 1,2,3,5,8,13.
Assignee Roll No | Yes | 23K91A05L5 | Must belong to the currently selected project batch.
Assignee Name | Yes | Royyala Sindhuja | Must match the student identified by Assignee Roll No.
Sprint | No | Sprint 1 | If blank, story remains unscheduled/backlog.
Status | Yes | To Do | Allowed: To Do, In Progress, In Review, Done.
Labels | No | authentication,frontend | Comma-separated tags.

## Import Process
Trainer Import Workflow
Step | Action | Expected Result
1 | Select Department → Section → Batch → Project | BharatBuild establishes project context.
2 | Open User Stories → Import Stories | Import wizard opens.
3 | Upload this Excel file | Columns are detected automatically.
4 | Map Excel columns | Excel fields are mapped to BharatBuild story fields.
5 | Validate | Missing mandatory data, duplicate IDs and invalid assignees are flagged.
6 | Preview | Trainer reviews stories and student assignments.
7 | Confirm Import | Valid stories are created under the selected project.